{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Тек. проекты"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Тек. проекты","index":0,"n_rows":13,"n_cols":23,"rows_kept":13,"cut":false,"hidden":false,"merged":[[1,19,2,19],[1,20,2,20],[1,21,2,21],[1,22,2,22],[1,13,2,13],[1,14,2,14],[1,15,2,15],[1,16,2,16],[1,17,2,17],[1,18,2,18],[1,12,2,12],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,2,5],[1,6,2,6],[1,7,1,8],[1,9,2,9],[1,10,2,10],[1,11,2,11]]}
[]
[null,"№","Дата  поступления объекта","Заказчик","Город","Наименование (адрес) объекта","Вид работ на объекте","Планируемые сроки СМР",null,"Требования по БГ","Аванс, %","Дата передачи КП","Сумма контракта","На какой стадии объект сейчас","Какой результат планируем получить в ближайшее время","Дата получения планируемого результата","Предполагаемая дата подписания договора","Вероятность подписания договора","Примечание","Дата контакта","Необходимые действия","Контактное лицо","Ответственный"]
[null,null,null,null,null,null,null,"От","До"]
["Т",1,null,"Больше","Москва","Ленинградский ",null,"2014-12-01","2015-05-01",null,"нет",null,null,"Договор","Будет подписан до…","2014-10-20","2014-10-01",1,null,"2014-10-20"]
["Т",2,"2014-09-04","Строй","Москва","Измайловский ",null,"2014-10-01","2014-11-01","Нет инфо",0.7,"2014-09-29",null,"Договор","Будет подписан до…","2014-10-20","2014-10-01",1,null,"2014-10-20"]
["Т",3,"2014-08-21","Кардиологи","иван","Черепковская ",null,"2014-11-01","2015-02-01","Обязательное предоставление","нет","2014-09-05",null,"Договор","Будет подписан до…","2014-10-24","2014-10-01",1,null,"2014-10-24"]
["Т",4,"2014-06-16","УГС","Москва","Авиаторов",null,"2014-11-01","2014-12-01",null,0.70513000000000003,"2014-10-06",null,"Договор","Будет подписан до…","2014-10-20","2014-10-01",1,null,"2014-10-20"]
["Т",5,"2014-09-04","Сбербанк","Москва","Вавилова",null,"2014-10-01","2014-12-01","Нет инфо",null,"2014-09-16",null,"Договор","Будет подписан до…","2014-10-24","2014-10-01",1,null,"2014-10-24"]
[null,6,null,"КФК","Москва","депо",null,"2014-11-01","2014-12-01",null,"нет",null,null,"Договор","Будет подписан до…","2014-10-27","2014-10-01",1,null,"2014-10-27"]
["Т",7,"2014-09-15","Автокомбинат","Москва","Хорошевское ",null,null,null,"Обязательное предоставление",0.48188999999999999,"2014-09-11",null,"Договор","Будет подписан до…","2014-10-24","2014-10-01",1,null,"2014-10-24"]
["Т",8,"2014-09-15","Автокомбинат ","Москва","Хорошевское",null,null,null,"Обязательное предоставление",null,null,null,"Готовится КП","Будет готово к…","2014-10-24",null,null,null,"2014-10-24"]
["Т",9,"2014-09-01","аэродромов, ФГУП","Химки г., МО","Аэропорт",null,"2014-10-01",null,"Нет инфо",null,null,null,"Договор","Будет подписан до…","2014-10-24","2014-10-01",1,null,"2014-10-24"]
["Т",10,"2014-08-19","ИНФИНТРА","Москва","Пионерская",null,"2014-10-01","2015-10-01",null,null,"2014-09-16",null,"Договор","Будет подписан до…","2014-10-24",null,null,null,"2014-10-24"]