{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["RioForged"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"RioForged","index":0,"n_rows":51,"n_cols":22,"rows_kept":51,"cut":false,"hidden":false,"merged":[[1,9,1,11],[1,13,1,15],[1,17,1,19],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,5,2,5],[1,6,2,6],[1,7,2,7]]}
[]
[null,"№ п./п.","Наименование работ","Ед. изм.",null,"Объем работ по проекту","Выполнено на начало планового месяца","Объем работ по набору",null,"Выполнено с начала месяца",null,null,null,"Выполнено за отчётный период",null,null,null,"Выполнено за прошедшие сутки",null,null,null,"Примечания"]
[null,null,null,null,null,null,null,null,null,"ПЛАН","ФАКТ","Отклонение",null,"ПЛАН","ФАКТ","Отклонение",null,"ПЛАН","ФАКТ","Отклонение"]
[null,{"$f":"Rio_Mark($B$4)","v":"1"},null,null,null,null,null,null,"Наименование подрядной организации 1"]
[null,{"$f":"Rio_Mark($B$4)","v":"1.1"},null,null,null,null,null,null,"Наименование объекта 1"]
[null,"1.1.1","Вид работ 1","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.2","Вид работ 2","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.3","Вид работ 3","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.4","Вид работ 4","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.5","Вид работ 5","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.6","Вид работ 6","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.7","Вид работ 7","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.8","Вид работ 8","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.9","Вид работ 9","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.10","Вид работ 10","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.1.11","Вид работ 11","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2",null,null,null,null,null,null,"Наименование объекта 2"]
[null,"1.2.1","Вид работ 1","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.2","Вид работ 2","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.3","Вид работ 3","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.4","Вид работ 4","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.5","Вид работ 5","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.6","Вид работ 6","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.7","Вид работ 7","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.8","Вид работ 8","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.9","Вид работ 9","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.10","Вид работ 10","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.11","Вид работ 11","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"1.2.12","Вид работ 12","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2",null,null,null,null,null,null,"Наименование подрядной организации 2"]
[null,"2.1",null,null,null,null,null,null,"Наименование объекта 1"]
[null,"2.1.1","Вид работ 1","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.2","Вид работ 2","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.3","Вид работ 3","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.4","Вид работ 4","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.5","Вид работ 5","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.6","Вид работ 6","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.7","Вид работ 7","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.8","Вид работ 8","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.9","Вид работ 9","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.10","Вид работ 10","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.11","Вид работ 11","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.12","Вид работ 12","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.1.13","Вид работ 13","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.2",null,null,null,null,null,null,"Наименование объекта 2"]
[null,"2.2.1","Вид работ 20","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.2.2","Вид работ 24","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.2.3","Вид работ 25","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.2.4","Вид работ 26","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.2.5","Вид работ 27","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]
[null,"2.2.6","Вид работ 28","Ед. изм.",null,10,2,8,null,6,4,-2,null,6,4,-2,null,1,1,0]