{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Реестр","Лог"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":7,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Реестр","index":0,"n_rows":41,"n_cols":19,"rows_kept":41,"cut":false,"hidden":false,"merged":[]}
[0,1,2,3,4,5,6,7,9,10,11,12,13,15,"2015-08-17","2015-08-17","2015-08-17","2015-08-17",16]
["№ п\\п","Цех","Исх_№","Дата\\исх","Вх_№","Дата\\вх","Кол-во позиций в заявке","Приоритет","Состояние по исполнению заявки на текущую дату","Поставщик","Документ на согласованис (сп\\счет-д.\\договор)","Датад\\с","Кол-во отработанных позиций","Начальная Дата  согласования службами завода","Дата начала договорных обязательств","Планируемая дата поставки","Фактическая дата поставки","Обеспечение ЦИСа","Примечание"]
[12,34,458,"2014-12-23",3865,"2014-12-24",17,null,null,"Гагарин-Инжиниринг",392,"2015-06-01",3,"2015-06-09",null,null,"2015-08-25"]
[13,34,458,"2014-12-23",3865,"2014-12-24",17,null,null,"Зерги",5,"2015-06-01",7,"2015-06-09"]
[14,34,458,"2014-12-23",3865,"2014-12-24",17,null,null,"Привет","С-0000415","2015-05-25",4,"2015-06-09",null,null,"2015-07-07"]
[15,34,458,"2014-12-23",3865,"2014-12-24",17,null,null,"Светлячок",23,"2015-05-13",1,"2015-06-09"]
[10,28,248,"2014-12-25",3908,"2014-12-30",7,null,"Р/З/И - 01.2015"]
[35,"046",2900,"2014-12-25",142,"2015-01-26",1,null,null,"Шеффманн",7,"2015-02-12",1,"2015-03-05",null,null,"2015-06-17"]
[36,"ПК2",40,"2015-01-14",16,"2015-01-15",2,null,null,"Гагарин-инжиниринг",346,"2015-01-22",2,"2015-01-22",null,null,"2015-03-24"]
[25,300,54,"2015-01-22",54,"2015-01-22",12,"А",null,"СПб Инэнэн",32,"2015-03-16",12,"2015-03-18",null,null,"2015-05-14"]
[29,"003",88,"2015-01-23",147,"2015-01-27",2,null,null,"Рога и копыта",357,"2015-02-17",2,"2015-02-18",null,null,"2015-04-29"]
[28,"003",90,"2015-01-23",149,"2015-01-27",4,null,null,"ООО Рога и копыта",348,"2015-01-29",4,"2015-02-11",null,null,"2015-03-30"]
[34,"046",123,"2015-01-23",144,"2015-01-27",5,null,null,"Нордэц",192,"2015-02-02",5,"2015-03-18"]
[26,300,68,"2015-01-26",68,"2015-01-26",2,null,"Р/З/И - 02.2015"]
[33,"032",44,"2015-02-04",260,"2015-02-06",1,null,null,"ООО \"Треант\"",25,"2015-03-03",1,"2015-03-04",null,null,"2015-05-14"]
[32,"018",7,"2015-02-09",281,"2015-02-09",1,null,null,"СнобИн","С-0000101 ","2015-02-10",1,"2015-02-12",null,null,"2015-03-19"]
[3,7,330,"2015-02-20",956,"2015-04-30",1]
[2,7,333,"2015-02-20",954,"2015-04-30",2,null,null,"Пряник",189,"2015-06-16",2,"2015-06-29",null,null,"2015-09-15"]
[31,"007",377,"2015-02-26",508,"2015-03-03",1,null,null,"Пряник",170,"2015-03-10",1,"2015-03-16",null,null,"2015-09-25"]
[30,"003",401,"2015-03-05",534,"2015-03-10",62,null,"Р/З/И - 04.2015"]
[20,46,536,"2015-03-05",538,"2015-03-10",34,null,"Р/З/И - 03.2015"]
[4,21,94,"2015-03-16",599,"2015-03-18",6,null,null,"Маккофе","С-0000227","2015-03-20",1,"2015-04-04",null,null,"2015-05-14"]
[5,21,94,"2015-03-16",599,"2015-03-18",6,null,null,"Нескафе",15,"2015-03-23",2,"2015-04-04"]
[6,21,94,"2015-03-16",599,"2015-03-18",6,null,null,"Чибо",270,"2015-03-26",3,"2015-04-04"]
[18,42,88,"2015-03-17",617,"2015-03-20",1,null,"Р/З/И - 04.2015"]
[21,75,151,"2015-03-24",631,"2015-03-24",2,null,null,"ДЦ Арбуз",15,"2015-03-25",2,"2015-04-01",null,null,"2015-05-07"]
[7,28,90,"2015-03-25",685,"2015-03-30",27,null,null,"Маккофе",182,"2015-04-28",10,"2015-05-14",null,null,"2015-07-24"]
[8,28,90,"2015-03-25",685,"2015-03-30",27,null,null,"Нескафе",18,"2015-04-29",6,"2015-05-14",null,null,"2015-07-07"]
[9,28,90,"2015-03-25",685,"2015-03-30",27,null,null,"Чибо",20,"2015-04-29",11,"2015-05-14"]
[11,32,121,"2015-03-25",663,"2015-03-26",2,null,null,"Дубок","С-0000254","2015-03-30",2,"2015-04-04",null,null,"2015-05-14"]
[37,"ПК2",1169,"2015-03-26",682,"2015-03-30",23,null,"Р/З/И - 04.2015"]
[38,"ПК2",1232,"2015-03-31",696,"2015-03-31",6,null,null,"НаноТехПром","5 (15259-1232)","2015-04-06",5,"2015-04-11",null,null,"2015-05-14"]
[39,"ПК2",1232,"2015-03-31",696,"2015-03-31",6,null,null,"Шеффманн",12,"2015-04-03",1,"2015-04-11",null,null,"2015-06-29"]
[22,75,221,"2015-04-16",987,"2015-05-06",2,null,null,"Саратовтим",2334,"2015-05-13",2,"2015-05-21"]
[16,42,171,"2015-06-03",1224,"2015-06-08",2,null,null,"Нордэц",1101,"2015-06-09",1,"2015-08-08",null,null,"2015-08-13"]
[17,42,171,"2015-06-03",1224,"2015-06-08",2,"А",null,"уралтвердит","СПб/0762","2015-06-09",1,"2015-08-08",null,null,"2015-07-21","ч/о"]
[24,300,633,"2015-06-24",633,"2015-06-24",7,null,null,"ООО Пряник",192,"2015-06-29",7,"2015-07-03",null,null,"2015-09-15","ч/о"]
[23,300,664,"2015-07-01",664,"2015-07-01",6,null,null,"Рога и копыта",31,"2015-08-03",6,"2015-08-08",null,null,"2015-08-13"]
[1,3,1400,"2015-07-10",1499,"2015-07-13",1,null,null,"ООО Кукурузка",20487,"2015-08-14",6,"2015-08-18"]
[19,42,252,"2015-08-07",1747,"2015-08-11",3]
[27,300,865,"2015-08-18",1802,"2015-08-18",129,null,"Р/З/И - 09.2015"]

{"sheet":"Лог","index":1,"n_rows":1,"n_cols":3,"rows_kept":1,"cut":false,"hidden":true,"merged":[]}
["Пользователь","Вошел","Вышел"]