## DST
Shipment Number | Shipment Type | Container number | Deconsol | Deconsol Arrival Date | Final Delivery Date | Final Delivery Hour | Final Delivery Ref | Sales Order Number | Sales Order Item Number | MATCH | Division Code | Material Number | Material Description | Order Quantity | Shipped quantity | Number Of Cartons | Actual Discharge Date | Discharge Date Confirmed | First Possible Delivery Date | Customs Status Date | Customer Name | Customer PO | Customer Request Date | Need Month | Delivery Remarks | Transportation Mode | Xref | Ship-to Customer Number | Seal | Origin Location | Purchase Order Number | Purchase Order Item Number | Purchase Order Quantity | Vas At Factory | Original Delivery Date | Customer Confirmed Date | Customer Cancellation Date | Expected Discharge Date | ready to ship date | weekday | FPDD | cust po date | KL | PO type | caselot idp dt | caselot bd emp | caselot mono check | mono & caselot pairs | Arrival 2nd Loc Date | Delivery Volume | Purchase Order Factory Country
93032254 | Z040 | KKFU1145814 | TDS | 2015-11-18 | 2016-01-08 | 12:00 |  | 0703249268 | 20 | 070324926820 | 10 | 340225-010 | NIKE METAL SWOOSH H86 - BLUE | 11121 | 11121 | 133 | 2015-11-11 | N | 2016-01-01 | 2015-11-11 | SPORTMASTER LLC | RDSSRU00066036MP | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | CBL01282 | 58309 | 4503637403 | 20 | 11121 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-11 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-17 |  | Bin |  |  | OK |  | 2015-11-13 | 14.02 | TW
93032225 | Z040 | KKFU1145814 | TDS | 2015-11-18 | 2016-01-08 | 12:00 |  | 0704040507 | 20 | 070404050720 | 10 | 340225-451 | NIKE METAL SWOOSH H86 - BLUE | 10077 | 10077 | 120 | 2015-11-11 | N | 2016-01-01 | 2015-11-11 | SPORTMASTER LLC | RDSSRU00066032MP | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | CBL01282 | 58309 | 4503637409 | 20 | 10077 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-11 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-17 |  | Bin |  |  | OK |  | 2015-11-13 | 12.71 | TW
94792007 | Z040 | TCNU9991800 | TDS |  | 2016-01-08 | 12:00 |  | 0704005998 | 10 | 070400599810 | 20 | 397690-511 | WMNS AIR MAX COMMAND | 876 | 876 | 146 | 2015-12-19 | N | 2016-01-07 | 2015-12-19 | SPORTMASTER LLC | RDSSRU00066282BN | 2016-01-20 | 2016-02-01 |  | VL | RUS15 | 384665 | AS50019721 | 56033 | 4503721814 | 570 | 876 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-19 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  |  | 8.2 | ID
94101999 | Z040 | KKTU7023166 | TDS | 2015-12-01 | 2016-01-08 | 12:00 |  | 0704036849 | 10 | 070403684910 | 10 | 545358-063 | NIKE AW77 FT SHORT | 800 | 800 | 50 | 2015-11-26 | N | 2016-01-01 | 2015-11-26 | SPORTMASTER LLC | RDSSRU00066363ML | 2015-12-20 | 2016-01-01 | 3 Outer carton wet - repacked ; | VL | RUS05 | 223116 | EAL20562 | 0301N1014E | 4503699906 | 10 | 800 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-26 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK |  | 2015-11-30 | 3.12 | MY
95959697 | Z040 | ECMU9441257 | TDS |  | 2016-01-14 | 12:00 |  | 0702467287 | 10 | 070246728710 | 10 | 552141-010 | NIKE LEGEND 2.0 TI DFC CAPRI | 5951 | 5951 | 200 |  | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066622BN | 2015-12-20 | 2016-01-01 |  | VL | RUS05 | 223116 | 3850294 | 54201 | 4503674705 | 20 | 5951 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2015-12-20 |  | Bin |  |  | OK |  |  | 12 | LK
93435152 | Z040 | APHU4583432 | TDS | 2015-11-26 | 2016-01-08 | 12:00 |  | 0704005996 | 10 | 070400599610 | 20 | 599359-001 | NIKE AIR VAPOR ADVANTAGE | 246 | 246 | 41 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066252BN | 2015-12-20 | 2016-01-01 | BARGE DELAYED ETA TCT VIA BARGE 25.11.15; | VL | RUS15 | 384665 | AS40205178 | 56033 | 4503701358 | 580 | 246 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-25 | 2.65 | ID
93437687 | Z040 | APHU4505851 | TDS | 2015-11-26 | 2016-01-08 | 12:00 |  | 0704040514 | 10 | 070404051410 | 20 | 616281-102 | SON OF FORCE MID | 3288 | 3288 | 548 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066261BN | 2015-12-20 | 2016-01-01 | available for Barge on 22.11.15 21u; | VL | RUS15 | 384665 | AI40108277 | 53357 | 4503652662 | 60 | 3288 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-24 | 39.93 | IN
93437700 | Z040 | APHU4505851 | TDS | 2015-11-26 | 2016-01-08 | 12:00 |  | 0704029997 | 10 | 070402999710 | 20 | 616302-011 | WMNS SON OF FORCE | 2016 | 2016 | 336 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066304BN | 2015-12-20 | 2016-01-01 | available for Barge on 22.11.15 21u; | VL | RUS15 | 384665 | AI40108277 | 53357 | 4503652606 | 340 | 2016 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | OK | pair1 | 2015-11-24 | 16.84 | IN
93437717 | Z040 | APHU7040085 | TDS | 2015-11-25 | 2016-01-08 | 12:00 |  | 0704040627 | 10 | 070404062710 | 20 | 616302-011 | WMNS SON OF FORCE | 2820 | 2820 | 235 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066305CL | 2015-12-20 | 2016-01-01 | available for Barge on 22.11.15 21u; | VL | RUS15 | 384665 | AI40181115 | 53357 | 4503652606 | 330 | 2820 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK | pair1 | 2015-11-24 | 22.04 | IN
95959805 | Z040 | ECMU9441257 | TDS |  | 2016-01-14 | 12:00 |  | 0702591663 | 10 | 070259166310 | 10 | 620277-703 | NIKE PRO RIVAL BRA | 1040 | 1040 | 40 |  | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066845BN | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | 3850294 | 54201 | 4503674545 | 10 | 1040 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Bin |  |  | OK |  |  | 3.36 | LK
94785935 | Z040 | TGHU9564919 | TDS |  | 2016-01-08 | 12:00 |  | 0704220822 | 10 | 070422082210 | 10 | 623872-032 | NIKE VICTORY REVERSIBLE BRA | 2653 | 2653 | 23 | 2015-12-18 | N | 2016-01-07 |  | SPORTMASTER LLC | RDSSRU00066629BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | AI40075479 | 53357 | 4503651989 | 10 | 2653 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-18 | 2016-01-01 | 5 | 2016-01-09 | 2015-12-20 |  | Bin |  |  | OK |  |  | 1.38
93517826 | Z040 | TCNU9991837 | TDS | 2015-12-01 | 2016-01-08 | 12:00 |  | 0704040521 | 10 | 070404052110 | 20 | 631457-017 | NIKE ZOOM VAPOR 9.5 TOUR CLAY | 240 | 240 | 40 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066249BN | 2015-12-20 | 2016-01-01 | BARGE DELAYED ETA TCT VIA BARGE 25.11.15; | VL | RUS15 | 384665 | AH40296546 | 57078 | 4503706410 | 160 | 240 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-25 | 2.7 | MO
93100403 | Z040 | KKFU9049550 | TDS | 2015-11-16 | 2016-01-08 | 12:00 |  | 0704040403 | 10 | 070404040310 | 20 | 631458-103 | NIKE ZOOM VAPOR 9.5 TOUR | 246 | 246 | 41 | 2015-11-11 | N | 2016-01-01 | 2015-11-11 | SPORTMASTER LLC | RDSSRU00066247BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | EAP58434 | 57078 | 4503706410 | 140 | 246 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-11 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-13 | 2.79 | MO
93191564 | Z040 | DRYU4520699 | TDS | 2015-11-19 | 2016-01-08 | 12:00 |  | 0704040402 | 10 | 070404040210 | 20 | 631458-106 | NIKE ZOOM VAPOR 9.5 TOUR | 1212 | 1212 | 202 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066248BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | AH50275124 | 57078 | 4503706410 | 20 | 1212 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-18 | 13.73 | MO
93397102 | Z040 | MRKU4671736 | TDS | 2015-11-20 | 2016-01-08 | 12:00 |  | 0704040401 | 10 | 070404040110 | 20 | 631475-146 | WMNS NIKE ZOOM VAPOR 9.5 TOUR | 924 | 924 | 154 | 2015-11-17 | N | 2016-01-01 | 2015-11-18 | SPORTMASTER LLC | RDSSRU00066255BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | CN2441459 | 57078 | 4503706410 | 10 | 924 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-17 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-19 | 7.6 | MO
95290337 | Z040 | HLXU9001571 | TDS |  | 2016-01-14 | 12:00 |  | 0704043564 | 10 | 070404356410 | 10 | 642813-023 | 9" DISTANCE SHORT | 3240 | 3240 | 51 | 2015-12-27 | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066366ML | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1832630 | 55224 | 4503715015 | 10 | 3240 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Caselot |  |  | OK | pair2 |  | 3.83 | MY
95290653 | Z040 | HLXU9001571 | TDS |  | 2016-01-14 | 12:00 |  | 0704044905 | 10 | 070404490510 | 10 | 642813-023 | 9" DISTANCE SHORT | 877 | 877 | 15 | 2015-12-27 | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066365BN | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1832630 | 55224 | 4503715016 | 10 | 877 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Mono |  |  | OK | pair2 |  | 1.05 | MY
95290368 | Z040 | HLXU9001571 | TDS |  | 2016-01-14 | 12:00 |  | 0704044908 | 10 | 070404490810 | 10 | 644252-022 | NIKE DF ESSENTIAL HALF TGHT | 1625 | 1625 | 20 | 2015-12-27 | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066371BN | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1832630 | 55224 | 4503707153 | 10 | 1625 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Mono |  |  | OK | pair3 |  | 1.47 | TW
95290528 | Z040 | HLXU9001571 | TDS |  | 2016-01-14 | 12:00 |  | 0704043563 | 10 | 070404356310 | 10 | 644252-022 | NIKE DF ESSENTIAL HALF TGHT | 3240 | 3240 | 45 | 2015-12-27 | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066372ML | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1832630 | 55224 | 4503707152 | 10 | 3240 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Caselot |  |  | OK | pair3 |  | 3.38 | TW
93517863 | Z040 | FCIU3042334 | TDS | 2015-11-26 | 2016-01-08 | 12:00 |  | 0704040512 | 10 | 070404051210 | 20 | 649087-444 | W NIKE ZOOM VAPOR 9.5 TOUR CLY | 966 | 966 | 161 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066256BN | 2016-01-12 | 2016-01-01 | BARGE DELAYED ETA TCT VIA BARGE 25.11.15; | VL | RUS15 | 384665 | AH50266679 | 57078 | 4503706410 | 150 | 966 | N |  | 2016-01-12 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-25 | 7.95 | MO
95242271 | Z040 | CMAU0038382 | TDS |  | 2016-01-08 | 12:00 |  | 0702591664 | 10 | 070259166410 | 10 | 650831-703 | NIKE PRO CLASSIC BRA | 1000 | 1000 | 11 | 2015-12-20 | N | 2016-01-07 | 2015-12-20 | SPORTMASTER LLC | RDSSRU00066837BN | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | 3850269 | 54201 | 4503699205 | 10 | 1000 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-20 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-17 | WT_Feb | Mono |  |  | OK | pair4 |  | 0.9 | LK
95242273 | Z040 | CMAU0038382 | TDS |  | 2016-01-08 | 12:00 |  | 0702591680 | 10 | 070259168010 | 10 | 650831-703 | NIKE PRO CLASSIC BRA | 3216 | 3216 | 34 | 2015-12-20 | N | 2016-01-07 | 2015-12-20 | SPORTMASTER LLC | RDSSRU00066838ML | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | 3850269 | 54201 | 4503699206 | 10 | 3216 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-20 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-17 | WT_Feb | Caselot |  |  | OK | pair4 |  | 2.74 | LK
95618115 | Z040 | UESU4828590 | TDS |  | 2016-01-14 | 12:00 |  | 0703995931 | 10 | 070399593110 | 20 | 651548-505 | MAGISTA OLA TF | 1428 | 1428 | 119 | 2015-12-27 | N | 2016-01-22 |  | SPORTMASTER LLC | RDSSRU00068334CL | 2016-02-10 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1672502 | 56033 | 4503721819 | 220 | 1428 | N |  | 2016-02-10 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Caselot |  |  | OK | pair5 |  | 13.47 | ID
95618274 | Z040 | UESU4828590 | TDS |  | 2016-01-14 | 12:00 |  | 0703995925 | 10 | 070399592510 | 20 | 651548-505 | MAGISTA OLA TF | 1818 | 1818 | 303 | 2015-12-27 | N | 2016-01-22 |  | SPORTMASTER LLC | RDSSRU00068333BN | 2016-02-10 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1672502 | 56033 | 4503721819 | 250 | 1818 | N |  | 2016-02-10 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Mono |  |  | OK | pair5 |  | 15.97 | ID
95618037 | Z040 | HLBU1591617 | TDS |  | 2016-01-14 | 12:00 |  | 0703995932 | 10 | 070399593210 | 20 | 651648-803 | MERCURIAL VORTEX II IC | 2958 | 2958 | 493 | 2015-12-27 | N | 2016-01-22 |  | SPORTMASTER LLC | RDSSRU00068329BN | 2016-02-10 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1663496 | 56033 | 4503721819 | 210 | 2958 | N |  | 2016-02-10 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Mono |  |  | OK | pair6 |  | 26.1 | ID
95618324 | Z040 | HLXU9012684 | TDS |  | 2016-01-14 | 12:00 |  | 0703995929 | 10 | 070399592910 | 20 | 651648-803 | MERCURIAL VORTEX II IC | 2640 | 2640 | 220 | 2015-12-27 | N | 2016-01-22 |  | SPORTMASTER LLC | RDSSRU00068330CL | 2016-02-10 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1672501 | 56033 | 4503721819 | 230 | 2640 | N |  | 2016-02-10 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Caselot |  |  | OK | pair6 |  | 27.68 | ID
95618071 | Z040 | HLXU9012684 | TDS |  | 2016-01-14 | 12:00 |  | 0703995928 | 10 | 070399592810 | 20 | 651649-803 | MERCURIAL VORTEX II TF | 2820 | 2820 | 235 | 2015-12-27 | N | 2016-01-22 |  | SPORTMASTER LLC | RDSSRU00068328CL | 2016-02-10 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1672501 | 56033 | 4503721819 | 240 | 2820 | N |  | 2016-02-10 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Caselot |  |  | OK | pair7 |  | 29.56 | ID
95618472 | Z040 | UESU4828590 | TDS |  | 2016-01-14 | 12:00 |  | 0703995934 | 10 | 070399593410 | 20 | 651649-803 | MERCURIAL VORTEX II TF | 3732 | 3732 | 622 | 2015-12-27 | N | 2016-01-22 |  | SPORTMASTER LLC | RDSSRU00068327BN | 2016-02-10 | 2016-02-01 |  | VL | RUS05 | 223116 | HLB1672502 | 56033 | 4503721819 | 200 | 3732 | N |  | 2016-02-10 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Mono |  |  | OK | pair7 |  | 33.35 | ID
95711165 | Z040 | HDMU4710070 | TDS |  | 2016-01-14 | 12:00 |  | 0706655882 | 10 | 070665588210 | 10 | 683521-657 | NIKE DRI-FIT CONTOUR LS | 660 | 660 | 55 | 2015-12-28 | N | 2016-01-14 |  | SPORTMASTER LLC | RDSSRU00076058ML | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | E017085 | 55224 | 4503686561 | 30 | 660 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-28 | 2016-01-04 | 1 | 2016-01-15 | 2016-01-24 |  | Caselot |  |  | OK |  |  | 1.21 | TW
95959354 | Z040 | ECMU9441257 | TDS |  | 2016-01-14 | 12:00 |  | 0704035553 | 10 | 070403555310 | 10 | 703092-480 | COOL COMP SL | 2867 | 2867 | 61 |  | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066415BN | 2015-12-20 | 2016-01-01 |  | VL | RUS05 | 223116 | 3850294 | 54201 | 4503699258 | 10 | 2867 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2015-12-20 |  | Mono | 2015-12-10 |  | OK |  |  | 3.66 | LK
93158291 | Z040 | GESU4309081 | TDS | 2015-11-19 | 2016-01-08 | 12:00 |  | 0704040625 | 20 | 070404062520 | 20 | 704889-001 |  | 1980 | 1980 | 330 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066208BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0786114 | 55224 | 4503652682 | 10 | 1980 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-18 | 23.53 | VN
95290670 | Z040 | MRKU8844249 | TDS |  | 2016-01-08 | 12:00 |  | 0702591668 | 10 | 070259166810 | 10 | 719803-703 | POWER EPIC LUX CROP PR | 1103 | 1103 | 24 | 2015-12-23 | N | 2016-01-11 |  | SPORTMASTER LLC | RDSSRU00066808BN | 2016-01-20 | 2016-02-01 | ETA TCT 29.12.2015; | VL | RUS05 | 223116 | CCDG063767 | 1038N1033E | 4503676110 | 10 | 1103 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-23 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  |  | 1.44 | TW
93089893 | Z040 | HMMU9037016 | TDS | 2015-11-13 | 2016-01-08 | 12:00 |  | 0704040522 | 10 | 070404052210 | 20 | 724382-012 | NIKE FREE 5.0 | 1134 | 1134 | 189 | 2015-11-09 | N | 2016-01-01 | 2015-11-09 | SPORTMASTER LLC | RDSSRU00066209BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | E017191 | 55224 | 4503656286 | 450 | 1134 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-09 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-11 | 11.79 | VN
96101038 | Z040 | 43Z1026267 | TDS | 2015-12-17 | 2016-01-08 | 12:00 |  | 0704043567 | 10 | 070404356710 | 20 | 724984-002 | NIKE AIR MAX SEQUENT (GS) | 2140 | 2140 | 214 | 2015-12-14 | N | 2015-12-31 | 2015-12-15 | SPORTMASTER LLC | RDSSRU00066175CL | 2016-01-20 | 2016-02-01 | @ DAMCO 17.12.2015_edeyge; | AF | RUS05 | 223116 |  | 55224 | 4503745538 | 1750 | 2140 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK |  |  | 21.96 | VN
95198136 | Z040 | CMAU0038382 | TDS |  | 2016-01-08 | 12:00 |  | 0704035570 | 10 | 070403557010 | 10 | 725029-010 | WARM COMP LS CREW | 1464 | 1464 | 51 | 2015-12-20 | N | 2016-01-07 | 2015-12-20 | SPORTMASTER LLC | RDSSRU00066438BN | 2015-12-20 | 2016-01-01 |  | VL | RUS05 | 223116 | 3850269 | 54201 | 4503674782 | 10 | 1464 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-20 | 2016-01-01 | 5 | 2016-01-09 | 2015-12-20 |  | Mono |  |  | Open |  |  | 3.14 | LK
94565104 | Z040 | 43Z1025353 | TDS | 2015-11-25 | 2016-01-08 | 12:00 |  | 0704743772 | 10 | 070474377210 | 10 | 725473-021 | NIKE PRO HC TIDAL MULTI CAPRI | 2320 | 2320 | 35 | 2015-11-23 | N | 2016-01-01 | 2015-11-23 | SPORTMASTER LLC | RDSSRU00067568BN | 2015-12-20 | 2016-01-01 | @DAMCO 25.11.15; | AF | RUS05 | 223116 |  | 55224 | 4503608873 | 40 | 2320 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-23 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-17 | WT_Feb | Mono |  |  | Open |  |  | 1.8 | TW
95242268 | Z040 | HFA00044371 | TDS | 2015-12-04 | 2016-01-08 | 12:00 |  | 0702591679 | 10 | 070259167910 | 10 | 725635-010 | NIKE PRO HC LIMITLESS CAPRI | 736 | 736 | 46 | 2015-12-01 | N | 2016-01-01 | 2015-12-01 | SPORTMASTER LLC | RDSSRU00066771ML | 2016-01-20 | 2016-02-01 | @DAMCO 03.12.15 ; | AF | RUS05 | 223116 |  | 50845 | 4503698234 | 10 | 736 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-01 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK |  |  | 1.31 | IL
95959345 | Z040 | ECMU9441257 | TDS |  | 2016-01-14 | 12:00 |  | 0702591670 | 10 | 070259167010 | 10 | 725726-703 | NIKE PRO HYPERCOOL TANK | 1309 | 1309 | 23 |  | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066756BN | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | 3850294 | 54201 | 4503714872 | 10 | 1309 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Bin |  |  | OK |  |  | 1.17 | LK
95290536 | Z040 | MRKU8844249 | TDS |  | 2016-01-08 | 12:00 |  | 0704136245 | 10 | 070413624510 | 10 | 726033-100 | NIKE RALLY PLUS PANT-JOGGER | 852 | 852 | 48 | 2015-12-23 | N | 2016-01-11 |  | SPORTMASTER LLC | RDSSRU00066737BN | 2015-12-20 | 2016-01-01 | ETA TCT 29.12.2015; | VL | RUS15 | 384665 | CCDG063767 | 1038N1033E | 4503637633 | 10 | 852 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-23 | 2016-01-01 | 5 | 2016-01-09 | 2015-12-20 |  | Mono |  | 2015-12-17 | OK |  |  | 3.45 | CN
95112655 | Z040 | APZU3258955 | TDS |  | 2016-01-14 | 12:00 |  | 0704215247 | 10 | 070421524710 | 10 | 728752-671 | PRACTICE TOP WB | 803 | 803 | 13 |  | N | 2016-01-14 |  | SPORTMASTER LLC | RDSSRU00066700BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | AN50218883 | 57035 | 4503637693 | 10 | 803 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-28 | 2016-01-04 | 1 | 2016-01-15 | 2015-12-20 |  | Bin |  |  | OK |  |  | 0.71 | HK
93625700 | Z040 | TCNU9994630 | TDS | 2015-12-07 | 2016-01-08 | 12:00 |  | 0704040510 | 10 | 070404051010 | 20 | 729809-001 | NIKE SB SATIRE II | 3822 | 3822 | 637 | 2015-11-30 | N | 2016-01-01 | 2015-11-30 | SPORTMASTER LLC | RDSSRU00066267BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | AV30007010 | 2050N1064E | 4503656285 | 420 | 3822 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-30 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-12-04 | 36.15 | VN
95959626 | Z040 | ECMU9441257 | TDS |  | 2016-01-14 | 12:00 |  | 0704040370 | 10 | 070404037010 | 10 | 742228-342 | DRI-FIT TRAINING SS | 1413 | 1413 | 48 |  | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066547BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | 3850294 | 54201 | 4503696870 | 100 | 1413 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2015-12-20 |  | Bin |  |  | OK |  |  | 2.88 | LK
95959334 | Z040 | ECMU9441257 | TDS |  | 2016-01-14 | 12:00 |  | 0704044920 | 10 | 070404492010 | 10 | 742228-435 | DRI-FIT TRAINING SS | 1074 | 1074 | 39 |  | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066548BN | 2016-01-20 | 2016-02-01 |  | VL | RUS05 | 223116 | 3850294 | 54201 | 4503699281 | 10 | 1074 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-24 |  | Mono |  |  | Open |  |  | 3.28 | LK
94544635 | Z040 | CMAU1051368 | TDS | 2015-12-14 | 2016-01-08 | 12:00 |  | 0704215263 | 10 | 070421526310 | 10 | 743164-342 | NIKE PRO INDY COLOURBLOCK BRA | 1944 | 1944 | 26 | 2015-12-08 | N | 2016-01-01 | 2015-12-08 | SPORTMASTER LLC | RDSSRU00066661BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | 3850268 | 54201 | 4503637517 | 10 | 1944 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-08 | 2016-01-01 | 5 | 2016-01-09 | 2015-12-20 |  | Mono |  |  | OK | pair8 | 2015-12-11 | 1.56 | LK
95198144 | Z040 | CMAU0038382 | TDS |  | 2016-01-08 | 12:00 |  | 0704220804 | 10 | 070422080410 | 10 | 743164-342 | NIKE PRO INDY COLOURBLOCK BRA | 3168 | 3168 | 40 | 2015-12-20 | N | 2016-01-07 | 2015-12-20 | SPORTMASTER LLC | RDSSRU00066662ML | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | 3850269 | 54201 | 4503637518 | 10 | 3168 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-20 | 2016-01-01 | 5 | 2016-01-09 | 2015-12-20 |  | Caselot |  |  | OK | pair8 |  | 2.4 | LK
93518137 | Z040 | TCNU9991837 | TDS | 2015-12-01 | 2016-01-08 | 12:00 |  | 0704005987 | 10 | 070400598710 | 20 | 749340-014 | NIKE AIR ZOOM PEGASUS 32 | 1224 | 1224 | 204 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066210BN | 2015-12-20 | 2016-01-01 | BARGE DELAYED ETA TCT VIA BARGE 25.11.15; | VL | RUS15 | 384665 | AH40296546 | 57078 | 4503656294 | 160 | 1224 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-25 | 13.7 | CN
95159415 | Z040 | HMMU9060994 | TDS |  | 2016-01-08 | 12:00 |  | 0704040538 | 10 | 070404053810 | 20 | 749477-410 | NIKE SB FOKUS | 3120 | 3120 | 520 | 2015-12-21 | N | 2016-01-07 | 2015-12-21 | SPORTMASTER LLC | RDSSRU00066291BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | E947649 | 55224 | 4503656288 | 20 | 3120 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-21 | 2016-01-01 | 5 | 2016-01-09 | 2015-12-13 |  | Mono |  |  | OK | pair9 |  | 29.04 | VN
95290649 | Z040 | HLXU9001571 | TDS |  | 2016-01-14 | 12:00 |  | 0704040631 | 10 | 070404063110 | 20 | 749477-410 | NIKE SB FOKUS | 3636 | 3636 | 303 | 2015-12-27 | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00066292CL | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB1832630 | 55224 | 4503656288 | 30 | 3636 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2015-12-13 |  | Caselot |  |  | OK | pair9 |  | 35.28 | VN
93435173 | Z040 | APHU4613603 | TDS | 2015-12-02 | 2016-01-08 | 12:00 |  | 0704084809 | 10 | 070408480910 | 20 | 749633-011 | NIKE SB PORTMORE MID | 6078 | 6078 | 1013 | 2015-11-21 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066266BN | 2015-12-20 | 2016-01-01 | BARGE DELAYED ETA TCT VIA BARGE 25.11.15; | VL | RUS15 | 384665 | AS40205172 | 56033 | 4503652648 | 80 | 6078 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-25 | 58.8 | ID
93158339 | Z040 | HLXU9012914 | TDS | 2015-11-19 | 2016-01-08 | 12:00 |  | 0704040605 | 10 | 070404060510 | 20 | 807144-001 | NIKE FS LITE RUN 3 | 3240 | 3240 | 270 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066218CL | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0786087 | 55224 | 4503652674 | 230 | 3240 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK | pair10 | 2015-11-18 | 38.43 | VN
93158363 | Z040 | UESU4830880 | TDS | 2015-11-19 | 2016-01-08 | 12:00 |  | 0704040517 | 10 | 070404051710 | 20 | 807144-001 | NIKE FS LITE RUN 3 | 3882 | 3882 | 647 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066217BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0786123 | 55224 | 4503652674 | 220 | 3882 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | OK | pair10 | 2015-11-18 | 44.87 | VN
93342394 | Z040 | HLXU9003194 | TDS | 2015-12-02 | 2016-01-08 | 12:00 |  | 0704040613 | 10 | 070404061310 | 20 | 807316-403 | NIKE MD RUNNER 2 (GS) | 2990 | 2990 | 299 | 2015-11-17 | N | 2016-01-01 | 2015-11-16 | SPORTMASTER LLC | RDSSRU00066183CL | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB1680660 | 56033 | 4503652647 | 70 | 2990 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-17 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK | pair11 | 2015-11-21 | 26.91 | ID
93342468 | Z040 | HLXU9008339 | TDS | 2015-11-23 | 2016-01-08 | 12:00 |  | 0704040728 | 10 | 070404072810 | 20 | 807316-403 | NIKE MD RUNNER 2 (GS) | 2616 | 2616 | 218 | 2015-11-17 | N | 2016-01-01 | 2015-11-16 | SPORTMASTER LLC | RDSSRU00066182BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB1680656 | 56033 | 4503652647 | 440 | 2616 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-17 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | OK | pair11 | 2015-11-21 | 20.39 | ID
95959341 | Z040 | ECMU9441257 | TDS |  | 2016-01-14 | 12:00 |  | 0704034697 | 10 | 070403469710 | 10 | 811963-696 | NIKE YA HYPRCL PRO AOP1BRA YTH | 700 | 700 | 10 |  | N | 2016-01-13 |  | SPORTMASTER LLC | RDSSRU00065924BN | 2015-12-20 | 2016-01-01 |  | VL | RUS05 | 223116 | 3850294 | 54201 | 4503699300 | 10 | 700 | N |  | 2015-12-20 | 2016-01-19 | 2015-12-27 | 2016-01-03 | 7 | 2016-01-15 | 2016-01-17 |  | Bin |  |  | OK |  |  | 0.6 | LK
92812933 | Z040 | DRYU4541876 | TDS | 2015-11-13 | 2016-01-08 | 12:00 |  | 0704035562 | 10 | 070403556210 | 20 | 816747-001 | NIKE AIR MAX DYNASTY | 810 | 810 | 135 | 2015-11-07 | N | 2016-01-01 | 2015-11-07 | SPORTMASTER LLC | RDSSRU00066293BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | AS50006701 | 56033 | 4503652649 | 500 | 810 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-07 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | OK | pair12 | 2015-11-11 | 8.84 | ID
92812975 | Z040 | DRYU4541876 | TDS | 2015-11-13 | 2016-01-08 | 12:00 |  | 0704036896 | 10 | 070403689610 | 20 | 816747-001 | NIKE AIR MAX DYNASTY | 1044 | 1044 | 87 | 2015-11-07 | N | 2016-01-01 | 2015-11-07 | SPORTMASTER LLC | RDSSRU00066294CL | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | AS50006701 | 56033 | 4503652649 | 490 | 1044 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-07 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK | pair12 | 2015-11-11 | 12.01 | ID
93342380 | Z040 | HLXU9012940 | TDS | 2015-11-25 | 2016-01-08 | 12:00 |  | 0704040505 | 10 | 070404050510 | 20 | 816747-400 | NIKE AIR MAX DYNASTY | 3678 | 3678 | 613 | 2015-11-17 | N | 2016-01-01 | 2015-11-16 | SPORTMASTER LLC | RDSSRU00066215BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB1680658 | 56033 | 4503652649 | 470 | 3678 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-17 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | Open |  | 2015-11-21 | 40.07 | ID
93036044 | Z040 | ECMU2012986 | TDS | 2015-11-24 | 2016-01-08 | 12:00 |  | 0704040607 | 10 | 070404060710 | 20 | 818097-002 | NIKE LUNARTEMPO 2 | 672 | 672 | 56 | 2015-11-17 | N | 2016-01-01 | 2015-11-17 | SPORTMASTER LLC | RDSSRU00066212CL | 2016-01-06 | 2016-01-01 | ETA tct per barge 23.11 (needed at tct 24.11 at the latest - trucking not necessary); | VL | RUS15 | 384665 | F1528227 | 57047 | 4503652664 | 500 | 672 | N |  | 2016-01-06 | 2016-01-19 | 2015-11-17 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK | pair13 | 2015-11-23 | 7.36 | CN
94618852 | Z040 | DRYU4205803 | TDS |  | 2016-01-08 | 12:00 |  | 0704040504 | 10 | 070404050410 | 20 | 818097-002 | NIKE LUNARTEMPO 2 | 576 | 576 | 96 | 2015-12-21 | N | 2016-01-07 | 2015-12-21 | SPORTMASTER LLC | RDSSRU00066211BN | 2016-01-20 | 2016-02-01 |  | VL | RUS15 | 384665 | F083037 | 57047 | 4503701306 | 1910 | 576 | N |  | 2016-01-20 | 2016-02-19 | 2015-12-21 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | OK | pair13 |  | 5.88 | CN
93158302 | Z040 | UESU4828970 | TDS | 2015-11-20 | 2016-01-08 | 12:00 |  | 0704036897 | 10 | 070403689710 | 20 | 818970-001 | NIKE AIR PERNIX | 2472 | 2472 | 206 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066246CL | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0790854 | 55224 | 4503652682 | 30 | 2472 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK | pair14 | 2015-11-18 | 29.41 | VN
93158352 | Z040 | UESU4828970 | TDS | 2015-11-20 | 2016-01-08 | 12:00 |  | 0704040503 | 10 | 070404050310 | 20 | 818970-001 | NIKE AIR PERNIX | 2604 | 2604 | 434 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066245BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0790854 | 55224 | 4503652682 | 40 | 2604 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | OK | pair14 | 2015-11-18 | 27.57 | VN
93489350 | Z040 | HLXU9006402 | TDS | 2015-11-26 | 2016-01-08 | 12:00 |  | 0704040550 | 10 | 070404055010 | 20 | 819300-001 | NIKE REVOLUTION 3 | 3936 | 3936 | 656 | 2015-11-22 | N | 2016-01-01 | 2015-11-21 | SPORTMASTER LLC | RDSSRU00066219BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0786032 | 55224 | 4503652620 | 1190 | 3936 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-22 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | Open |  | 2015-11-25 | 42.14 | VN
93741951 | Z040 | TCNU6049410 | TDS | 2015-11-30 | 2016-01-08 | 12:00 |  | 0704040542 | 10 | 070404054210 | 20 | 819305-106 | NIKE AIR VAPOR ADAVANTAGE OMNI | 1188 | 1188 | 198 | 2015-11-24 | N | 2016-01-01 | 2015-11-24 | SPORTMASTER LLC | RDSSRU00066251BN | 2016-01-12 | 2016-01-01 |  | VL | RUS15 | 384665 | CBH60782 | 56033 | 4503701358 | 590 | 1188 | N |  | 2016-01-12 | 2016-01-19 | 2015-11-24 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Bin |  |  | OK |  | 2015-11-27 | 12.77 | ID
93158307 | Z040 | GATU7012640 | TDS | 2015-11-19 | 2016-01-08 | 12:00 |  | 0704040610 | 10 | 070404061010 | 20 | 819416-001 | NIKE REVOLUTION 3 (GS) | 2140 | 2140 | 214 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066193CL | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0786150 | 55224 | 4503652618 | 940 | 2140 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Caselot |  |  | OK | pair15 | 2015-11-18 | 14.75 | VN
93158423 | Z040 | GESU4309081 | TDS | 2015-11-19 | 2016-01-08 | 12:00 |  | 0704040726 | 10 | 070404072610 | 20 | 819416-001 | NIKE REVOLUTION 3 (GS) | 2676 | 2676 | 223 | 2015-11-14 | N | 2016-01-01 | 2015-11-14 | SPORTMASTER LLC | RDSSRU00066192BN | 2015-12-20 | 2016-01-01 |  | VL | RUS15 | 384665 | HLB0786114 | 55224 | 4503652618 | 950 | 2676 | N |  | 2015-12-20 | 2016-01-19 | 2015-11-14 | 2016-01-01 | 5 | 2016-01-09 | 2016-01-24 |  | Mono |  |  | OK | pair15 | 2015-11-18 | 18.34 | VN