## Preliminary Schedule
Как Избавиться от этих "*" и Букв "А" в датах и чтоб эти ячейки стали как даты в виде 05.01.2017
UNF PROJECT - TARGET SCHEDULE [Preliminary]
Activity ID | Activity Name | Original Duration | Start | Finish
MILESTONE
Project Milestone
MG100 | Effective Date of Contract (EDC) | 0 | 01-Mar-16 A
MG210 | Plot Plan Issue for Permission | 0 |  | 30-Sep-16
MG220 | Hazardous Area Plan Issue | 0 |  | 30-Sep-16
MG230 | Equip. Layout(0) Issue | 0 |  | 02-Sep-16
MG240 | One Line Diagram(0) Issue | 0 |  | 15-Sep-16
MG250 | 3D Model Review 1st Complete | 0 |  | 16-Feb-17
MG260 | 3D Model Review 2nd Complete | 0 |  | 16-Jun-17
MG270 | 3D Model Review 3rd Complete | 0 |  | 15-Oct-17
MG310 | Civil Work Start | 0 | 01-Apr-17
MG320 | Foundation Work Start | 0 | 01-Apr-17
MG330 | U/G Piping Work Start | 0 | 01-Feb-17
MG350 | K.D. Tank Erection Start | 0 | 30-Jan-18
MG360 | Equip. Installation Start | 0 | 01-Jan-18
MG410 | Pipe Rack Erection Start | 0 | 01-Sep-17
MG420 | Piping Prefabrication Start | 0 | 01-Sep-17
MG430 | A/G Piping Work Start | 0 | 15-Feb-18
MG450 | Substation Equip. Installation Start | 0 | 01-Apr-18
MG500 | Power Available for Utility Precommissionig | 0 | 01-Sep-18
MG520 | IA Available | 0 | 22-Sep-18
MG540 | N2 Receiving from Existing Plant | 0 | 24-Mar-19
MG580 | DMW Available | 0 | 30-Oct-18
MG610 | MP/LP Steam Available from Aux. Boiler | 0 | 16-Dec-18
MG700 | NG Receiving | 0 | 03-Nov-18
MG800 | Mechanical Completion | 0 |  | 15-Sep-19
MG805 | UREA FIRST DROP | 0 |  | 01-Jul-19*
MG810 | Performance Test Start | 0 | 01-Dec-19
MG900 | PAC | 0 |  | 31-Dec-19
MG910 | As-built Document | 0 |  | 31-Mar-20
Owner's Milestone
MO001 | Completion of Obstacles Relocation / Demolition | 0 |  | 01-Sep-16
MO010 | Soil Investigation Report (with Laboratory Test) | 0 |  | 01-Sep-16 A
MO020 | Construction Permit for Temporary Facilities | 0 |  | 01-Sep-16
MO030 | Site Handover of Temporary Facilities | 0 |  | 01-Sep-16
MO031 | Completion of Site Preparation Leveling | 0 |  | 01-Sep-16
MO032 | Preliminary Site Handover | 0 |  | 01-Sep-16
MO040 | Construction Permit | 0 |  | 31-Jan-17
MO050 | Site Handover for Temporary Facilities with Access | 0 |  | 01-Sep-16
MO060 | Site Leveling | 60 | 01-Jul-16 A | 01-Sep-16
MO070 | Site Handover with Access | 0 |  | 28-Jan-17
MO099 | Temporary Power for DCS (Required) | 0 |  | 26-Jul-18
MO099A | Temporary Power for DCS Available | 0 |  | 01-Jul-17
MO100 | Power Receiving for Utility Substation (Required) | 0 |  | 31-Aug-18
MO100A | Power Receiving for Utility Substation Available | 0 |  | 01-Feb-18
MO101 | Power Receiving for Ammonia Substation (Required) | 0 |  | 31-Oct-18
MO101A | Power Receiving for Ammonia Substation Available | 0 |  | 01-Feb-18
MO102 | Power Receiving for Urea Substation (Required) | 0 |  | 01-Dec-18
MO102A | Power Receiving for Urea Substation Available | 0 |  | 01-Feb-18
MO110 | MP Steam (Required) | 0 |  | 02-Nov-18
MO110A | MP Steam Available | 0 |  | 01-Mar-18
MO111 | River Water (Required) | 0 |  | 07-Sep-18
MO111A | River Water Available | 0 |  | 01-Aug-17
MO112 | Chemicals (Required) | 0 |  | 10-Oct-18
MO112A | Chemicals Available | 0 |  | 01-Oct-17
MO120 | N2 (Required) | 0 |  | 22-Sep-18
MO120A | N2 Available | 0 |  | 31-Mar-18
MO130 | Hot Water (Required) | 0 |  | 31-Aug-18
MO130A | Hot Water Available | 0 |  | 01-Oct-17
MO140 | NG (Required) | 0 |  | 12-Oct-18
MO140A | NG Available | 0 |  | 01-Apr-18
MO150 | Permit for Pre-commissioning (Required) | 0 |  | 31-Jan-19
MO150A | Permit for Pre-commissioning Available | 0 |  | 01-Jan-18
MO160 | Permit for Plant Operation (Required) | 0 |  | 12-May-19
MO160A | Permit for Plant Operation Available | 0 |  | 01-Aug-18
Project Management Milestone
MP010 | Project Strategy Meeting | 0 | 06-Mar-16 A
MP020 | BM/BQ Increase/Decrease Study Meeting (#1) | 0 | 01-Mar-16 A
MP030 | Master/Front End Schedule Coordination Meeting | 0 | 08-Mar-16 A
MP040 | Engineering Policy Meeting | 0 | 01-Mar-16 A
MP050 | Constructability Study Meeting (#1) | 0 | 31-Mar-16 A
MP060 | Procurement Policy Meeting | 0 | 16-Apr-16 A
MP070 | Precommi./Commissioning Plan Study Meeting | 0 | 01-May-16 A
MP080 | Plot Plan Study Meeting | 0 | 11-Mar-16 A
MP090 | Cable Route Plan Study Meeting | 0 | 11-Mar-16 A
MP100 | Road/Equip. Area Pavement & Ditch Plan Study | 0 | 11-Mar-16 A
MP110 | Subcontracting Plan Study Meeting | 0 | 26-Mar-16 A
MP120 | P&ID Study Meeting (#1) | 0 | 11-Jun-16 A
MP130 | Equip. Layout Dwg Study Meeting | 0 | 31-May-16 A
MP140 | Engineering Document Freeze Study Meeting | 0 | 14-May-16 A
MP150 | Constructability Study Meeting (#2) | 0 | 03-Sep-16
MP160 | P&ID Study Meeting (#2) | 0 | 01-Dec-16
MP170 | Piping Route Plan Study Meeting | 0 | 03-Sep-16
MP190 | BM/BQ Increase/Decrease Study Meeting (#2) | 0 | 16-Oct-16
MP200 | Engineering Document Inventory (#1) | 0 | 03-Jan-17
MP210 | P&ID Study Meeting (#3) | 0 | 16-Jan-17
MP220 | Engineering Document Inventory (#2) | 0 | 04-Mar-17
MP230 | P&ID Study Meeting (#4:Final) | 0 | 23-May-17
MP240 | Constructability Study Meeting (#3) | 0 | 03-Mar-17
MP250 | Engineering Document Inventory (#3) | 0 | 02-Jul-17
MP280 | BM/BQ Increase/Decrease Study Meeting (#3) | 0 | 16-Sep-17
3D Design Milestone
M3200 | Plot Plan Review | 0 | 01-Apr-16 A
M3300 | Outline Dwg for Equip. Layout Issue for All Unit | 0 |  | 27-Jul-16 A
M3400 | Equip. Layout Review | 0 | 28-Jul-16 A
M3500 | Outline Dwg for 3D 1st Model Review | 0 |  | 15-Dec-16
Payment Milestone
M4010 | First submission of Overall Project Schedule | 0 | 29-Mar-16 A
M4020 | First submission of Basic Engineering Design Data | 0 | 29-Apr-16 A
M4030 | First submission of Process Flow Diagram | 0 | 29-May-16 A
M4040 | First submission of Utility Flow Diagram | 0 | 29-Jun-16 A
M4050 | First submission of Plot Plant | 0 | 29-Jul-16 A
M4060 | First submission of Substation Equipment Layout | 0 | 29-Aug-16 A
M4070 | First submission of Design Basis of Foundation Design | 0 | 29-Sep-16
M4080 | First submission of Site Preparation Drawing | 0 | 29-Oct-16
M4090 | First submission of Equipment Layout | 0 | 29-Nov-16
M4100 | First submission of Specification and Data Sheet for DCS/ESD | 0 | 29-Dec-16
M4110 | First submission of Foundation Drawing | 0 | 29-Jan-17
M4120 | First submission of Standard Drawing for Steeel Structure | 0 | 01-Mar-17
M4130 | First submission of Design Basis of Fire Protection System | 0 | 29-Mar-17
M4140 | First submission of Paving and Road General Layout | 0 | 29-Apr-17
M4150 | First submission of Specification and Data Sheets for Control Valves | 0 | 29-May-17
M4160 | First submission of Pressure Releaf Device Data Sheet | 0 | 29-Jun-17
M4170 | First submission of Cable Schedule | 0 | 29-Jul-17
M4180 | First submission of Steel Structure Detail Drawing | 0 | 29-Aug-17
ENGINEERING
Project Management
Project
EJ100020 | Project Execution Procedure | 31 | 01-Mar-16 A | 31-Mar-16 A
EJ100030 | Project Coordination Procedure | 31 | 01-Mar-16 A | 31-Mar-16 A
Schedule
EJ200021 | Master Schedule | 31 | 01-Mar-16 A | 31-Mar-16 A
EJ200022 | Front-End Schedule | 31 | 01-Mar-16 A | 31-Mar-16 A
EJ200023 | Detail Schedule | 121 | 01-Mar-16 A | 31-Oct-16
QA / QC
EJ300021 | Quality Assurance / Control Plan | 31 | 01-Mar-16 A | 08-Apr-16 A
EJ300022 | Inspection Plan | 59 | 01-Apr-16 A | 29-May-16 A
Process
Licensor Process Design Package
EB301005 | Ammonia Licensor (HTAS) - Resume Design Work | 0 | 08-Mar-16 A
EB301010 | Licensor (HTAS) Design Package Receive 1st | 0 |  | 22-Mar-16 A
EB301020 | Licensor (HTAS) Design Package Receive 2nd A Package | 0 |  | 01-Apr-16 A
EB301025 | Licensor (HTAS) Design Package Receive 2nd B Package | 0 |  | 06-Apr-16 A
EB301030 | Licensor (HTAS) Design Package Receive 3rd | 0 |  | 08-Apr-16 A
EB301040 | Licensor (HTAS) Design Package Receive 4th | 0 |  | 26-Apr-16 A
EB301050 | Licensor (HTAS) Design Package Receive 5th | 0 |  | 24-May-16 A
EB301060 | Licensor (HTAS) Design Package Receive 6th | 0 |  | 07-Jun-16 A
EB301070 | Licensor (HTAS) Design Package Receive 7th | 0 |  | 05-Jul-16 A
EB302005 | Urea Licensor (SP) - Resume Design Work | 0 | 09-Mar-16 A
EB302010 | Licensor (SP) Design Package Receive 1st | 0 |  | 16-Mar-16 A
EB302020 | Licensor (SP) Design Package Receive 2nd | 0 |  | 23-Mar-16 A
EB302030 | Licensor (SP) Design Package Receive 3rd | 0 |  | 06-Apr-16 A
EB302040 | Licensor (SP) Design Package Receive 4th | 0 |  | 20-Apr-16 A
EB302050 | Licensor (SP) Design Package Receive 5th | 0 |  | 04-May-16 A
EB302060 | Licensor (SP) Design Package Receive 6th | 0 |  | 18-May-16 A
EB302070 | Licensor (SP) Design Package Receive 7th | 0 |  | 25-May-16 A
EB302080 | Licensor (SP) Design Package Receive 8th | 0 |  | 13-Jul-16 A
EB302090 | Licensor (SP) Design Package Receive 9th | 0 |  | 27-Jul-16 A
EB302100 | Licensor (SP) Design Package Receive 10th | 0 |  | 03-Oct-16
EB303005 | Urea Licensor (UFT) - Resume Design Work | 0 | 14-Mar-16 A
EB303010 | Licensor (UFT) Design Package Receive 1st | 0 |  | 04-Apr-16 A
EB303020 | Licensor (UFT) Design Package Receive 2nd | 0 |  | 02-May-16 A
EB303030 | Licensor (UFT) Design Package Receive 3rd | 0 |  | 30-May-16 A
EB303040 | Licensor (UFT) Design Package Receive 4th | 0 |  | 24-Dec-16
Licensor Equipment List
EB311010 | Licensor (HTAS) Equip. List | 0 |  | 15-Mar-16 A
EB312020 | Licensor (SP) Equip. List | 0 |  | 23-Mar-16 A
EB313030 | Licensor (UFT) Equip. List | 0 |  | 04-Apr-16 A
Licensor PFD
EB321010 | Licensor (HTAS) PFD | 0 |  | 22-Mar-16 A
EB322020 | Licensor (SP) PFD | 0 |  | 09-Mar-16 A
EB323030 | Licensor (UFT) PFD | 0 |  | 04-Apr-16 A
Licensor P&ID
EB331010 | Licensor (HTAS) P&ID(0) | 0 |  | 08-Mar-16 A
EB332020 | Licensor (SP) P&ID(0) | 0 |  | 13-Jul-16 A
EB333030 | Licensor (UFT) P&ID | 0 |  | 02-May-16 A
Licensor Plot Plan
EB342010 | Licensor (SP) Plot Plan | 0 |  | 27-Jul-16 A
Licensor Medium List
EB351011 | Licensor (HTAS) Medium List(0) | 0 |  | 08-Mar-16 A
Licensor Data Sheet
EB361010 | Licensor (HTAS) D/S - Ammonia Converter | 0 |  | 30-Mar-16 A
EB361020 | Licensor (HTAS) D/S - Secondary Reformer | 0 |  | 30-Mar-16 A
EB361032 | Licensor (HTAS) D/S - Reactor in Front End | 0 |  | 06-Apr-16 A
EB361040 | Licensor (HTAS) D/S - Columns in CO2 Removal | 0 |  | 06-Apr-16 A
EB361050 | Licensor (HTAS) D/S - Remaining Column | 0 |  | 08-Mar-16 A
EB361060 | Licensor (HTAS) D/S - Separator (HP Vaned Type Vessel) | 0 |  | 06-Apr-16 A
EB361070 | Licensor (HTAS) D/S - General Vessel | 0 |  | 26-Apr-16 A
EB361080 | Licensor (HTAS) D/S - WHB & Steam Superheater | 0 |  | 25-Mar-16 A
EB361090 | Licensor (HTAS) D/S - H/E in Front End | 0 |  | 26-Apr-16 A
EB361100 | Licensor (HTAS) D/S - Synloop H/E | 0 |  | 08-Mar-16 A
EB361111 | Licensor (HTAS) D/S - H/E in Methanol Synthesis | 0 |  | 26-Apr-16 A
EB361112 | Licensor (HTAS) D/S - Other S&T H/E | 0 |  | 26-Apr-16 A
EB361120 | Licensor (HTAS) D/S - Tank | 0 |  | 26-Apr-16 A
EB361130 | Licensor (HTAS) D/S - Filter | 0 |  | 26-Apr-16 A
EB361270 | Licensor (HTAS) D/S - Primary Reformer | 0 |  | 22-Mar-16 A
EB361272 | Licensor (HTAS) D/S - Convection Section Coils | 0 |  | 06-Apr-16 A
EB361275 | Licensor (HTAS) D/S - SCR Reactor | 0 |  | 22-Mar-16 A
EB361280 | Licensor (HTAS) D/S - Start-up Heater | 0 |  | 26-Apr-16 A
EB361290 | Licensor (HTAS) D/S - Pumps (Main) in CO2 Removal | 0 |  | 06-Apr-16 A
EB361300 | Licensor (HTAS) D/S - Compressors | 0 |  | 01-Apr-16 A
EB361310 | Licensor (HTAS) D/S - Flue Gas & Combustion Air Blower | 0 |  | 08-Apr-16 A
EB361320 | Licensor (HTAS) D/S - Fan | 0 |  | 26-Apr-16 A
EB361360 | Licensor (HTAS) D/S - Hydrogen Recovry Unit (HRU) | 0 |  | 08-Mar-16 A
EB361430 | Licensor (HTAS) D/S - Remaining Equip. | 0 |  | 26-Apr-16 A
EB362140 | Licensor (SP) D/S - Urea Reactor | 0 |  | 06-Apr-16 A
EB362150 | Licensor (SP) D/S - Urea Hydrolyzer | 0 |  | 25-May-16 A
EB362160 | Licensor (SP) D/S - Distillation Tower (Stripping Tower) | 0 |  | 04-May-16 A
EB362170 | Licensor (SP) D/S - HP Carbamate Separator | 0 |  | 06-Apr-16 A
EB362180 | Licensor (SP) D/S - Stripper | 0 |  | 06-Apr-16 A
EB362190 | Licensor (SP) D/S - Carbamate Condenser | 0 |  | 06-Apr-16 A
EB362201 | Licensor (SP) D/S - MP & LP Decomposer | 0 |  | 04-May-16 A
EB362202 | Licensor (SP) D/S - Urea High Grade H/E | 0 |  | 25-May-16 A
EB362203 | Licensor (SP) D/S - MP Absorber | 0 |  | 25-May-16 A
EB362204 | Licensor (SP) D/S - Preconcentrator | 0 |  | 04-May-16 A
EB362210 | Licensor (SP) D/S - Ammonia Preheater | 0 |  | 06-Apr-16 A
EB362220 | Licensor (SP) D/S - Carbamate Ejector | 0 |  | 06-Apr-16 A
EB362230 | Licensor (SP) D/S - Vacuum Unit | 0 |  | 06-Apr-16 A
EB362320 | Licensor (SP) D/S - HP Ammonia Pumps | 0 |  | 29-Mar-16 A
EB362330 | Licensor (SP) D/S - HP Carbamate Solution Pumps | 0 |  | 29-Mar-16 A
EB362340 | Licensor (SP) D/S - Remaining Items | 0 |  | 25-May-16 A
EB363240 | Licensor (UFT) D/S - Tanks | 0 |  | 02-May-16 A
EB363250 | Licensor (UFT) D/S - First & Final Fluid Bed Cooler | 0 |  | 02-May-16 A
EB363260 | Licensor (UFT) D/S - Diverter | 0 |  | 02-May-16 A
EB363340 | Licensor (UFT) D/S - Scrubber Ciculation Pumps | 0 |  | 02-May-16 A
EB363351 | Licensor (UFT) D/S - Air & Dedusting Fans | 0 |  | 02-May-16 A
EB363352 | Licensor (UFT) D/S - Atomization Air Blower | 0 |  | 02-May-16 A
EB363370 | Licensor (UFT) D/S - Bucket Elevator | 0 |  | 02-May-16 A
EB363380 | Licensor (UFT) D/S - Granulator | 0 |  | 02-May-16 A
EB363390 | Licensor (UFT) D/S - Crusher | 0 |  | 02-May-16 A
EB363401 | Licensor (UFT) D/S - Granulator Scrubber | 0 |  | 02-May-16 A
EB363402 | Licensor (UFT) D/S - Acid Scrubber | 0 |  | 02-May-16 A
EB363411 | Licensor (UFT) D/S - Granulator Extractor | 0 |  | 02-May-16 A
EB363412 | Licensor (UFT) D/S - Safety Screen | 0 |  | 02-May-16 A
EB363413 | Licensor (UFT) D/S - Vibrating Screen | 0 |  | 02-May-16 A
Licensor Instrument Data Sheet
EB371010 | Licensor (HTAS) Instrument D/S - CV | 0 |  | 07-Jun-16 A
EB371020 | Licensor (HTAS) Instrument D/S - Remaining | 0 |  | 07-Jun-16 A
EB371030 | Licensor (HTAS) Interlock System | 0 |  | 08-Mar-16 A
EB372031 | Licensor (SP) Instrument List | 0 |  | 27-Jul-16 A
EB372032 | Licensor (SP) Instrument D/S & Control Valve D/S | 0 |  | 27-Jul-16 A
EB372040 | Licensor (SP) Interlock Logic Diagram | 0 |  | 27-Jul-16 A
EB373031 | Licensor (UFT) Interlock Logic System | 0 |  | 30-May-16 A
EB373032 | Licensor (UFT) Instrument List & Data Sheets | 0 |  | 30-May-16 A
EB373040 | Licensor (UFT) Instrument Control Valve D/S | 0 |  | 30-May-16 A
Licensor Safety Valve Data Sheet
EB381010 | Licensor (HTAS) Instrument D/S - PSV | 0 |  | 07-Jun-16 A
EB382010 | Licensor (SP) Safety Valve and Rupture Disc Specification | 0 |  | 10-Aug-16 A
Licensor Dwg
EB391011 | Licensor (HTAS) Dwg - Ammonia Converter Pressure Shell (Sketch) | 0 |  | 08-Mar-16 A
EB391012 | Licensor (HTAS) Dwg - Ammonia Converter Basket Dwg | 0 |  | 29-Mar-16 A
EB391020 | Licensor (HTAS) Dwg - Secondary Reformer | 0 |  | 08-Mar-16 A
EB391030 | Licensor (HTAS) Dwg - Reactor | 0 |  | 10-May-16 A
EB391040 | Licensor (HTAS) Dwg - Columns in CO2 Removal | 0 |  | 22-Apr-16 A
EB391050 | Licensor (HTAS) Dwg - General Towers | 0 |  | 10-May-16 A
EB391060 | Licensor (HTAS) Dwg - Synloop H/E | 0 |  | 15-Apr-16 A
EB391070 | Licensor (HTAS) Dwg - Primary Reformer | 0 |  | 29-Mar-16 A
EB391080 | Licensor (HTAS) Dwg - Primary Reformer | 0 |  | 08-Mar-16 A
Licensor Catalyst & Chemical List
EB3A1010 | Licensor (HTAS) MSDS for Catalyst | 0 |  | 24-May-16 A
Licensor Operating & Analytical Manual
EB3D1010 | Licensor (HTAS) Operating & Analytical Manual | 0 |  | 05-Jul-16 A
EB3D2020 | Licensor (SP) Operating & Analytical Manual | 0 |  | 03-Oct-16
EB3D3030 | Licensor (UFT) Operating & Analytical Manual | 0 |  | 24-Dec-16
Other Licensor Drawing
EB3X1010 | Licensor (HTAS) Design Basis | 0 |  | 15-Mar-16 A
EB3X1020 | Licensor (HTAS) Production and Consumption Figures | 0 |  | 22-Mar-16 A
EB3X1030 | Licensor (HTAS) Process Stream Data | 0 |  | 22-Mar-16 A
EB3X1040 | Licensor (HTAS) MSD | 0 |  | 30-Mar-16 A
EB3X1050 | Licensor (HTAS) Process Description | 0 |  | 30-Mar-16 A
EB3X1060 | Licensor (HTAS) Start-up and Trip Scenarios Steam Balance | 0 |  | 08-Mar-16 A
EB3X1070 | Licensor (HTAS) Utility Diagram | 0 |  | 08-Mar-16 A
EB3X2010 | Licensor (SP) Heat and Material Balance | 0 |  | 16-Mar-16 A
EB3X2020 | Licensor (SP) Utility Balance | 0 |  | 09-Mar-16 A
EB3X2030 | Licensor (SP) Process Description | 0 |  | 23-Mar-16 A
EB3X2040 | Licensor (SP) Material Selection Philosophy | 0 |  | 20-Apr-16 A
EB3X2050 | Licensor (SP) General Specification for Equipment, Piping & Instrument | 0 |  | 20-Apr-16 A
EB3X2060 | Licensor (SP) Production and Consumption Figures | 0 |  | 18-May-16 A
EB3X2070 | Licensor (SP) Venting, Blowdown and Flare System | 0 |  | 18-May-16 A
EB3X3010 | Licensor (UFT) Design Basis | 0 |  | 04-Apr-16 A
EB3X3020 | Licensor (UFT) Process Description | 0 |  | 04-Apr-16 A
Process Design Basis
Design Basis
EB410010 | BEDD | 0 |  | 01-Mar-16 A
Conceptual Operation Plan
EB420010 | Conceputual Operation Plan | 31 | 22-Jun-16 A | 01-Sep-16
Hazardous Area Plan
EB440010 | Hazardous Area Plan | 30 | 02-Jul-16 A | 30-Sep-16
Process Basic Design
Equipment List
EB511010 | Equip. List(0) - Ammmonia | 13 | 30-Mar-16 A | 20-Apr-16 A
EB512020 | Equip. List(0) - Urea | 28 | 13-Apr-16 A | 28-Apr-16 A
EB51A030 | Equip. List(0) - Utility | 15 | 16-May-16 A | 14-Jun-16 A
EB51B040 | Equip. List(0) - Offsite | 15 | 16-May-16 A | 14-Jun-16 A
Process Flow Diagram
EB521010 | PFD(0) - Ammmonia | 20 | 23-Mar-16 A | 27-Apr-16 A
EB522020 | PFD(0) - Urea | 36 | 05-Apr-16 A | 28-Apr-16 A
Utility Flow Diagram
UFD for U/G Piping
EB53A010 | UFD(P) | 0 |  | 01-Mar-16 A
UFD (IFA)
EB53A020 | UFD(0) - Utility | 61 | 18-Apr-16 A | 21-Jun-16 A
EB53B020 | UFD(0) - Offsite | 61 | 11-May-16 A | 21-Jun-16 A
Utility Summary List
EB55A010 | Utility Summary List(0) | 13 | 05-Apr-16 A | 17-Apr-16 A
Design Flow Plan
Design Flow Plan(0)
EB561010 | Design Flow Plan(0) - Ammmonia | 31 | 12-Apr-16 A | 06-Jun-16 A
EB562010 | Design Flow Plan(0) - Urea | 31 | 11-May-16 A | 31-May-16 A
Design Flow Plan(1)
EB561020 | Design Flow Plan(1) - Ammmonia | 30 | 16-Oct-16 | 14-Nov-16
EB562020 | Design Flow Plan(1) - Urea | 30 | 16-Oct-16 | 14-Nov-16
Flare Design Flow Plan
EB570010 | Flare Design Flow Plan | 30 | 01-Nov-16 | 30-Nov-16
Sewerage Plan
EB580010 | Sewerage Plan | 31 | 27-Sep-16 | 27-Oct-16
Process Description
EB591010 | Process Description - Ammonia | 110 | 02-Apr-16 A | 20-Jul-16 A
EB592010 | Process Description - Urea | 105 | 24-Mar-16 A | 06-Jul-16 A
EB59A010 | Process Description - Utility | 162 | 22-Jun-16 A | 30-Nov-16
EB59B010 | Process Description - Offsite | 162 | 22-Jun-16 A | 30-Nov-16