## Старая
Activity ID | Activity Name
EDC 2016/3/1
MILESTONE
Project Milestone
MG100 | Effective Date of Contract (EDC)
MG210 | Plot Plan Issue for Permission
MG220 | Hazardous Area Plan Issue
MG230 | Equip. Layout(0) Issue
MG240 | One Line Diagram(0) Issue
MG250 | 3D Model Review 1st Complete
MG260 | 3D Model Review 2nd Complete
MG270 | 3D Model Review 3rd Complete
MG310 | Civil Work Start
MG320 | Foundation Work Start
MG330 | U/G Piping Work Start
MG350 | K.D. Tank Erection Start
MG360 | Equip. Installation Start
MG410 | Pipe Rack Erection Start
MG420 | Piping Prefabrication Start
MG430 | A/G Piping Work Start
MG450 | Substation Equip. Installation Start
MG500 | Power Available for Utility Precommissionig
MG520 | IA Available
MG540 | N2 Receiving from Existing Plant
MG580 | DMW Available
MG610 | MP/LP Steam Available from Aux. Boiler
MG700 | NG Receiving
MG800 | Mechanical Completion - Ammonia
MG802 | Mechanical Completion - Urea
MG804 | Mechanical Completion - Utility
MG806 | Mechanical Completion - Offsite
MG810 | Performance Test Start
MG900 | PAC
MG910 | As-built Document
Owner's Milestone
MO001 | Completion of Obstacles Relocation / Demolition
MO010 | Soil Investigation Report (with Laboratory Test)
MO020 | Construction Permit for Temporary Facilities
MO030 | Site Handover of Temporary Facilities
MO031 | Completion of Site Preparation Leveling
MO032 | Preliminary Site Handover
MO040 | Construction Permit
MO050 | Site Handover for Temporary Facilities with Access
MO060 | Site Leveling
MO070 | Site Handover with Access
MO099 | Temporary Power for DCS Available
MO100 | Power Receiving for Utility Substation
MO101 | Power Receiving for Ammonia Substation
MO102 | Power Receiving for Urea Substation
MO110 | MP Steam Available
MO111 | River Water Available
MO112 | Chemicals Available
MO120 | N2 Available
MO130 | Hot Water Available
MO140 | NG Available
MO150 | Permit for Pre-commissioning
MO160 | Permit for Plant Operation
Project Management Milestone
MP010 | Project Strategy Meeting
MP020 | BM/BQ Increase/Decrease Study Meeting (#1)
MP030 | Master/Front End Schedule Coordination Meeting
MP040 | Engineering Policy Meeting
MP050 | Constructability Study Meeting (#1)
MP060 | Procurement Policy Meeting
MP070 | Precommi./Commissioning Plan Study Meeting
MP080 | Plot Plan Study Meeting
MP090 | Cable Route Plan Study Meeting
MP100 | Road/Equip. Area Pavement & Ditch Plan Study
MP110 | Subcontracting Plan Study Meeting
MP120 | P&ID Study Meeting (#1)
MP130 | Equip. Layout Dwg Study Meeting
MP140 | Engineering Document Freeze Study Meeting
MP150 | Constructability Study Meeting (#2)
MP160 | P&ID Study Meeting (#2)
MP170 | Piping Route Plan Study Meeting
MP190 | BM/BQ Increase/Decrease Study Meeting (#2)
MP200 | Engineering Document Inventory (#1)
MP210 | P&ID Study Meeting (#3)
MP220 | Engineering Document Inventory (#2)
MP230 | P&ID Study Meeting (#4:Final)
MP240 | Constructability Study Meeting (#3)
MP250 | Engineering Document Inventory (#3)
MP280 | BM/BQ Increase/Decrease Study Meeting (#3)
3D Design Milestone
M3200 | Plot Plan Review
M3300 | Outline Dwg for Equip. Layout Issue for All Unit
M3400 | Equip. Layout Review
M3500 | Outline Dwg for 3D 1st Model Review
Payment Milestone
M4010 | First submission of Overall Project Schedule
M4020 | First submission of Basic Engineering Design Data
M4030 | First submission of Process Flow Diagram
M4040 | First submission of Utility Flow Diagram
M4050 | First submission of Plot Plant
M4060 | First submission of Substation Equipment Layout
M4070 | First submission of Design Basis of Foundation Design
M4080 | First submission of Site Preparation Drawing
M4090 | First submission of Equipment Layout
M4100 | First submission of Specification and Data Sheet for DCS/ESD
M4110 | First submission of Foundation Drawing
M4120 | First submission of Standard Drawing for Steeel Structure
M4130 | First submission of Design Basis of Fire Protection System
M4140 | First submission of Paving and Road General Layout
M4150 | First submission of Specification and Data Sheets for Control Valves
M4160 | First submission of Pressure Releaf Device Data Sheet
M4170 | First submission of Cable Schedule
M4180 | First submission of Steel Structure Detail Drawing
ENGINEERING
Project Management
Project
EJ100020 | Project Execution Procedure
EJ100030 | Project Coordination Procedure
Schedule
EJ200021 | Master Schedule
EJ200022 | Front-End Schedule
EJ200023 | Detail Schedule
QA / QC
EJ300021 | Quality Assurance / Control Plan
EJ300022 | Inspection Plan
Process
Licensor Process Design Package
EB301005 | Ammonia Licensor (HTAS) - Resume Design Work
EB301010 | Licensor (HTAS) Design Package Receive 1st
EB301020 | Licensor (HTAS) Design Package Receive 2nd A Package
EB301025 | Licensor (HTAS) Design Package Receive 2nd B Package
EB301030 | Licensor (HTAS) Design Package Receive 3rd
EB301040 | Licensor (HTAS) Design Package Receive 4th
EB301050 | Licensor (HTAS) Design Package Receive 5th
EB301060 | Licensor (HTAS) Design Package Receive 6th
EB301070 | Licensor (HTAS) Design Package Receive 7th
EB302005 | Urea Licensor (SP) - Resume Design Work
EB302010 | Licensor (SP) Design Package Receive 1st
EB302020 | Licensor (SP) Design Package Receive 2nd
EB302030 | Licensor (SP) Design Package Receive 3rd
EB302040 | Licensor (SP) Design Package Receive 4th
EB302050 | Licensor (SP) Design Package Receive 5th
EB302060 | Licensor (SP) Design Package Receive 6th
EB302070 | Licensor (SP) Design Package Receive 7th
EB302080 | Licensor (SP) Design Package Receive 8th
EB302090 | Licensor (SP) Design Package Receive 9th
EB302100 | Licensor (SP) Design Package Receive 10th
EB303005 | Urea Licensor (UFT) - Resume Design Work
EB303010 | Licensor (UFT) Design Package Receive 1st
EB303020 | Licensor (UFT) Design Package Receive 2nd
EB303030 | Licensor (UFT) Design Package Receive 3rd
EB303040 | Licensor (UFT) Design Package Receive 4th
Licensor Equipment List
EB311010 | Licensor (HTAS) Equip. List
EB312020 | Licensor (SP) Equip. List
EB313030 | Licensor (UFT) Equip. List
Licensor PFD
EB321010 | Licensor (HTAS) PFD
EB322020 | Licensor (SP) PFD
EB323030 | Licensor (UFT) PFD
Licensor P&ID
EB331010 | Licensor (HTAS) P&ID(0)
EB332020 | Licensor (SP) P&ID(0)
EB333030 | Licensor (UFT) P&ID
Licensor Plot Plan
EB342010 | Licensor (SP) Plot Plan
Licensor Medium List
EB351011 | Licensor (HTAS) Medium List(0)
Licensor Data Sheet
EB361010 | Licensor (HTAS) D/S - Ammonia Converter
EB361020 | Licensor (HTAS) D/S - Secondary Reformer
EB361032 | Licensor (HTAS) D/S - Reactor in Front End
EB361040 | Licensor (HTAS) D/S - Columns in CO2 Removal
EB361050 | Licensor (HTAS) D/S - Remaining Column
EB361060 | Licensor (HTAS) D/S - Separator (HP Vaned Type Vessel)
EB361070 | Licensor (HTAS) D/S - General Vessel
EB361080 | Licensor (HTAS) D/S - WHB & Steam Superheater
EB361090 | Licensor (HTAS) D/S - H/E in Front End
EB361100 | Licensor (HTAS) D/S - Synloop H/E
EB361111 | Licensor (HTAS) D/S - H/E in Methanol Synthesis
EB361112 | Licensor (HTAS) D/S - Other S&T H/E
EB361120 | Licensor (HTAS) D/S - Tank
EB361130 | Licensor (HTAS) D/S - Filter
EB361270 | Licensor (HTAS) D/S - Primary Reformer
EB361272 | Licensor (HTAS) D/S - Convection Section Coils
EB361275 | Licensor (HTAS) D/S - SCR Reactor
EB361280 | Licensor (HTAS) D/S - Start-up Heater
EB361290 | Licensor (HTAS) D/S - Pumps (Main) in CO2 Removal
EB361300 | Licensor (HTAS) D/S - Compressors
EB361310 | Licensor (HTAS) D/S - Flue Gas & Combustion Air Blower
EB361320 | Licensor (HTAS) D/S - Fan
EB361360 | Licensor (HTAS) D/S - Hydrogen Recovry Unit (HRU)
EB361430 | Licensor (HTAS) D/S - Remaining Equip.
EB362140 | Licensor (SP) D/S - Urea Reactor
EB362150 | Licensor (SP) D/S - Urea Hydrolyzer
EB362160 | Licensor (SP) D/S - Distillation Tower (Stripping Tower)
EB362170 | Licensor (SP) D/S - HP Carbamate Separator
EB362180 | Licensor (SP) D/S - Stripper
EB362190 | Licensor (SP) D/S - Carbamate Condenser
EB362201 | Licensor (SP) D/S - MP & LP Decomposer
EB362202 | Licensor (SP) D/S - Urea High Grade H/E
EB362203 | Licensor (SP) D/S - MP Absorber
EB362204 | Licensor (SP) D/S - Preconcentrator
EB362210 | Licensor (SP) D/S - Ammonia Preheater
EB362220 | Licensor (SP) D/S - Carbamate Ejector
EB362230 | Licensor (SP) D/S - Vacuum Unit
EB362320 | Licensor (SP) D/S - HP Ammonia Pumps
EB362330 | Licensor (SP) D/S - HP Carbamate Solution Pumps
EB362340 | Licensor (SP) D/S - Remaining Items
EB363240 | Licensor (UFT) D/S - Tanks
EB363250 | Licensor (UFT) D/S - First & Final Fluid Bed Cooler
EB363260 | Licensor (UFT) D/S - Diverter
EB363340 | Licensor (UFT) D/S - Scrubber Ciculation Pumps
EB363351 | Licensor (UFT) D/S - Air & Dedusting Fans
EB363352 | Licensor (UFT) D/S - Atomization Air Blower
EB363370 | Licensor (UFT) D/S - Bucket Elevator
EB363380 | Licensor (UFT) D/S - Granulator
EB363390 | Licensor (UFT) D/S - Crusher
EB363401 | Licensor (UFT) D/S - Granulator Scrubber
EB363402 | Licensor (UFT) D/S - Acid Scrubber
EB363411 | Licensor (UFT) D/S - Granulator Extractor
EB363412 | Licensor (UFT) D/S - Safety Screen
EB363413 | Licensor (UFT) D/S - Vibrating Screen
Licensor Instrument Data Sheet
EB371010 | Licensor (HTAS) Instrument D/S - CV
EB371020 | Licensor (HTAS) Instrument D/S - Remaining
EB371030 | Licensor (HTAS) Interlock System
EB372031 | Licensor (SP) Instrument List
EB372032 | Licensor (SP) Instrument D/S & Control Valve D/S
EB372040 | Licensor (SP) Interlock Logic Diagram
EB373031 | Licensor (UFT) Interlock Logic System
EB373032 | Licensor (UFT) Instrument List & Data Sheets
EB373040 | Licensor (UFT) Instrument Control Valve D/S
Licensor Safety Valve Data Sheet
EB381010 | Licensor (HTAS) Instrument D/S - PSV
EB382010 | Licensor (SP) Safety Valve and Rupture Disc Specification
Licensor Dwg
EB391011 | Licensor (HTAS) Dwg - Ammonia Converter Pressure Shell (Sketch)
EB391012 | Licensor (HTAS) Dwg - Ammonia Converter Basket Dwg
EB391020 | Licensor (HTAS) Dwg - Secondary Reformer
EB391030 | Licensor (HTAS) Dwg - Reactor
EB391040 | Licensor (HTAS) Dwg - Columns in CO2 Removal
EB391050 | Licensor (HTAS) Dwg - General Towers
EB391060 | Licensor (HTAS) Dwg - Synloop H/E
EB391070 | Licensor (HTAS) Dwg - Primary Reformer
EB391080 | Licensor (HTAS) Dwg - Primary Reformer
Licensor Catalyst & Chemical List
EB3A1010 | Licensor (HTAS) MSDS for Catalyst
Licensor Operating & Analytical Manual
EB3D1010 | Licensor (HTAS) Operating & Analytical Manual
EB3D2020 | Licensor (SP) Operating & Analytical Manual
EB3D3030 | Licensor (UFT) Operating & Analytical Manual
Other Licensor Drawing
EB3X1010 | Licensor (HTAS) Design Basis
EB3X1020 | Licensor (HTAS) Production and Consumption Figures
EB3X1030 | Licensor (HTAS) Process Stream Data
EB3X1040 | Licensor (HTAS) MSD
EB3X1050 | Licensor (HTAS) Process Description
EB3X1060 | Licensor (HTAS) Start-up and Trip Scenarios Steam Balance
EB3X1070 | Licensor (HTAS) Utility Diagram
EB3X2010 | Licensor (SP) Heat and Material Balance
EB3X2020 | Licensor (SP) Utility Balance
EB3X2030 | Licensor (SP) Process Description
EB3X2040 | Licensor (SP) Material Selection Philosophy
EB3X2050 | Licensor (SP) General Specification for Equipment, Piping & Instrument
EB3X2060 | Licensor (SP) Production and Consumption Figures
EB3X2070 | Licensor (SP) Venting, Blowdown and Flare System
EB3X3010 | Licensor (UFT) Design Basis
EB3X3020 | Licensor (UFT) Process Description
Process Design Basis
Design Basis
EB410010 | Design Basis
Conceptual Operation Plan
EB420010 | Conceputual Operation Plan
Hazardous Area Plan
EB440010 | Hazardous Area Plan
Process Basic Design
Equipment List
EB511010 | Equip. List(0) - Ammmonia
EB512020 | Equip. List(0) - Urea
EB51A030 | Equip. List(0) - Utility
EB51B040 | Equip. List(0) - Offsite
Process Flow Diagram
EB521010 | PFD(0) - Ammmonia
EB522020 | PFD(0) - Urea
Utility Flow Diagram
UFD for U/G Piping
EB53A010 | UFD(P)
UFD (IFA)
EB53A020 | UFD(0) - Utility
EB53B020 | UFD(0) - Offsite
Utility Summary List
EB55A010 | Utility Summary List(0)
Design Flow Plan
Design Flow Plan(0)
EB561010 | Design Flow Plan(0) - Ammmonia
EB562010 | Design Flow Plan(0) - Urea
Design Flow Plan(1)
EB561020 | Design Flow Plan(1) - Ammmonia
EB562020 | Design Flow Plan(1) - Urea
Flare Design Flow Plan
EB570010 | Flare Design Flow Plan
Sewerage Plan
EB580010 | Sewerage Plan
Process Data Sheet
Process Data Sheet - Process
Process Data Sheet - Process (IFA)
EB711010 | D/S (Process) - Ammonia Converter(0)
EB711020 | D/S (Process) - Secondary Reformer(0)
EB711030 | D/S (Process) - Reactor(0)
EB711040 | D/S (Process) - Column in CO2 Removal(0)
EB711050 | D/S (Process) - General Tower(0)
EB711060 | D/S (Process) - HP Vessel(0)
EB711070 | D/S (Process) - General Vessel(0) - Ammmonia
EB711080 | D/S (Process) - Waste Heat Boiler(0)
EB711090 | D/S (Process) - HP & Cr-Mo S&T H/E(0) - Ammonia
EB711100 | D/S (Process) - Synloop H/E(0)
EB711110 | D/S (Process) - General S&T H/E(0) - Ammmonia
EB711120 | D/S (Process) - K.D. Tank - Ammonia (0)
EB711130 | D/S (Process) - Shop Tank - Ammonia (0)
EB711140 | D/S (Process) - Cartridge Filter(0) - Ammmonia
EB711145 | D/S (Process) - Air Filter (0)
EB711150 | D/S (Process) - Plate H/E(0) - Ammmonia
EB711155 | D/S (Process) - Surface Condenser(0) - Ammmonia
EB711160 | D/S (Process) - Silencer(0) - Ammmonia
EB711392 | D/S (Process) - Primary Reformer(0)
EB711400 | D/S (Process) - Start-up Heater(0)
EB711422 | D/S (Process) - Semilean Solution Pump & Turbine (0)
EB711432 | D/S (Process) - Lean Solution Pump(0)
EB711440 | D/S (Process) - Centrifugal Pump (Middle & Light Duty)(0) - Ammmonia
EB711452 | D/S (Process) - Reciprocating Pump(0)
EB711462 | D/S (Process) - Diaphragm Pump(0)
EB711467 | D/S (Process) - Off-spec Condensate Pump
EB711472 | D/S (Process) - PA Compressor(0)
EB711482 | D/S (Process) - NG Compressor(0)
EB711492 | D/S (Process) - SG Compressor(0)
EB711502 | D/S (Process) - Ammonia Compressor(0)
EB711510 | D/S (Process) - N2 Booster Compressor(0)
EB711522 | D/S (Process) - Flue Gas & Combustion Air Blower(0)
EB711532 | D/S (Process) - Start-up N2 Blower(0)
EB711622 | D/S (Process) - Hydrogen Recovery Unit(0)
EB711632 | D/S (Process) - Chemical Injection Unit(0)
EB711640 | D/S (Process) - Sump Tank Mixer(0)
EB711650 | D/S (Process) - SCR Unit(0)
EB712170 | D/S (Process) - Urea Reactor(0)
EB712180 | D/S (Process) - Urea Hydrolyzer(0)
EB712190 | D/S (Process) - Distillation Tower(0)
EB712200 | D/S (Process) - Carbamate Separator(0)
EB712210 | D/S (Process) - General Vessel(0) - Urea
EB712220 | D/S (Process) - Urea Stripper(0)
EB712230 | D/S (Process) - Carbamate Condenser(0)
EB712240 | D/S (Process) - Urea High Grade Equipment (0)
EB712250 | D/S (Process) - General S&T H/E(0) - Urea
EB712260 | D/S (Process) - K.D. Tank - Urea (0)
EB712270 | D/S (Process) - Shop Tank - Urea (0)
EB712280 | D/S (Process) - Cartridge Filter(0) - Urea
EB712285 | D/S (Process) - Surface Condenser(0) - Urea
EB712290 | D/S (Process) - Plate H/E(0) - Urea
EB712295 | D/S (Process) - HP & Cr-Mo S&T H/E(0) - Urea
EB712300 | D/S (Process) - Silencer(0) - Urea
EB712310 | D/S (Process) - Carbamate Ejector(0)
EB712320 | D/S (Process) - Steam Ejector(0)
EB712330 | D/S (Process) - Carbamate Mixer(0)
EB712340 | D/S (Process) - Vacuum Unit(0)
EB712410 | D/S (Process) - Urea Flare(0)
EB712552 | D/S (Process) - HP Ammonia Pump(0)
EB712562 | D/S (Process) - HP Carbamate Solution Pump(0)
EB712580 | D/S (Process) - Centrifugal Pump (Middle & Light Duty)(0) - Urea
EB712592 | D/S (Process) - CO2 Compressor(0)
EB712602 | D/S (Process) - Stripper Passivation Air Compressor(0)
EB713350 | D/S (Process) - K.D. Tank - Granulation (0)
EB713360 | D/S (Process) - Heater/Chiler(0)
EB713370 | D/S (Process) - Granulator (Upper/Fluid Bed Cooler)(0)
EB713380 | D/S (Process) - Diverter(0)
EB713612 | D/S (Process) - Granulation Fan/Blower(0)
EB713660 | D/S (Process) - Bucket Elevator(0)
EB713670 | D/S (Process) - Granulator (Lower)(0)
EB713680 | D/S (Process) - Crusher(0)
EB713690 | D/S (Process) - Granulator Scrubber(0)
EB713700 | D/S (Process) - Extractor&Screen(0)
EB71B650 | D/S (Process) - Conveyer(0)
Process Data Sheet - Utility & Offsite
Process Data Sheet - U&O (IFA)
EB72A020 | D/S (U&O) - General Vessel(0)
EB72A030 | D/S (U&O) - General S&T H/E(0)
EB72A040 | D/S (U&O) - K.D. Tank(0) - Utility
EB72A050 | D/S (U&O) - Shop Tank(0)
EB72A060 | D/S (U&O) - Cartridge Filter(0)
EB72A070 | D/S (U&O) - Plate H/E(0)
EB72A080 | D/S (U&O) - Silencer(0)
EB72A102 | D/S (U&O) - Auxiliary Boiler(0)
EB72A120 | D/S (U&O) - Flare(0)
EB72A132 | D/S (U&O) - HP BFW Pump(0)
EB72A152 | D/S (U&O) - Cooling Water Pump(0)
EB72A170 | D/S (U&O) - Centrifugal Pump (Fire Water Pump)(0)
EB72A180 | D/S (U&O) - Centrifugal Pump (Middle & Light Duty)(0) - Utility
EB72A190 | D/S (U&O) - Instrument Air Compressor(0)
EB72A200 | D/S (U&O) - Steam Turbine(0)
EB72A220 | D/S (U&O) - Diesel Engine Generator(0)
EB72A240 | D/S (U&O) - Demineralized Water Treatment Unit(0)
EB72A265 | D/S (U&O) - CT Side Filter
EB72A270 | D/S (U&O) - Waste Water Treatment Unit(0)
EB72A290 | D/S (U&O) - Cooling Tower(0)
EB72A300 | D/S (U&O) - Chemical Injection Unit(0)
EB72B090 | D/S (U&O) - Ammonia Storage Tank (0)
EB72B230 | D/S (U&O) - Centrifugal Pump (Middle & Light Duty)(0) - Offsite
EB72B320 | D/S (U&O) - Refrigerator(0)
EB72B340 | D/S (U&O) - Reclaimer(0)
EB72B360 | D/S (U&O) - Railcar Loading System (0)
Study & Calculation
Start-up & Shutdown Study
EB851010 | Startup & Shutdown Study - Ammmonia
EB852020 | Startup & Shutdown Study - Urea
Pump Head Calculation
EB871010 | Pump Head Calculation for Data Sheet - Ammmonia
EB872020 | Pump Head Calculation for Data Sheet - Urea
EB87A030 | Pump Head Calculation for Data Sheet - Utility
EB87B040 | Pump Head Calculation for Data Sheet - Offsite
Safety Valve Calculation
EB8A1010 | Safety Valve Calculation - Ammmonia
EB8A2020 | Safety Valve Calculation - Urea
EB8AA030 | Safety Valve Calculation - Utility
EB8AB040 | Safety Valve Calculation - Offsite
Catalyst & Chemical List
Catalyst List
EBB10010 | Catalyst List
Chemical List
EBB20010 | Chemical List
Laboratory Design
Laboratory Design
EBC10010 | Laboratory Design
Commissioning
Operation Manual
EBD11010 | Operation Manual - Ammmonia
EBD12020 | Operation Manual - Urea
Pre-commissioning Procedure
EBD20010 | Mechanical Running Procedure
Performance Test Procedure
EBD31010 | Performance Test Procedure - Ammmonia
EBD32020 | Performance Test Procedure - Urea
Purchase Spec. / Subcontract Spec.
Purchase Spec.
EBM10010 | Purchase Spec. - Catalyst
EBM10020 | Purchase Spec. - Chemical
EBM10030 | Purchase Spec. - Laboratory Equipment
Equipment
Equipment Basic Design
Equipment Eng'g Standard
EV310010 | Engineering Standard for Stationary Equip.
Equipment Reference Drawing
EV330010 | Equipment Reference Dwg (GA Dwg & L/D)
Engineering Dwg & Loading Data
Engineering Dwg
Engineering Dwg for Piping Layout
EV510011 | Engineering Dwg(0) - Platform & Ladder
EV511021 | Engineering Dwg(0) - Ammonia Converter
EV511031 | Engineering Dwg(0) - Secondary Reformer
EV511041 | Engineering Dwg(0) - Reactor
EV511051 | Engineering Dwg(0) - CO2 Stripper & Absorber
EV511061 | Engineering Dwg(0) - General Tower - Ammmonia
EV511071 | Engineering Dwg(0) - HP Vessel
EV511081 | Engineering Dwg(0) - General Vessel - Ammmonia
EV511091 | Engineering Dwg(0) - HP & Cr-Mo H/E - Ammonia
EV511101 | Engineering Dwg(0) - Syn Loop H/E (1)
EV511106 | Engineering Dwg(0) - Syn Loop H/E (2)
EV511111 | Engineering Dwg(0) - General S&T H/E - Ammmonia
EV511121 | Engineering Dwg(0) - K.D. Tank - Ammmonia
EV511131 | Engineering Dwg(0) - Shop Tank - Ammmonia
EV512141 | Engineering Dwg(0) - Urea Hydrolyzer
EV512151 | Engineering Dwg(0) - Distillation Tower
EV512161 | Engineering Dwg(0) - General Vessel - Urea
EV512171 | Engineering Dwg(0) - Urea Grade Equipment
EV512181 | Engineering Dwg(0) - General S&T H/E - Urea
EV512191 | Engineering Dwg(0) - K.D. Tank - Urea
EV512201 | Engineering Dwg(0) - Shop Tank - Urea
EV512211 | Engineering Dwg(0) - HP & Cr-Mo H/E - Urea
EV513211 | Engineering Dwg(0) - K.D. Tank - Granulation
EV51A231 | Engineering Dwg(0) - Deaerator
EV51A241 | Engineering Dwg(0) - General Vessel - Utility & Offsite
EV51A251 | Engineering Dwg(0) - General S&T H/E - Utility
EV51A261 | Engineering Dwg(0) - K.D. Tank - Utility
EV51A271 | Engineering Dwg(0) - Shop Tank - Utility
EV51B281 | Engineering Dwg(0) - Ammonia Storage Tank
Engineering Dwg with Nozzle Orientation
EV510012 | Engineering Dwg(F) - Platform & Ladder Fabrication Detail
EV511022 | Engineering Dwg(F) with Nozzle Orientation - Ammonia Converter
EV511032 | Engineering Dwg(F) with Nozzle Orientation - Secondary Reformer
EV511042 | Engineering Dwg(F) with Nozzle Orientation - Reactor
EV511052 | Engineering Dwg(F) with Nozzle Orientation - CO2 Stripper & Absorber
EV511062 | Engineering Dwg(F) with Nozzle Orientation - General Tower - Ammmonia
EV511072 | Engineering Dwg(F) with Nozzle Orientation - HP Vessel
EV511082 | Engineering Dwg(F) with Nozzle Orientation - General Vessel - Ammmonia
EV511092 | Engineering Dwg(F) with Nozzle Orientation - HP & Cr-Mo H/E - Ammonia
EV511102 | Engineering Dwg(F) with Nozzle Orientation - Syn Loop H/E (1)
EV511107 | Engineering Dwg(F) with Nozzle Orientation - Syn Loop H/E (2)
EV511112 | Engineering Dwg(F) with Nozzle Orientation - General S&T H/E - Ammmonia
EV511122 | Engineering Dwg(F) with Nozzle Orientation - K.D. Tank - Ammmonia
EV511132 | Engineering Dwg(F) with Nozzle Orientation - Shop Tank - Ammmonia
EV512142 | Engineering Dwg(F) with Nozzle Orientation - Urea Hydrolyzer
EV512152 | Engineering Dwg(F) with Nozzle Orientation - Distillation Tower
EV512162 | Engineering Dwg(F) with Nozzle Orientation - General Vessel - Urea
EV512172 | Engineering Dwg(F) with Nozzle Orientation - Urea Grade Equipment
EV512182 | Engineering Dwg(F) with Nozzle Orientation - General S&T H/E - Urea
EV512192 | Engineering Dwg(F) with Nozzle Orientation - K.D. Tank - Urea
EV512202 | Engineering Dwg(F) with Nozzle Orientation - Shop Tank - Urea
EV512212 | Engineering Dwg(F) with Nozzle Orientation - HP & Cr-Mo H/E - Urea
EV513212 | Engineering Dwg(F) with Nozzle Orientation - K.D. Tank - Granulation
EV51A232 | Engineering Dwg(F) with Nozzle Orientation - Deaerator
EV51A242 | Engineering Dwg(F) with Nozzle Orientation - General Vessel - Utility
EV51A252 | Engineering Dwg(F) with Nozzle Orientation - General S&T H/E - Utility
EV51A262 | Engineering Dwg(F) with Nozzle Orientation - K.D. Tank - Utility
EV51A272 | Engineering Dwg(F) with Nozzle Orientation - Shop Tank - Utility
EV51B282 | Engineering Dwg(F) with Nozzle Orientation - Ammonia Storage Tank
Loading Data
EV521010 | L/D(0) - Ammonia Converter
EV521020 | L/D(0) - Ammonia Converter Basket
EV521030 | L/D(0) - Secondary Reformer
EV521040 | L/D(0) - Reactor
EV521050 | L/D(0) - CO2 Stripper & Absorber
EV521060 | L/D(0) - General Tower - Ammmonia
EV521070 | L/D(0) - HP Vessel
EV521080 | L/D(0) - General Vessel - Ammmonia
EV521090 | L/D(0) - HP & Cr-Mo H/E - Ammonia
EV521100 | L/D(0) - Syn Loop H/E (1)
EV521105 | L/D(0) - Syn Loop H/E (2)
EV521110 | L/D(0) - General S&T H/E - Ammmonia
EV521120 | L/D(0) - K.D. Tank - Ammmonia
EV521130 | L/D(0) - Shop Tank - Ammmonia
EV522140 | L/D(0) - Urea Hydrolyzer
EV522150 | L/D(0) - Distillation Tower
EV522160 | L/D(0) - General Vessel - Urea
EV522170 | L/D(0) - Urea Grade Equipment
EV522180 | L/D(0) - General S&T H/E - Urea
EV522190 | L/D(0) - K.D. Tank - Urea
EV522200 | L/D(0) - Shop Tank - Urea
EV523210 | L/D(0) - K.D. Tank - Granulation
EV523220 | L/D(0) - HP & Cr-Mo H/E - Urea
EV52A230 | L/D(0) - Deaerator
EV52A240 | L/D(0) - General Vessel - Utility
EV52A250 | L/D(0) - General S&T H/E - Utility
EV52A260 | L/D(0) - K.D. Tank - Utility
EV52A270 | L/D(0) - Shop Tank - Utility
EV52B280 | L/D(0) - Ammonia Storage Tank
Equipment Vendor Drawing Review
General Arrangement Drawing
EV611010 | GA Dwg(0) Review - Waste Heat Boiler
EV611020 | GA Dwg(0) Review - Cartridge Filter - Ammmonia
EV611025 | GA Dwg(0) Review - Air Filter
EV611030 | GA Dwg(0) Review - Plate H/E - Ammmonia
EV611040 | GA Dwg(0) Review - Silencer - Ammmonia
EV611045 | GA Dwg(0) Review - Surface Condenser - Ammmonia
EV612050 | GA Dwg(0) Review - Urea Reactor
EV612060 | GA Dwg(0) Review - Carbamate Sepatator
EV612070 | GA Dwg(0) Review - Urea Stripper
EV612080 | GA Dwg(0) Review - Carbamate Condenser
EV612090 | GA Dwg(0) Review - Cartridge Filter - Urea
EV612100 | GA Dwg(0) Review - Plate H/E - Urea
EV612110 | GA Dwg(0) Review - Silencer - Urea
EV612115 | GA Dwg(0) Review - Surface Condenser - Urea
EV612120 | GA Dwg(0) Review - Carbamate Ejector
EV612130 | GA Dwg(0) Review - Steam Ejector
EV612140 | GA Dwg(0) Review - Carbamate Mixer
EV612150 | GA Dwg(0) Review - Vacuum Unit
EV613160 | GA Dwg(0) Review - Heater/Chiller
EV613170 | GA Dwg(0) Review - Granulator (Upper/Fluid Bed Cooler)
EV613180 | GA Dwg(0) Review - Diverter
EV61A190 | GA Dwg(0) Review - Cartridge Filter - Utility
EV61A210 | GA Dwg(0) Review - Silencer - Utility
Loading Data
EV620010 | L/D(0) Review - Tower Internal
EV620020 | L/D(0) Review - Vane Separator
EV620025 | L/D(0) Review - Ceramic Ball
EV621030 | L/D(0) Review - Waste Heat Boiler
EV621040 | L/D(0) Review - Cartridge Filter - Ammmonia
EV621045 | L/D(0) Review - Air Filter
EV621050 | L/D(0) Review - Plate H/E - Ammmonia
EV621060 | L/D(0) Review - Silencer - Ammmonia
EV621070 | L/D(0) Review - Surface Condenser - Ammmonia
EV622070 | L/D(0) Review - Urea Reactor
EV622080 | L/D(0) Review - Carbamate Sepatator
EV622090 | L/D(0) Review - Urea Stripper
EV622100 | L/D(0) Review - Carbamate Condenser
EV622110 | L/D(0) Review - Cartridge Filter - Urea
EV622120 | L/D(0) Review - Plate H/E - Urea
EV622130 | L/D(0) Review - Silencer - Urea
EV622135 | L/D(0) Review - Surface Condenser - Urea
EV622140 | L/D(0) Review - Carbamate Ejector
EV622150 | L/D(0) Review - Steam Ejector
EV622160 | L/D(0) Review - Carbamate Mixer
EV622170 | L/D(0) Review - Vacuum Unit
EV623180 | L/D(0) Review - Heater/Chiller
EV623190 | L/D(0) Review - Granulator (Upper/Fluid Bed Cooler)
EV623200 | L/D(0) Review - Diverter
EV62A210 | L/D(0) Review - Cartridge Filter - Utility
EV62A230 | L/D(0) Review - Silencer - Utility
Other Dwg
EV6X0010 | Vendor Detail Dwg Review - Tower Internal
EV6X0020 | Vendor Detail Dwg Review - Vane Separator
EV6X0025 | Vendor Detail Dwg Review - Ceramic Ball
EV6X1030 | Vendor Detail Dwg Review - Ammonia Converter
EV6X1040 | Vendor Detail Dwg Review - Secondary Reformer
EV6X1050 | Vendor Detail Dwg Review - Reactor
EV6X1060 | Vendor Detail Dwg Review - CO2 Stripper & Absorber
EV6X1070 | Vendor Detail Dwg Review - General Tower - Ammmonia
EV6X1080 | Vendor Detail Dwg Review - HP Vessel
EV6X1085 | Vendor Detail Dwg Review - Deaerator
EV6X1090 | Vendor Detail Dwg Review - General Vessel (CS) - Ammmonia
EV6X1091 | Vendor Detail Dwg Review - General Vessel (SS) - Ammmonia
EV6X1100 | Vendor Detail Dwg Review - Waste Heat Boiler
EV6X1110 | Vendor Detail Dwg Review - HP & Cr-Mo H/E - Ammonia
EV6X1120 | Vendor Detail Dwg Review - Syn Loop H/E (1)
EV6X1125 | Vendor Detail Dwg Review - Syn Loop H/E (2)
EV6X1130 | Vendor Detail Dwg Review - General S&T H/E (CS) - Ammmonia
EV6X1131 | Vendor Detail Dwg Review - General S&T H/E (SS) - Ammmonia
EV6X1140 | Detail Engineering - K.D. Tank - Ammmonia
EV6X1150 | Vendor Detail Dwg Review - Shop Tank - Ammmonia
EV6X1160 | Vendor Detail Dwg Review - Cartridge Filter - Ammmonia
EV6X1165 | Vendor Detail Dwg Review - Air Filter
EV6X1170 | Vendor Detail Dwg Review - Plate H/E - Ammmonia
EV6X1180 | Vendor Detail Dwg Review - Silencer - Ammmonia
EV6X1190 | Vendor Detail Dwg Review - Surface Condenser - Ammmonia
EV6X13400 | Vendor Detail Dwg Review - Vacuum Unit
EV6X2190 | Vendor Detail Dwg Review - Urea Reactor
EV6X2200 | Vendor Detail Dwg Review - Urea Hydrolyzer
EV6X2210 | Vendor Detail Dwg Review - Distillation Tower
EV6X2220 | Vendor Detail Dwg Review - Carbamate Sepatator
EV6X2230 | Vendor Detail Dwg Review - General Vessel (CS) - Urea
EV6X2231 | Vendor Detail Dwg Review - General Vessel (SS) - Urea
EV6X2240 | Vendor Detail Dwg Review - Urea Stripper
EV6X2250 | Vendor Detail Dwg Review - Carbamate Condenser
EV6X2260 | Vendor Detail Dwg Review - Urea Grade Equipment
EV6X2270 | Vendor Detail Dwg Review - General S&T H/E (CS) - Urea
EV6X2271 | Vendor Detail Dwg Review - General S&T H/E (SS) - Urea
EV6X2280 | Detail Engineering - K.D. Tank - Urea
EV6X2290 | Vendor Detail Dwg Review - Shop Tank - Urea
EV6X2300 | Vendor Detail Dwg Review - Cartridge Filter - Urea
EV6X2310 | Vendor Detail Dwg Review - Plate H/E - Urea
EV6X2320 | Vendor Detail Dwg Review - Silencer - Urea
EV6X2325 | Vendor Detail Dwg Review - Surface Condenser - Urea
EV6X2330 | Vendor Detail Dwg Review - Carbamate Ejector
EV6X2340 | Vendor Detail Dwg Review - Steam Ejector
EV6X2350 | Vendor Detail Dwg Review - Carbamate Mixer
EV6X2365 | Vendor Detail Dwg Review - HP & Cr-Mo H/E - Urea
EV6X3370 | Detail Engineering - K.D. Tank - Granulation
EV6X3380 | Vendor Detail Dwg Review - Heater/Chiller
EV6X3390 | Vendor Detail Dwg Review - Granulator (Upper/Fluid Bed Cooler)
EV6X3400 | Vendor Detail Dwg Review - Diverter
EV6XA430 | Vendor Detail Dwg Review - General Vessel (CS) - Utility
EV6XA431 | Vendor Detail Dwg Review - General Vessel (SS) - Utility
EV6XA440 | Vendor Detail Dwg Review - General S&T H/E (CS) - Utility
EV6XA450 | Detail Engineering - K.D. Tank - Utility
EV6XA460 | Vendor Detail Dwg Review - Shop Tank - Utility
EV6XA470 | Vendor Detail Dwg Review - Cartridge Filter - Utility
EV6XA490 | Vendor Detail Dwg Review - Silencer - Utility
EV6XB500 | Detail Engineering - Ammonia Storage Tank
Coordination for Other Groups
Coordination for Piping
EV951011 | Outline Dwg for 3D 1st Model Review - Static Equip. - Ammonia
EV951012 | Outline Dwg for 3D 2nd Model Review - Static Equip. - Ammonia
EV952021 | Outline Dwg for 3D 1st Model Review - Static Equip. - Urea
EV952022 | Outline Dwg for 3D 2nd Model Review - Static Equip. - Urea
EV95A030 | Outline Dwg for 3D 1st Model Review - Static Equip. - Utiity
EV95B041 | Outline Dwg for 3D 1st Model Review - Static Equip. - Offsite
EV95B042 | Outline Dwg for 3D 1st Model Review - Static Equip. - Offsite
Coordination for Civil & Architecture
EV981011 | Preliminary L/D for for ES-101
EV981012 | L/D(0) for ES-101
EV981021 | Preliminary L/D for ES-102
EV981022 | L/D(0) for ES-102
EV981031 | Preliminary L/D for ES-103
EV981032 | L/D(0) for ES-103
EV981091 | L/D for Structural Calc. for Equip. Foundation - Static Equip. - Ammonia
EV981092 | L/D for Equip. Foundation Dwg - Static Equip. - Ammonia
EV982051 | Preliminary L/D for ES-201
EV982052 | L/D(0) for ES-201
EV982061 | Preliminary L/D for ES-202
EV982062 | L/D(0) for ES-202
EV982071 | Preliminary L/D for ES-203A
EV982072 | L/D(0) for ES-203A
EV982081 | Preliminary L/D for ES-203B
EV982082 | L/D(0) for ES-203B
EV982101 | L/D for Structural Calc. for Equip. Foundation - Static Equip. - Urea
EV982102 | L/D for Equip. Foundation Dwg - Static Equip. - Urea
EV982122 | L/D(0) for ES-204
EV982132 | L/D(0) for ES-205
EV982141 | Preliminary L/D for Compressor Shelter
EV982142 | L/D(0) for Compressor Shelter
EV982161 | Preliminary L/D for GRH
EV982162 | L/D(0) for GRH
EV982192 | L/D(0) for LR-104
EV98A111 | L/D for Structural Calc. for Equip. Foundation - Static Equip. - Utiity
EV98A112 | L/D for Equip. Foundation Dwg - Static Equip. - Utiity
EV98B121 | L/D for Structural Calc. for Equip. Foundation - Static Equip. - Offsite
EV98B122 | L/D for Equip. Foundation Dwg - Static Equip. - Offsite
3D Model Review
Equipment 3D Model Check with Vendor Dwg
EVL50010 | Equip. 3D Model Check with Vendor Dwg(F)
Purchase Spec. / Subcontract Spec.
Purchase Spec.
EVM10010 | Purchase Spec. - Tower Internal
EVM10020 | Purchase Spec. - Vane Seprator
EVM10025 | Purchase Spec. - Ceramic Ball
EVM10030 | Purchase Spec. - Platform & Ladder
EVM11040 | Purchase Spec. - Ammonia Converter
EVM11050 | Purchase Spec. - Ammonia Converter Basket
EVM11060 | Purchase Spec. - Secondary Reformer
EVM11070 | Purchase Spec. - Reactor (Ammonia)
EVM11080 | Purchase Spec. - CO2 Stripper & Absorber
EVM11090 | Purchase Spec. - General Tower - Ammmonia
EVM11100 | Purchase Spec. - HP Vessel
EVM11110 | Purchase Spec. - General Vessel - Carbon Steel
EVM11115 | Purchase Spec. - General Vessel - Stainless Steel
EVM11120 | Purchase Spec. - Waste Heat Boiler
EVM11130 | Purchase Spec. - HP & Cr-Mo H/E
EVM11140 | Purchase Spec. - Syn Loop H/E (1)
EVM11145 | Purchase Spec. - Syn Loop H/E (2)
EVM11150 | Purchase Spec. - General S&T H/E - Carbon Steel
EVM11155 | Purchase Spec. - General S&T H/E - Stainless Steel
EVM11160 | Purchase Spec. - K.D. Tank
EVM11170 | Purchase Spec. - Shop Tank
EVM11180 | Purchase Spec. - Cartridge Filter
EVM11190 | Purchase Spec. - Plate H/E
EVM11200 | Purchase Spec. - Silencer
EVM11205 | Purchase Spec. - Surface Condenser
EVM12210 | Purchase Spec. - Urea Reactor & Carbamate Separator
EVM12260 | Purchase Spec. - Urea Stripper
EVM12270 | Purchase Spec. - Carbamate Condenser
EVM12280 | Purchase Spec. - Urea Grade Equipment
EVM12350 | Purchase Spec. - Carbamate Ejector
EVM12360 | Purchase Spec. - Steam Ejector
EVM12370 | Purchase Spec. - Carbamate Mixer
EVM12380 | Purchase Spec. - Vacuum Unit
EVM13400 | Purchase Spec. - Heater/Chiller
EVM13410 | Purchase Spec. - Granulator (Upper/Fluid Bed Cooler)
EVM13420 | Purchase Spec. - Diverter
EVM13520 | Purchase Spec. - Air Filter
EVM13521 | Purchase Spec. - Urea Hydrolyzer
EVM1A440 | Purchase Spec. - Deaerator
EVM1B520 | Inq/PO - Ammonia Storage Tank Engineering
Furnace
Furnace Basic Design
Furnace Eng'g Standard
EU310010 | Engineering Standard for Furnace Equip.
Furnace Reference Drawing
EU320010 | Furnace Reference Dwg (GA Dwg & L/D)
Furnace Vendor Drawing Review
GA Dwg / Outline Dwg
EU611010 | GA Dwg(0) Review - Primary Reformer
EU611020 | GA Dwg(0) Review - Start-up Heater
EU612030 | GA Dwg(0) Review - Urea Flare
EU61A040 | GA Dwg(0) Review - Auxiliary Boiler
EU61A060 | GA Dwg(0) Review - Flare
Loading Data
EU621010 | L/D(0) Review - Primary Reformer
EU621020 | L/D(0) Review - Start-up Heater
EU622030 | L/D(0) Review - Urea Flare
EU62A040 | L/D(0) Review - Auxiliary Boiler
EU62A060 | L/D(0) Review - Flare
Vendor P&ID
EU632030 | Vendor P&ID Review - Urea Flare
EU63A040 | Vendor P&ID Review - Auxiliary Boiler
EU63A060 | Vendor P&ID Review - Flare
Logic Diagram
EU651010 | Vendor Instrument Schedule & Set Point List Review - Primary Reformer
EU651020 | Vendor Instrument Schedule & Set Point List Review - Start-up Heater
EU652030 | Vendor Instrument Schedule & Set Point List Review - Urea Flare
EU65A040 | Vendor Instrument Schedule & Set Point List Review - Auxiliary Boiler
EU65A060 | Vendor Instrument Schedule & Set Point List Review - Flare
Other Vendor Dwg
EU6X1010 | Vendor Dwg Review - Primary Reformer
EU6X1020 | Vendor Dwg Review - Start-up Heater
EU6X2030 | Vendor Dwg Review - Urea Flare
EU6XA040 | Vendor Dwg Review - Auxiliary Boiler
EU6XA060 | Vendor Dwg Review - Flare
Coordination for Other Groups
Coordination for Piping
EU951011 | Outline Dwg for Equip. Layout - Furnace - Ammonia
EU951012 | Outline Dwg for 3D 1st Model Review - Furnace - Ammonia
EU952021 | Outline Dwg for 3D 1st Model Review - Furnace - Urea
EU952022 | Outline Dwg for 3D 2nd Model Review - Furnace - Urea
EU95A031 | Outline Dwg for Equip. Layout - Furnace - Utility
EU95A032 | Outline Dwg for 3D 1st Model Review - Furnace - Utiity
EU95A033 | Outline Dwg for 3D 2nd Model Review - Furnace - Utiity
Coordination for Civil & Architecture
EU981011 | L/D for Structural Calc. for Equip. Foundation - Furnace - Ammonia
EU981012 | L/D for Equip. Foundation Dwg - Furnace - Ammonia
EU982021 | L/D for Structural Calc. for Equip. Foundation - Furnace - Urea
EU982022 | L/D for Equip. Foundation Dwg - Furnace - Urea
EU98A031 | L/D for Structural Calc. for Equip. Foundation - Furnace - Utiity
EU98A032 | L/D for Equip. Foundation Dwg - Furnace - Utiity
3D Model Review
Furnace 3D Model Check with Vendor Dwg(F)
EUL50010 | Furnace 3D Model Check with Vendor Dwg(F)
Purchase Specification
Purchase Spec.
EUM11010 | Purchase Spec. - Primary Reformer
EUM11020 | Purchase Spec. - Start-up Heater
EUM12030 | Purchase Spec. - Flare
EUM1A040 | Purchase Spec. - Auxiliary Boiler
Machinery
Machinery Basic Design
Machinery Eng'g Standard
EM310010 | Engineering Standard for Machinery
Machinery Reference Drawing
EM320010 | Machinery Reference Dwg (GA Dwg & L/D)
Machinery Vendor Drawing Review
GA Dwg / Outline Dwg
EM610010 | GA Dwg(0) Review - Reciprocating Pump
EM610320 | GA Dwg(0) Review - Chemical Injection Unit
EM611020 | GA Dwg(0) Review - Semilean Solution Pump & Turbine
EM611030 | GA Dwg(0) Review - Lean Solution Pump
EM611040 | GA Dwg(0) Review - Centrifugal Pump (Middle & Light Duty) - Ammmonia
EM611050 | GA Dwg(0) Review - Diaphragm Pump
EM611055 | GA Dwg(0) Review - Off-spec Condensate Pump
EM611060 | GA Dwg(0) Review - PA Compressor & Turbine
EM611070 | GA Dwg(0) Review - NG Compressor & Turbine
EM611080 | GA Dwg(0) Review - SG Compressor & Turbine
EM611090 | GA Dwg(0) Review - Ammonia Compressor & Turbine
EM611100 | GA Dwg(0) Review - N2 Booster Compressor
EM611110 | GA Dwg(0) Review - Flue Gas & Combustion Air Blower
EM611120 | GA Dwg(0) Review - Start-up N2 Blower
EM611330 | GA Dwg(0) Review - Hydrogen Recovery Unit
EM611420 | GA Dwg(0) Review - Overhead Crane & Hoist
EM611430 | GA Dwg(0) Review - Sump Tank Mixer
EM612140 | GA Dwg(0) Review - HP Ammonia Pump
EM612150 | GA Dwg(0) Review - Carbamate Solution/Booster Pump
EM612170 | GA Dwg(0) Review - Centrifugal Pump (Middle & Light Duty) - Urea Synthesis
EM612175 | GA Dwg(0) Review - Centrifugal Pump (Middle & Light Duty) - Urea Granulation
EM612180 | GA Dwg(0) Review - CO2 Compressor & Turbine
EM612190 | GA Dwg(0) Review - Stripper Passivation Air Compressor
EM613200 | GA Dwg(0) Review - Granulation Fan/Blower
EM613450 | GA Dwg(0) Review - Bucket Elevator
EM613460 | GA Dwg(0) Review - Granulator (Lower)
EM613470 | GA Dwg(0) Review - Crusher
EM613480 | GA Dwg(0) Review - Granulation Scrubber
EM613490 | GA Dwg(0) Review - Extractor & Screen
EM61A210 | GA Dwg(0) Review - HP BFW Pump
EM61A230 | GA Dwg(0) Review - Cooling Water Pump
EM61A250 | GA Dwg(0) Review - Fire Water Pump
EM61A260 | GA Dwg(0) Review - Centrifugal Pump (Middle & Light Duty) - Utility
EM61A270 | GA Dwg(0) Review - Instrument Air Compressor & Dryer
EM61A280 | GA Dwg(0) Review - Steam Turbine for Pumps
EM61A300 | GA Dwg(0) Review - Emergency DEG
EM61A340 | GA Dwg(0) Review - Deminerized Water Treatment Unit
EM61A365 | GA Dwg(0) Review - CT Side Filter
EM61A370 | GA Dwg(0) Review - Waste Water Treatment Unit
EM61A390 | GA Dwg(0) Review - Cooling Tower
EM61B310 | GA Dwg(0) Review - Centrifugal Pump (Middle & Light Duty) - Offsite
EM61B410 | GA Dwg(0) Review - Refrigeration Unit
EM61B440 | GA Dwg(0) Review - Conveyor
EM61B520 | GA Dwg(0) Review - Reclaimer
EM61B540 | GA Dwg(0) Review - Raicar Loading System
Loading Data
EM620010 | L/D(0) Review - Reciprocating Pump
EM620320 | L/D(0) Review - Chemical Injection Unit
EM621020 | L/D(0) Review - Semilean Solution Pump & Turbine
EM621030 | L/D(0) Review - Lean Solution Pump
EM621040 | L/D(0) Review - Centrifugal Pump (Middle & Light Duty) - Ammmonia
EM621050 | L/D(0) Review - Diaphragm Pump
EM621055 | L/D(0) Review - Off-spec Condensate Pump
EM621060 | L/D(0) Review - PA Compressor & Turbine
EM621070 | L/D(0) Review - NG Compressor & Turbine
EM621080 | L/D(0) Review - SG Compressor & Turbine
EM621090 | L/D(0) Review - Ammonia Compressor & Turbine
EM621100 | L/D(0) Review - N2 Booster Compressor
EM621110 | L/D(0) Review - Flue Gas & Combustion Air Blower
EM621120 | L/D(0) Review - Start-up N2 Blower
EM621330 | L/D(0) Review - Hydrogen Recovery Unit
EM621420 | L/D(0) Review - Overhead Crane & Hoist
EM621430 | L/D(0) Review - Sump Tank Mixer
EM622140 | L/D(0) Review - HP Ammonia Pump
EM622150 | L/D(0) Review - Carbamate Solution/Booster Pump
EM622170 | L/D(0) Review - Centrifugal Pump (Middle & Light Duty) - Urea Synthesis
EM622175 | L/D(0) Review - Centrifugal Pump (Middle & Light Duty) - Urea Granulation
EM622180 | L/D(0) Review - CO2 Compressor & Turbine
EM622190 | L/D(0) Review - Stripper Passivation Air Compressor
EM623200 | L/D(0) Review - Granulation Fan/Blower
EM623450 | L/D(0) Review - Bucket Elevator
EM623460 | L/D(0) Review - Granulator (Lower)
EM623470 | L/D(0) Review - Crusher
EM623480 | L/D(0) Review - Granulation Scrubber
EM623490 | L/D(0) Review - Extractor & Screen
EM62A210 | L/D(0) Review - HP BFW Pump
EM62A230 | L/D(0) Review - Cooling Water Pump
EM62A250 | L/D(0) Review - Fire Water Pump
EM62A260 | L/D(0) Review - Centrifugal Pump (Middle & Light Duty) - Utility
EM62A270 | L/D(0) Review - Instrument Air Compressor & Dryer
EM62A280 | L/D(0) Review - Steam Turbine for Pumps
EM62A300 | L/D(0) Review - Emergency DEG
EM62A340 | L/D(0) Review - Deminerized Water Treatment Unit
EM62A365 | L/D(0) Review - CT Side Filter
EM62A370 | L/D(0) Review - Waste Water Treatment Unit
EM62A390 | L/D(0) Review - Cooling Tower
EM62B310 | L/D(0) Review - Centrifugal Pump (Middle & Light Duty) - Offsite
EM62B410 | L/D(0) Review - Refrigeration Unit
EM62B440 | L/D(0) Review - Conveyor
EM62B520 | L/D(0) Review - Reclaimer
EM62B540 | L/D(0) Review - Raicar Loading System
Vendor P&ID
EM630010 | Vendor P&ID Review - Reciprocating Pump
EM630320 | Vendor P&ID Review - Chemical Injection Unit
EM631020 | Vendor P&ID Review - Semilean Solution Pump & Turbine
EM631030 | Vendor P&ID Review - Lean Solution Pump
EM631040 | Vendor P&ID Review - Centrifugal Pump (Middle & Light Duty) - Ammmonia
EM631050 | Vendor P&ID Review - Diaphragm Pump
EM631055 | Vendor P&ID Review - Off-spec Condensate Pump
EM631060 | Vendor P&ID Review - PA Compressor & Turbine
EM631070 | Vendor P&ID Review - NG Compressor & Turbine
EM631080 | Vendor P&ID Review - SG Compressor & Turbine
EM631090 | Vendor P&ID Review - Ammonia Compressor & Turbine
EM631100 | Vendor P&ID Review - N2 Booster Compressor
EM631110 | Vendor P&ID Review - Flue Gas & Combustion Air Blower
EM631120 | Vendor P&ID Review - Start-up N2 Blower
EM631330 | Vendor P&ID Review - Hydrogen Recovery Unit
EM631410 | Vendor P&ID Review - Sump Tank Mixer
EM632140 | Vendor P&ID Review - HP Ammonia Pump
EM632150 | Vendor P&ID Review - Carbamate Solution/Booster Pump
EM632170 | Vendor P&ID Review - Centrifugal Pump (Middle & Light Duty) - Urea Synthesis
EM632175 | Vendor P&ID Review - Centrifugal Pump (Middle & Light Duty) - Urea Granulation
EM632180 | Vendor P&ID Review - CO2 Compressor & Turbine
EM632190 | Vendor P&ID Review - Stripper Passivation Air Compressor
EM633200 | Vendor P&ID Review - Granulation Fan/Blower
EM633430 | Vendor P&ID Review - Bucket Elevator
EM633440 | Vendor P&ID Review - Granulator (Lower)
EM633450 | Vendor P&ID Review - Crusher
EM633460 | Vendor P&ID Review - Granulation Scrubber
EM633470 | Vendor P&ID Review - Extractor & Screen
EM63A210 | Vendor P&ID Review - HP BFW Pump
EM63A230 | Vendor P&ID Review - Cooling Water Pump
EM63A250 | Vendor P&ID Review - Fire Water Pump
EM63A260 | Vendor P&ID Review - Centrifugal Pump (Middle & Light Duty) - Utility
EM63A270 | Vendor P&ID Review - Instrument Air Compressor & Dryer
EM63A280 | Vendor P&ID Review - Steam Turbine for Pumps
EM63A300 | Vendor P&ID Review - Emergency DEG
EM63A340 | Vendor P&ID Review - Deminerized Water Treatment Unit
EM63A365 | Vendor P&ID Review - CT Side Filter
EM63A370 | Vendor P&ID Review - Waste Water Treatment Unit
EM63B310 | Vendor P&ID Review - Centrifugal Pump (Middle & Light Duty) - Offsite
EM63B400 | Vendor P&ID Review - Refrigeration Unit
EM63B420 | Vendor P&ID Review - Conveyor
EM63B500 | Vendor P&ID Review - Reclaimer
EM63B520 | Vendor P&ID Review - Raicar Loading System
Allowable Nozzle Forces and Moment
EM641010 | Allowable Nozzle Forces & Moment Review - Semilean Solution Pump & Turbine
EM641020 | Allowable Nozzle Forces & Moment Review - Lean Solution Pump
EM641030 | Allowable Nozzle Forces & Moment Review - PA Compressor & Turbine
EM641040 | Allowable Nozzle Forces & Moment Review - NG Compressor & Turbine
EM641050 | Allowable Nozzle Forces & Moment Review - SG Compressor & Turbine
EM641060 | Allowable Nozzle Forces & Moment Review - Ammonia Compressor & Turbine
EM642070 | Allowable Nozzle Forces & Moment Review - HP Ammonia Pump
EM642080 | Allowable Nozzle Forces & Moment Review - Carbamate Solution/Booster Pump
EM642100 | Allowable Nozzle Forces & Moment Review - CO2 Compressor & Turbine
EM642110 | Allowable Nozzle Forces & Moment Review - Stripper Passivation Air Compressor
EM64A120 | Allowable Nozzle Forces & Moment Review - HP BFW Pump
EM64A140 | Allowable Nozzle Forces & Moment Review - Cooling Water Pump
Logic Diagram
EM651010 | Vendor Instrument Schedule & Set Point List Review - PA Compressor & Turbine
EM651020 | Vendor Instrument Schedule & Set Point List Review - NG Compressor & Turbine
EM651030 | Vendor Instrument Schedule & Set Point List Review - SG Compressor & Turbine
EM651040 | Vendor Instrument Schedule & Set Point List Review - Ammonia Compressor & Turbine
EM651060 | Vendor Instrument Schedule & Set Point List Review - Semilean Solution Pump Turbine
EM651120 | Vendor Instrument Schedule & Set Point List Review - Hydrogen Recovery Unit
EM652060 | Vendor Instrument Schedule & Set Point List Review - CO2 Compressor & Turbine
EM652070 | Vendor Instrument Schedule & Set Point List Review - Stripper Passivation Air Compressor
EM653200 | Vendor Instrument Schedule & Set Point List Review - Granulator (Lower)
EM65A080 | Vendor Instrument Schedule & Set Point List Review - Instrument Air Compressor & Dryer
EM65A090 | Vendor Instrument Schedule & Set Point List Review - Steam Turbine for Pumps
EM65A110 | Vendor Instrument Schedule & Set Point List Review - Emergency DEG
EM65A130 | Vendor Instrument Schedule & Set Point List Review - Deminerized Water Treatment Unit
EM65A155 | Vendor Instrument Schedule & Set Point List Review - CT Side Filter
EM65A160 | Vendor Instrument Schedule & Set Point List Review - Waste Water Treatment Unit
EM65B190 | Vendor Instrument Schedule & Set Point List Review - Refrigeration Unit
EM65B210 | Vendor Instrument Schedule & Set Point List Review - Reclaimer
Other Vendor Dwg
EM6X0010 | Vendor Dwg Review - Reciprocating Pump
EM6X0320 | Vendor Dwg Review - Chemical Injection Unit
EM6X1020 | Vendor Dwg Review - Semilean Solution Pump & Turbine
EM6X1030 | Vendor Dwg Review - Lean Solution Pump
EM6X1040 | Vendor Dwg Review - Centrifugal Pump (Middle & Light Duty) - Ammmonia
EM6X1050 | Vendor Dwg Review - Diaphragm Pump
EM6X1060 | Vendor Dwg Review - PA Compressor & Turbine
EM6X1070 | Vendor Dwg Review - NG Compressor & Turbine
EM6X1080 | Vendor Dwg Review - SG Compressor & Turbine
EM6X1090 | Vendor Dwg Review - Ammonia Compressor & Turbine
EM6X1100 | Vendor Dwg Review - N2 Booster Cpmressor
EM6X1110 | Vendor Dwg Review - Flue Gas & Combustion Air Blower
EM6X1120 | Vendor Dwg Review - Start-up N2 Blower
EM6X1330 | Vendor Dwg Review - Hydrogen Recovery Unit
EM6X1420 | Vendor Dwg Review - Overhead Crane & Hoist
EM6X1430 | Vendor Dwg Review - Sump Tank Mixer
EM6X2140 | Vendor Dwg Review - HP Ammonia Pump
EM6X2150 | Vendor Dwg Review - Carbamate Solution/Booster Pump
EM6X2170 | Vendor Dwg Review - Centrifugal Pump (Middle & Light Duty) - Urea Synthesis
EM6X2175 | Vendor Dwg Review - Centrifugal Pump (Middle & Light Duty) - Urea Granulation
EM6X2180 | Vendor Dwg Review - CO2 Compressor & Turbine
EM6X2190 | Vendor Dwg Review - Stripper Passivation Air Compressor
EM6X3200 | Vendor Dwg Review - Granulation Fan/Blower
EM6X3450 | Vendor Dwg Review - Bucket Elevator
EM6X3460 | Vendor Dwg Review - Granulator (Lower)
EM6X3470 | Vendor Dwg Review - Crusher
EM6X3480 | Vendor Dwg Review - Granulation Scrubber
EM6X3490 | Vendor Dwg Review - Extractor & Screen
EM6X4500 | Vendor Dwg Review - Off-spec Condensate Pump
EM6XA210 | Vendor Dwg Review - HP BFW Pump
EM6XA230 | Vendor Dwg Review - Cooling Water Pump
EM6XA250 | Vendor Dwg Review - Fire Water Pump
EM6XA260 | Vendor Dwg Review - Centrifugal Pump (Middle & Light Duty) - Utility
EM6XA270 | Vendor Dwg Review - Instrument Air Compressor & Dryer
EM6XA280 | Vendor Dwg Review - Steam Turbine for Pumps
EM6XA300 | Vendor Dwg Review - Emergency DEG
EM6XA340 | Vendor Dwg Review - Deminerized Water Treatment Unit
EM6XA365 | Vendor Dwg Review - CT Side Filter
EM6XA370 | Vendor Dwg Review - Waste Water Treatment Unit
EM6XA390 | Vendor Dwg Review - Cooling Tower
EM6XB310 | Vendor Dwg Review - Centrifugal Pump (Middle & Light Duty) - Offsite
EM6XB410 | Vendor Dwg Review - Refrigeration Unit
EM6XB440 | Vendor Dwg Review - Conveyor
EM6XB520 | Vendor Dwg Review - Reclaimer
EM6XB540 | Vendor Dwg Review - Raicar Loading System
Coordination for Other Groups
Coordination for Piping
EM951011 | Outline Dwg for Equip. Layout - Machinery - Ammonia
EM951012 | Outline Dwg for 3D 1st Model Review - Machinery - Ammonia
EM951013 | Outline Dwg for 3D 2nd Model Review - Machinery - Ammonia
EM952021 | Outline Dwg for Equip. Layout - Machinery - Urea
EM952022 | Outline Dwg for 3D 1st Model Review - Machinery - Urea
EM952023 | Outline Dwg for 3D 2nd Model Review - Machinery - Urea
EM95A031 | Outline Dwg for Equip. Layout - Machinery - Utility
EM95A032 | Outline Dwg for 3D 1st Model Review - Machinery - Utiity
EM95A033 | Outline Dwg for 3D 2nd Model Review - Machinery - Utiity
EM95B041 | Outline Dwg for 3D 1st Model Review - Machinery - Offsite
EM95B042 | Outline Dwg for 3D 2nd Model Review - Machinery - Offsite
Coordination for Civil & Architecture
EM981010 | L/D for Structural Calc. for Equip. Foundation - Machinery - Ammonia
EM981020 | L/D for Equip. Foundation Dwg - Machinery - Ammonia
EM981030 | L/D for Structural Calc. for Equip. Foundation - Machinery - Compressor Shelter
EM981040 | L/D for Structural Calc. for Equip. Foundation - Machinery - GRH
EM981050 | GA for Structural Calc. - Machinery - HP BFW Pump Enclosure (BG-825) (0)
EM981060 | L/D for Structural Calc. - Machinery - HP BFW Pump Enclosure (BG-825) (0)
EM981070 | Heat Emission for HVAC - HP BFW Pump Enclosure (BG-825)
EM981080 | GA for Structural Calc. - Machinery - Ammonia Side Filter Enclosure (BG-821)
EM981090 | Heat Loss for HVAC (0) - Ammonia Side Filter Enclosure (BG-821)
EM981100 | L/D for Structural Calc. - Ammonia Side Filter Enclosure (BG-821)
EM981110 | L/D (0) for Structural Calc. for Equip. Foundation - Machinery - NG Compressor Shed SH-831
EM981120 | GA (0) for Structural Calc. for Equip. Foundation - Machinery - NG Compressor Shed SH-831
EM982020 | L/D for Structural Calc. for Equip. Foundation - Machinery - Urea
EM982030 | L/D for Equip. Foundation Dwg - Machinery - Urea
EM982040 | GA for Structural Calc. - Machinery - Urea Side Filter Enclosure (BG-823)
EM982050 | Heat Loss for HVAC (0) - Urea Side Filter Enclosure (BG-823)
EM982060 | L/D for Structural Calc. - Urea Side Filter Enclosure (BG-823)
EM982070 | L/D for Structural Calc. for Equip. Foundation - Machinery - DS-201
EM982080 | L/D for Structural Calc. for Equip. Foundation - Machinery - DS-201 (0)
EM982090 | L/D for Structural Calc. for Equip. Foundation - Machinery - DS-202 (0)
EM982100 | L/D for Structural Calc. for Equip. Foundation - Machinery - DS-203 (0)
EM982110 | L/D for Structural Calc. for Equip. Foundation - Machinery - DS-204 (0)
EM982120 | L/D for Structural Calc. for Equip. Foundation - Machinery - DS-205 (0)
EM98A030 | L/D for Structural Calc. for Equip. Foundation - Machinery - Utiity
EM98A040 | L/D for Equip. Foundation Dwg - Machinery - Utiity
EM98A050 | L/D (0) for Structural Calc. for Equip. Foundation - Machinery - IA Compressor Shed SH-831
EM98A060 | GA (0) for Structural Calc. for Equip. Foundation - Machinery - IA Compressor Shed SH-831
EM98A070 | GA for Structural Calc. - Machinery - Ammonia CW Pump Enclosure (BG-820) (P)
EM98A080 | L/D for Structural Calc. - Machinery - Ammonia CW Pump Enclosure (BG-820) (P)
EM98A090 | GA for Structural Calc. - Machinery - Ammonia CW Pump Enclosure (BG-820) (0)
EM98A100 | L/D for Structural Calc. - Machinery - Ammonia CW Pump Enclosure (BG-820) (0)
EM98A110 | Heat Emission for HVAC - Ammonia CW Pump Enclosure (BG-820)
EM98A120 | GA for Structural Calc. - Machinery - Urea CW Pump Enclosure (BG-822) (P)
EM98A130 | L/D for Structural Calc. - Machinery - Urea CW Pump Enclosure (BG-822) (P)
EM98A140 | GA for Structural Calc. - Machinery - Urea CW Pump Enclosure (BG-822) (0)
EM98A150 | L/D for Structural Calc. - Machinery - Urea CW Pump Enclosure (BG-822) (0)
EM98A160 | Heat Emission for HVAC - Urea CW Pump Enclosure (BG-822)
EM98A170 | GA for Structural Calc. - Machinery - DEMI & RWT Unit Enclosure (BG-818)
EM98A180 | Heat Loss for HVAC (P) - DEMI & RWT Unit Enclosure (BG-818)
EM98A190 | L/D for Structural Calc. - Machinery - DEMI & RWT Unit Enclosure (BG-818)
EM98A200 | GA for Structural Calc. - Machinery - Waste Water Treatment Unit Enclosure (BG-819)
EM98A210 | Heat Loss for HVAC (0) - Waste Water Treatment Unit Enclosure (BG-819)
EM98A220 | L/D for Structural Calc. - Waste Water Treatment Unit Enclosure (BG-819)
EM98A230 | GA for Structural Calc. - Machinery - HP BFW Injection Unit Enclosure (BG-8xx)
EM98A240 | Heat Loss for HVAC (0) - HP BFW Injection Unit Enclosure (BG-8xx)
EM98A250 | L/D for Structural Calc. - HP BFW Injection Unit Enclosure (BG-8xx)
EM98A260 | GA for Structural Calc. - Machinery - MP BFW Injection Unit Enclosure (BG-8xx)
EM98A270 | Heat Loss for HVAC (0) - MP BFW Injection Unit Enclosure (BG-8xx)
EM98A280 | L/D for Structural Calc. - MP BFW Injection Unit Enclosure (BG-8xx)
EM98A290 | GA for Structural Calc. - Machinery - MP BFW Pump Enclosure (BG-826) (0)
EM98A300 | L/D for Structural Calc. - Machinery - MP BFW Pump Enclosure (BG-826) (0)
EM98A310 | Heat Emission for HVAC - MP BFW Pump Enclosure (BG-826)
EM98B040 | L/D for Structural Calc. for Equip. Foundation - Machinery - Offsite
EM98B050 | L/D for Equip. Foundation Dwg - Machinery - Offsite
EM98B060 | GA for Structural Calc. - Machinery - Fire Water Pump Enclosure (BG-824) (P)
EM98B070 | L/D for Structural Calc. - Machinery - Fire Water Pump Enclosure (BG-824) (P)
EM98B080 | GA for Structural Calc. - Machinery - Fire Water Pump Enclosure (BG-824) (0)
EM98B090 | L/D for Structural Calc. - Machinery - Fire Water Pump Enclosure (BG-824) (0)
EM98B100 | Heat Emission for HVAC - Fire Water Pump Enclosure (BG-824)
EM98B110 | GA for Structural Calc. - Machinery - Bagging Unit Enclosure, Storage House (BG-812/813)
EM98B120 | Heat Loss for HVAC (P) - Bagging Unit Enclosure, Storage House (BG-812/813)
EM98B130 | GA (Reclaimer) for Structural Calc. - Machinery - Bulk Urea Storage Warehouse (BG-811)
EM98B140 | GA (Tripper Conveyor) for Structural Calc. - Machinery - Bulk Urea Storage Warehouse (BG-811)
EM98B150 | Heat Emission for HVAC - Bulk Urea Storage Warehouse (BG-811)
3D Model Review
Machinery 3D Model Check with Vendor Dwg
EML50010 | Machinery 3D Model Check with Vendor Dwg(F)
Purchase Specification
Purchase Spec.
EMM10010 | Purchase Spec. - Reciprocating Pump
EMM10320 | Purchase Spec. - Chemical Injection Unit
EMM11020 | Purchase Spec. - Semilean Solution Pump & Turbine
EMM11030 | Purchase Spec. - Lean Solution Pump
EMM11040 | Purchase Spec. - Centrifugal Pump (Middle & Light Duty) - Ammmonia
EMM11050 | Purchase Spec. - Diaphragm Pump
EMM11055 | Purchase Spec. - Off-spec Condensate Pump
EMM11060 | Purchase Spec. - Process Compressors & Turbines
EMM11100 | Purchase Spec. - N2 Booster Compressor
EMM11110 | Purchase Spec. - Flue Gas & Combustion Air Blower
EMM11120 | Purchase Spec. - Start-up N2 Blower
EMM11330 | Purchase Spec. - Hydrogen Recovery Unit
EMM11420 | Purchase Spec. - Overhead Crane & Hoist
EMM11430 | Purchase Spec. - Sump Tank Mixer
EMM12140 | Purchase Spec. - HP Ammonia Pump, Carbonate Solution Pump and Booster Pumps
EMM12170 | Purchase Spec. - Centrifugal Pump (Middle & Light Duty) - Urea Synthesis
EMM12175 | Purchase Spec. - Centrifugal Pump (Middle & Light Duty) - Urea Granulation
EMM12190 | Purchase Spec. - Stripper Passivation Air Compressor
EMM13200 | Purchase Spec. - Granulation Fan/Blower
EMM13450 | Purchase Spec. - Bucket Elevator
EMM13460 | Purchase Spec. - Granulator (Lower)
EMM13470 | Purchase Spec. - Crusher
EMM13480 | Purchase Spec. - Granulation Scrubber
EMM13490 | Purchase Spec. - Extractor & Screen
EMM1A210 | Purchase Spec. - BFW Pump
EMM1A230 | Purchase Spec. - Cooling Water Pump
EMM1A250 | Purchase Spec. - Fire Water Pump
EMM1A260 | Purchase Spec. - Centrifugal Pump (Middle & Light Duty) - Utility
EMM1A270 | Purchase Spec. - Instrument Air Compressor & Dryer
EMM1A280 | Purchase Spec. - Steam Turbine for Pumps
EMM1A300 | Purchase Spec. - Emergency DEG
EMM1A340 | Purchase Spec. - Deminerized Water Treatment Unit
EMM1A365 | Purchase Spec. - CT Side Filter
EMM1A370 | Purchase Spec. - Waste Water Treatment Unit
EMM1A390 | Purchase Spec. - Cooling Tower
EMM1B410 | Purchase Spec. - Refrigeration Unit
EMM1B440 | Purchase Spec. - Conveyor
EMM1B520 | Purchase Spec. - Reclaimer
EMM1B540 | Purchase Spec. - Raicar Loading System
Piping
Piping Design Basis
Piping Design Basis
EP310010 | Piping Design Basis
Piping Material Spec.
EP320010 | Piping Material Specification
Piping Material Identification Spec.
EP330010 | Piping Material Identification Specification
Fire Protection System Design Basis
EP360010 | Fire Protection System Design Basis
Piping & Instrument Diagram
P&I Diagram - Process
Process P&ID for Basic Design
EP411010 | P&ID - Process(P) - Ammmonia
EP412010 | P&ID - Process(P) - Urea
Process P&ID (IFA)
EP411020 | P&ID - Process(0) - Ammmonia
EP412020 | P&ID - Process(0) - Urea
Process P&ID of Follow-Up Comment & HAZOP Study
EP411030 | P&ID - Process(1) - Ammmonia
EP412030 | P&ID - Process(1) - Urea
Process P&ID of Follow-Up Vendor Dwg
EP411040 | P&ID - Process(2) - Ammmonia
EP412040 | P&ID - Process(2) - Urea
Process P&ID for Construction
EP411050 | P&ID - Process(IFC) - Ammmonia
EP412050 | P&ID - Process(IFC) - Urea
P&I Diagram - Utility
Utility P&ID (IFA)
EP42A020 | P&ID - Utility(0) - Utility
EP42B020 | P&ID - Utility(0) - Offsite
Utility P&ID of Follow-Up Comment & HAZOP Study
EP42A030 | P&ID - Utility(1) - Utility
EP42B030 | P&ID - Utility(1) - Offsite
Utility P&ID of Follow-Up Vendor Dwg
EP42A040 | P&ID - Utility(2) - Utility
EP42B040 | P&ID - Utility(2) - Offsite
Utility P&ID for Construction
EP42A050 | P&ID - Utility(IFC) - Utility
EP42B050 | P&ID - Utility(IFC) - Offsite
P&I Diagram - Fire Protection
Fire Protection P&ID (IFA)
EP430010 | P&ID - Fire Protection(0)
Line Index
Line Index (IFA)
EP461020 | Line Index (IFA) - Ammonia
EP462020 | Line Index (IFA) - Urea
EP46A020 | Line Index (IFA) - Utility
EP46B020 | Line Index (IFA) - Offsite
Line Index for Construction
EP461030 | Line Index for Construction - Ammonia
EP462030 | Line Index for Construction - Urea
EP46A030 | Line Index for Construction - Utility
EP46B030 | Line Index for Construction - Offsite
Plot Plan / Equipment Layout
Plot Plan
Plot Plan for Basic Design
EP510010 | Plot Plan(P)
Plot Plan (IFA)
EP510020 | Plot Plan(0)
Equipment Layout
Equipment Layout (IFA)
EP521010 | Equip. Layout(0) - Ammonia
EP522010 | Equip. Layout(0) - Urea
EP52A010 | Equip. Layout(0) - Utility
EP52B010 | Equip. Layout(0) - Offsite
Equipment Layout Follow-Up Vendor Dwg
EP521020 | Equip. Layout(F) - Ammonia
EP522020 | Equip. Layout(F) - Urea
EP52A020 | Equip. Layout(F) - Utility
EP52B020 | Equip. Layout(F) - Offsite
Fire Protection System Layout
EP530010 | Fire Protection System Layout
Piping Route Plan
Piping Route Plan for Piperack
EP611010 | Piping Route Plan for Ammonia Piperack
EP612020 | Piping Route Plan for Urea Piperack
EP61A030 | Piping Route Plan for Utility Piperack
EP61B040 | Piping Route Plan for Offsite Piperack
Piping Route Plan around Equipment
EP620010 | Piping Route Plan(P) for Pump Head Calculation
EP621020 | Piping Route Plan for Ammonia Area
EP622030 | Piping Route Plan for Urea Area
EP62A040 | Piping Route Plan for Utility Area
EP62B050 | Piping Route Plan for Offsite Area
Underground Piping Design
U/G Piping Plan
EP710010 | U/G Piping Plan
U/G Piping Layout Dwg
EP720010 | U/G Piping Layout
Information for Other Group
Pipe Rack Plan & L/D
Piperack L/D for Civil Structural Calc.
EP811010 | Pipe Rack Plan & L/D(0) - Ammonia
EP811050 | L/D(0) for PR-101
EP811060 | L/D(0) for PR-102
EP811070 | L/D(0) for PR-103
EP811120 | L/D(0) for GRH
EP811130 | L/D(0) for LR-101
EP811140 | L/D(0) for LR-102
EP811150 | L/D(0) for LR-106
EP811160 | L/D(0) for LR-105
EP811170 | L/D(0) for LR-107
EP811180 | L/D(0) for LR-104
EP811190 | L/D(0) for LR-103
EP811200 | L/D(0) for LR-108
EP811210 | L/D(0) for LR-109
EP811220 | L/D(0) for LS-101
EP811230 | L/D(0) for LS-102
EP811240 | L/D(0) for LS-103
EP811250 | L/D(0) for LS-104
EP811260 | L/D(0) for LS-105
EP812010 | Pipe Rack Plan & L/D(0) - Urea
EP812040 | L/D(0) for PR-201
EP812050 | L/D(0) for PR-202
EP812060 | L/D(0) for PR-203
EP812070 | L/D(0) for PR-204
EP812140 | L/D(0) for LR-201
EP812150 | L/D(0) for LR-202
EP812160 | L/D(0) for LR-203
EP812170 | L/D(0) for DS-201
EP812180 | L/D(0) for DS-202
EP812190 | L/D(0) for DS-203
EP812200 | L/D(0) for DS-204
EP812210 | L/D(0) for DS-205
EP81A010 | Pipe Rack Plan & L/D(0) - Utility
EP81A020 | L/D(0) for PR-401
EP81A030 | L/D(0) for PR-402
EP81A040 | L/D(0) for PR-403
EP81A050 | L/D(0) for PR-404
EP81A060 | L/D(0) for PR-405
EP81A070 | L/D(0) for SL-401
EP81A080 | L/D(0) for SL-402
EP81A090 | L/D(0) for SL-403
EP81A100 | L/D(0) for SL-404
EP81A110 | L/D(0) for SL-405
EP81A120 | L/D(0) for SL-406
EP81A130 | L/D(0) for SL-407
EP81A140 | L/D(0) for SL-408
EP81A150 | L/D(0) for SL-411
EP81B010 | Pipe Rack Plan & L/D(0) for PR-601
EP81B020 | Pipe Rack Plan & L/D(0) for PR-602
EP81B030 | Pipe Rack Plan & L/D(0) for PR-611
EP81B040 | L/D(0) for SL-604
EP81B050 | L/D(0) for SL-601
EP81B060 | L/D(0) for SL-602
EP81B070 | L/D(0) for SL-603
Piperack L/D for Civil Detail Design
EP811020 | Pipe Rack Plan & L/D(1) for PR-101
EP811030 | Pipe Rack Plan & L/D(1) for PR-102
EP811040 | Pipe Rack Plan & L/D(1) for PR-103
EP812020 | Pipe Rack Plan & L/D(1) for PR-201
EP812030 | Pipe Rack Plan & L/D(1) for PR-202
EP81A025 | L/D(1) for PR-401
EP81A035 | L/D(1) for PR-402
Structure & Building Plan & L/D
Structure & Building L/D for Civil Structural Calc.
EP821010 | Structure Plan & L/D(0) - Ammonia
EP821015 | L/D(0) for ES-101
EP821030 | L/D(0) for ES-102
EP821040 | L/D(0) for ES-103
EP821050 | L/D(0) for Compressor Shelter
EP821060 | L/D(0) for HP BFW Pump Enclosure (BG-825)
EP821070 | L/D(0) for Ammonia Side Filter Enclosure (BG-821)
EP821080 | L/D(0) for NG Compressor Shed SH-831
EP822010 | Structure Plan & L/D(0) - Urea
EP822030 | L/D(0) for ES-201
EP822040 | L/D(0) for ES-202
EP822050 | L/D(0) for ES-203A
EP822060 | L/D(0) for ES-203B
EP822070 | L/D(0) for ES-204
EP822080 | L/D(0) for ES-205
EP822090 | L/D(0) for Urea Side Filter Enclosure (BG-823)
EP82A010 | L/D(0) for IA Compressor Shed SH-831
EP82A020 | L/D(0) for Ammonia CW Pump Enclosure (BG-820)
EP82A030 | L/D(0) for Urea CW Pump Enclosure (BG-822)
EP82A040 | L/D(0) for DEMI & RWT Unit Enclosure (BG-818)
EP82A050 | L/D(0) for Waste Water Treatment Unit Enclosure (BG-819)
EP82A060 | L/D(0) for HP BFW Injection Unit Enclosure (BG-8xx)
EP82A070 | L/D(0) for MP BFW Injection Unit Enclosure (BG-8xx)
EP82A080 | L/D(0) for MP BFW Pump Enclosure (BG-826)
EP82B010 | L/D(0) for Fire Water Pump Enclosure (BG-824)
EP82B020 | L/D(0) for Bagging Unit Enclosure, Storage House (BG-812/813)
EP82B030 | L/D(0) for Bulk Urea Storage Warehouse (BG-811)
Structure & Building L/D for Civil Detail Design
EP821020 | Structure Plan & L/D(1) - Ammonia
EP822020 | Structure Plan & L/D(1) - Urea
Nozzle Orientation Plan
EP831010 | Nozzle Orientation Plan - Ammonia
EP832020 | Nozzle Orientation Plan - Urea
EP83A030 | Nozzle Orientation Plan - Utility
EP83B040 | Nozzle Orientation Plan - Offsite
Piping Support Pad Plan
EP841010 | Piping Support Pad Plan - Ammonia
EP842020 | Piping Support Pad Plan - Urea
EP84A030 | Piping Support Pad Plan - Utility
Platform and Stage Plan & L/D
EP851010 | Platform & Stage Plan & L/D - Ammmonia
EP852020 | Platform & Stage Plan & L/D - Urea
EP85A030 | Platform & Stage Plan & L/D - Utility
Piping Sewer & Pit Plan
EP860010 | Piping Sewer & Pit Plan
Piping Penetration Hole Plan
EP871010 | Piping Penetration Hole Plan - Ammonia
EP871020 | Piping Penetration Hole Information for PR-101
EP871030 | Piping Penetration Hole Information for PR-102
EP871040 | Piping Penetration Hole Information for PR-103
EP871050 | Piping Penetration Hole Information for ES-101
EP871060 | Piping Penetration Hole Information for ES-102
EP871070 | Piping Penetration Hole Information for ES-103
EP871080 | Piping Penetration Hole Information for Compressor Shelter
EP871090 | Piping Penetration Hole Information for GRH
EP872020 | Piping Penetration Hole Plan - Urea
EP872030 | Piping Penetration Hole Information for PR-201
EP872040 | Piping Penetration Hole Information for PR-202
EP872050 | Piping Penetration Hole Information for ES-201
EP872060 | Piping Penetration Hole Information for ES-202
EP872070 | Piping Penetration Hole Information for ES-203A
EP872080 | Piping Penetration Hole Information for ES-203B
EP872090 | Piping Penetration Hole Information for ES-204
EP872100 | Piping Penetration Hole Information for ES-205
EP872130 | Piping Penetration Hole Information for DS-201
EP872140 | Piping Penetration Hole Information for DS-202
EP872150 | Piping Penetration Hole Information for DS-203
EP872160 | Piping Penetration Hole Information for DS-204
EP872170 | Piping Penetration Hole Information for DS-205
Embedded Piping Support Plate Plan
EP881010 | Embedded Piping Support Plate Plan - Ammonia
EP881020 | Embedded Item Information for PR-101
EP881030 | Embedded Item Information for PR-102
EP881040 | Embedded Item Information for PR-103
EP881050 | Embedded Item Information for ES-101
EP881060 | Embedded Item Information for ES-102
EP881070 | Embedded Item Information for ES-103
EP881080 | Embedded Plate Drawing for PR-101 (IFI)
EP881090 | Embedded Plate Drawing for PR-101 (IFC)
EP881100 | Embedded Plate Drawing for PR-102 (IFI)
EP881110 | Embedded Plate Drawing for PR-102 (IFC)
EP881120 | Embedded Plate Drawing for PR-103 (IFI)
EP881130 | Embedded Plate Drawing for PR-103 (IFC)
EP881140 | Embedded Plate Drawing for ES-101 (IFI)
EP881150 | Embedded Plate Drawing for ES-101 (IFC)
EP881160 | Embedded Plate Drawing for ES-102 (IFI)
EP881170 | Embedded Plate Drawing for ES-102 (IFC)
EP881180 | Embedded Plate Drawing for ES-103 (IFI)
EP881190 | Embedded Plate Drawing for ES-103 (IFC)
EP881200 | Embedded Item Information for LR-104
EP881210 | Embedded Plate Drawing for LR-104 (IFI)
EP881220 | Embedded Plate Drawing for LR-104 (IFC)
EP881230 | Embedded Item Information for Compressor Shelter
EP881240 | Embedded Plate Drawing for Compressor Shelter (IFI)
EP881250 | Embedded Plate Drawing for Compressor Shelter (IFC)
EP882020 | Embedded Piping Support Plate Plan - Urea
EP882030 | Embedded Item Information for PR-201
EP882040 | Embedded Item Information for PR-202
EP882050 | Embedded Item Information for ES-201
EP882060 | Embedded Item Information for ES-202
EP882070 | Embedded Item Information for ES-203A
EP882080 | Embedded Item Information for ES-203B
EP882090 | Embedded Plate Drawing for PR-201 (IFI)
EP882100 | Embedded Plate Drawing for PR-201 (IFC)
EP882110 | Embedded Plate Drawing for PR-202 (IFI)
EP882120 | Embedded Plate Drawing for PR-202 (IFC)
EP882130 | Embedded Plate Drawing for ES-201 (IFI)
EP882140 | Embedded Plate Drawing for ES-201 (IFC)
EP882150 | Embedded Plate Drawing for ES-202 (IFI)
EP882160 | Embedded Plate Drawing for ES-202 (IFC)
EP882170 | Embedded Plate Drawing for ES-203A (IFI)
EP882180 | Embedded Plate Drawing for ES-203A (IFC)
EP882190 | Embedded Plate Drawing for ES-203B (IFI)
EP882200 | Embedded Plate Drawing for ES-203B (IFC)
Calculation & Analysis
Piping Pressure Loss Calculation
Piping S.Head and Pressure Loss Calculation for Rotating Machine Data Sheet
EP920010 | Piping S.Head and Pressure Loss Calculation(P)
Piping Pressure Loss Calculation for Piping Layout Dwg
EP920020 | Piping Pressure Loss Calculation(0)
Piping Thermal Stress Calculation
Piping Thermal Stress Calculation for Piperack/Structure Plan & L/D
EP930010 | Piping Thermal Stress Calculation(0)
Piping Thermal Stress Calculation for Piping Layout
EP930020 | Piping Thermal Stress Calculation(1)
Piping Thermal Stress Calculation for Final
EP930030 | Piping Thermal Stress Calculation(F)
Piping Earthquake-Proof Calculation
EP940010 | Piping Earthquake-Proof Calculation
Safety Valve Sizing Calculation
EP950010 | Safety Valve Sizing Calculation
Restriction Orifice Calculation
EP960010 | Restriction Orifice Calculation
Piping Vibration Calculation
EP970010 | Piping Vibration Calculation
Calculation for Fire Protection
EP990010 | Calculation for Fire Protection
Piping Arrangement Dwg
General Piping Arrangement Dwg around Equipment
EPA21010 | Piping Arrangement Dwg Issue - Ammonia
EPA22020 | Piping Arrangement Dwg Issue - Urea
EPA2A030 | Piping Arrangement Dwg Issue - Utility
EPA2B040 | Piping Arrangement Dwg Issue - Offsite
Piping Isometric Dwg
Piping Isometric Dwg around Equipment
EPB21010 | Isometric Dwg Issue - Ammonia
EPB22020 | Isometric Dwg Issue - Urea
EPB2A030 | Isometric Dwg Issue - Utility
EPB2B040 | Isometric Dwg Issue - Offsite
Piping Support Dwg
Support Study
EPC10010 | Support Study
Piping Support Layout Dwg
EPC21010 | Piping Support Layout Dwg - Ammmonia
EPC22020 | Piping Support Layout Dwg - Urea
EPC2A030 | Piping Support Layout Dwg - Utility
EPC2B040 | Piping Support Layout Dwg - Offsite
Piping Support Foundation Layout Dwg
EPC31010 | Piping Support Foundation Layout Dwg - Ammmonia
EPC32020 | Piping Support Foundation Layout Dwg - Urea
EPC3A030 | Piping Support Foundation Layout Dwg - Utility
EPC3B040 | Piping Support Foundation Layout Dwg - Offsite
Support Style List around Equipment
EPC51010 | Support Style List - Ammmonia
EPC52020 | Support Style List - Urea
EPC5A030 | Support Style List - Utility
EPC5B040 | Support Style List - Offsite
Piping Material Data Sheet
Piping Material Data Sheet
EPD10010 | Valve Data Sheet
EPD10020 | Safety Device Data Sheet
EPD10030 | Complete Parts Data Sheet
EPD10040 | Spring Hanger Data Sheet
EPD10050 | Fire Protection Material Data Sheet
Piping Vendor Dwg Review
Other Vendor Dwg
EPEX0010 | Valve Vendor Dwg Review
EPEX0020 | Safety Device Vendor Dwg Review
EPEX0030 | Complete Parts Vendor Dwg Review 1st
EPEX0040 | Fire Protection Material Vendor Dwg Review
3D Modeling Work
3D Set Up
EPK10010 | 3D Set Up
3D Modeling Work for Equipment & Machinery
3D Modeling for Equipment & Machinery for 1st Review
EPK50010 | 3D Create & Check Equip. & Machinery
3D Modeling for Equipment & Machinery for 2nd Review
EPK50020 | 3D Update Equip. Model for 2nd Review
3D Modeling Work for U/G Piping
EPK80010 | 3D Create & Check U/G Piping
3D Modeling Work for A/G Piping
3D Modeling for A/G Piping for 1st Review
EPK90010 | 3D Create & Check Major AG Piping
3D Modeling for A/G Piping for 2nd Review
EPK90020 | 3D Create & Check AG Piping (2" & Larger)
3D Modeling for A/G Piping for 3rd Review
EPK90030 | 3D Create & Check AG Piping (11/2" & Smaller), Vendor Scope
A/G Piping Follow-Up 3rd Review
EPK90040 | 3D Update AG Piping
3D Modeling Work for Others
EPKX0010 | 3D Create & Check Stage, Platform, Ladder
EPKX0020 | 3D Create & Check Volume of Maintenance, Access, Safety
EPKX0030 | 3D Create & Check Fire Fighting & Safety Equip.
EPKX0040 | 3D Create & Check Space for Construction, Precommissioning
3D Model Review
Internal Review & Follow 1st
EPL10010 | Internal Review, Clash Check & Follow 1st
3D Model Review 1st (30%)
EPL20010 | 3D Model Review 1st
Internal Review & Follow 2nd
EPL30010 | Internal Review, Clash Check & Follow 2nd
3D Model Review 2nd (60%)
EPL40010 | 3D Model Review 2nd
Internal Review & Follow 3rd
EPL50010 | Internal Review, Clash Check & Follow 3rd
3D Model Review 3rd (90%)
EPL60010 | 3D Model Review 3rd
Purchase Spec. / Subcontract Spec.
Subcontract Spec.
EPM20010 | Piping Detail Design Inquiry Spec
Piping MTO
U/G Piping Material MTO (Fitting / Flange / Bolt / Nut / Gasket)
EPN10010 | U/G Piping Material MTO
A/G Piping Material MTO (Fitting / Flange / Bolt / Nut / Gasket)
AGP 1st MTO
EPN30010 | A/G Piping Material 1st MTO
AGP 2nd MTO
EPN30020 | A/G Piping Material 2nd MTO
AGP 3rd MTO
EPN30030 | A/G Piping Material 3rd MTO
AGP 4th MTO
EPN30040 | A/G Piping Material 4th MTO
Valve MTO
Valve 1st MTO
EPN40010 | Valve 1st MTO
Valve 2nd MTO
EPN40020 | Valve 2nd MTO
Safety Device MTO
Safety Device 1st MTO (Safety Valve / Rupture Disk)
EPN50010 | Safety Device MTO
Complete Parts MTO
Complete Parts 1st MTO (Expansion Joint)
EPN60010 | Complete Parts MTO 1st
Complete Parts 2st MTO (Others)
EPN60020 | Complete Parts MTO 2nd
Piping Support MTO
EPN70010 | Piping Support MTO
Fire Protection System Material MTO
EPN80010 | Fire Protection Material MTO
Instrumentation
Instrumentation Design Basis
Instrumentation Eng'g Standard
EK310010
Control System Basic Design
Control System Configuration Diagram
EK510010
Interlock / Sequence Logic Diagram
EK530010
Layout Plan of Control System in Control Room and Loading Data
EK540010
Power Supply and Grounding Diagram for Instrument System
EK550010
I/O List
I/O List for Inquiry
EK570010
Control System Specification
EK580020
Control System Detail Specification
EK590010
EK590020
Field Instrument Basic Design
Instrument Schedule List
Instrument Schedule List (IFA)
EK610020
Nozzle Elevation Plan for Level Instrument
EK620010
Field Instrument Specification
EK640010
EK640020
EK640030
EK640040
EK640050
EK640060
EK640070
EK640080
EK640090
EK910050
EK910060
Instrumentation Work Planning and Basic Design
Layout Plan of Instrument Main Cable way and Loading Data
EK720010
Control System Vendor Dwg Review
Control System Vendor Dwg Review
EK910010
EK910030
Field Instrument Vendor Dwg Review
Field Instrument Vendor Dwg Review
EKA10010
EKA10020
EKA10030
EKA10040
EKA10050
EKA10060
EKA10070
EKA10080
EKA10090
EKA10100
EKA10110
Construction Specification / Procedure
Instrumentation Construction Specification / Procedure
EKC10010
Instrumentation Work Test Procedure
EKC20010
Instrumentation Work Design
Control Equipment Layout in Control Room
EKD31010
EKD3A020
EKD3B040
Layout of Instrument U/G Conduit
EKD60010
Instrument Main Cable Way Layout
EKD71010
EKD72020
EKD7A030
EKD7B040
Layout of Instrument Wiring
EKD81010
EKD82020
EKD8A030
EKD8B040
Layout of Instrument Piping
EKD91010
EKD92020
EKD9A030
EKD9B040
Instrument Wiring/Tubing Connection List
EKDA1010
EKDA2020
EKDAA030
EKDAB040
Instrument Wiring Hook-Up
EKDB1010
EKDB2020
EKDBA030
EKDBB040
Instrument Piping Hook-Up
EKDC1010
EKDC2020
EKDCA030
EKDCB040
Instrument Cable/Tube Schedule/Wiring Diagram
EKDE0010
Instrument Cable/Tube Drum Schedule
EKDF0010
Instrument Construction Material Vendor Dwg Review
Vendor Dwg Review
EKE10010
EKE10020
3D Modeling Work
3D Modeling Work for Instr. Cable Tray
3D Modeling for Instr. Cable Tray for 2nd Review
EKK20010
3D Model Review Follow-up for Instr. Cable Tray
EKK20020
3D Modeling Work for Field Panel and JB
3D Modeling for Field Panel and JB for 2nd Review
EKK30010
3D Model Review Follow-up for Field Panel and JB
EKK30020
3D Modeling Work for Stanchion Instrument
3D Modeling for Stanchion Instrument for 2nd Review
EKK40010
3D Model Review Follow-up for Stanchion Instrument
EKK40020
In-line Instrument Outline Data (RDB)
EKK50010
EKK50020
EKK50030
Purchase Spec. / Subcontract Spec.
Purchase Spec. (Control System/Computer System)
EKM20010
EKM20030
Purchase Spec. (Field Instrument)
EKM30010
EKM30020
EKM30030
EKM30040
EKM30050
EKM30060
EKM30070
EKM30080
EKM30090
EKM50030
EKM50040
Subcontract Spec.
EKM50010
EKM50020
Instrumentation Construction Material MTO
Instrument Installation Material MTO
EKN10010
EKN10020
EKN10030
EKN10040
EKN10050
Electrical
Electrical Design Basis
Electrical Eng'g Standard
EE310010
Electrical Basic Design
Electrical Load Summary
Electrical Load Summary for Electrical Equip. Inquiry
EE410010
Electrical Load Summary for Electrical Equip. PO (IFA)
EE410020
Electrical Load Summary for Electrical Equip. Fabrication
EE410030
One Line Diagram
One Line Diagram for Electrical Equip. Inquiry
EE420010
One Line Diagram for Electrical Equip. PO (IFA)
EE420020
One Line Diagram for Electrical Equip. Fabrication
EE420030
Calculation of Electrical Basic Design
EE430010
Operation Mode List
EE450010
Electrical Equipment Basic Design
Motor List / Motor Data Sheet
EE510010
Reference Motor Drawing
EE530010
Electrical System Basic Design
Communication System Basic Design
EE610010
EE610020
Electrical Work Planning
Electrical Standard for Construction Design
EE710010
Electrical Main Cable Route Plan
EE730010
Electrical Main Cable Route L/D
EE740010
EE740020
Electrical Cable Trench Plan
EE750010
Electrical BOQ for Civil and Architecture Work
EE760010
EE761010
EE762010
EE76A010
EE76B010
EE76B020
Electrical Heat Loss List for HVAC
EE770010
Earthing & Lightning Protection Plan
EE780010
Lighting Plan
EE790010
Electrical Equip. Vendor Dwg Review
Outline Dwg
EE910010
EE910020
Electrical Equip. Vendor Dwg Review
EE9X0010
EE9X0020
EE9X0040
EE9X0050
EE9X0060
EE9X0070
EE9X0080
EE9X0090
EE9X0100
EE9X0110
EE9X0120
EE9X0130
EE9X0140
Information for Other Group
LD for Civil Structural Calculation
EED11010
EED11020
EED11030
EED12010
EED1A010
EED1A020
EED1A030
EED1A040
EED1A050
EED1A060
EED1A070
EED1A080
EED1B010
EED1B020
EED1B030
Electrical Const. Material Vendor Dwg Review
Electrical Const. Material Vendor Dwg Review
EEAX0010
EEAX0020
EEAX0030
EEAX0040
Electrical Work Design
U/G Conduit / Duct Bank / Trench Layout
EEC10010
Electrical Cable Tray Layout
EE910030
EEC21005
EEC21010
EEC22010
EEC22020
EEC2A025
EEC2A030
EEC2B035
EEC2B040
Substation Equipment Layout and L/D
EE720010
EE720020
Power & Control Wiring Layout
EEC51010
EEC52020
EEC5A030
EEC5B040
Lighting Wiring Layout
EEC61010
EEC62020
EEC6A030
EEC6B040
Earthing & Lightning Protection Wiring Layout
EEC71010
EEC71020
EEC72020
EEC72030
EEC7A030
EEC7A040
EEC7B040
EEC7B050
Communication System Wiring Layout
EEC81010
EEC82020
EEC8A030
EEC8B040
Fire Alarm System Wiring Layout
EEC91010
EEC92020
EEC9A030
EEC9B040
Heat Trace Layout
EECB1010
EECB2020
EECBA030
EECBB040
Electrical Cable Schedule
EECC0010
Electrical Cable Drum Schedule
Cable Drum Schedule for Fabrication
EECD0010
EECD10
EECD20
EECD30
Electrical Terminal Connection Diagram
EECF0010
3D Modeling Work
EEK00020
3D Modeling Work for Electrical Cable Tray
3D Modeling for Electrical Cable Tray
EEK30010
3D Modeling Work for Lighting
3D Modeling for Lighting
EEK40010
Electrical Purchase Specification
Purchase Spec.
EEM10010
EEM10020
EEM10040
EEM10050
EEM10060
EEM10070
EEM10080
EEM10090
EEM10100
EEM10105
EEM10110
EEM10120
EEM10130
EEM10140
EEM10150
Electrical Construction Material MTO
Electrical Construction Material MTO
EEN10010
EEN10020
EEN10025
EEN10030
EEN10031
EEN10040
EEN10050
Civil & Architecture
Civil Design Basis
Civil Engineering Standard
EC310010
Soil / Topo Survey & Site Preparation
Site Preparation Design
EC520010
Foundation Plan & Piling Design
Civil Standard Dwg
EC610010
Foundation Plan
EC630010
Pipe Rack Basic Design
Design Guide for Pipe Rack & Pre Calculation
EC731010
EC731020
EC731030
EC732020
EC732030
EC732040
EC732050
EC73B040
EC73B042
EC73B043
Structure Basic Design
Design Guide for Structure & Pre Calculation
EC831010
EC832020
Equip. Foundation Basic Design
Design Guide for Equip. Foundation & Pre Calculation
EC921010
EC922020
EC92A030
EC92B040
Trench, Drainage, etc. Basic Design
Drainage Plan
ECA20010
Road & Paving Plan
ECA30010
Building Basic Design
Planning Dwg for Building
ECB21010
ECB21020
ECB21030
ECB21040
ECB21050
ECB21060
ECB22010
ECB22020
ECB22030
ECB2A010
ECB2A020
ECB2A030
ECB2A040
ECB2A050
ECB2A060
ECB2A070
ECB2A080
ECB2A090
ECB2A100
ECB2A110
ECB2A120
ECB2A130
ECB2A140
ECB2A150
ECB2A160
ECB2B120
ECB2B140
ECB2B150
ECB2B160
ECB2B170
ECB2B180
ECB2B190
Pipe Rack Detail Design
Structural Calculation for Pipe Rack
ECC21010
ECC21015
ECC21020
ECC21025
ECC21030
ECC21035
ECC22010
ECC22020
ECC22030
ECC22040
ECC22050
ECC22060
ECC22070
ECC22080
ECC2A020
ECC2A030
ECC2A050
ECC2A060
ECC2A070
ECC2A080
ECC2A090
ECC2A100
ECC2A110
ECC2A120
ECC2A130
ECC2A140
ECC2A150
ECC2A160
ECC2A170
ECC2B070
ECC2B080
ECC2B090
ECC2B100
ECC2B110
ECC2B120
Foundation Dwg for Pipe Rack
ECC31010
ECC31020
ECC31050
ECC31060
ECC31090
ECC31100
ECC32010
ECC32020
ECC32030
ECC32040
ECC32050
ECC32060
ECC32070
ECC32080
ECC3A050
ECC3A060
ECC3A070
ECC3A080
ECC3A090
ECC3A100
ECC3A110
ECC3A120
ECC3A130
ECC3A140
ECC3B070
ECC3B080
ECC3B090
ECC3B100
ECC3B110
ECC3B120
Framing Plan & Elevation for Pipe Rack
ECC41010
ECC41020
ECC41030
ECC41040
ECC41050
ECC41060
ECC42040
ECC42050
ECC42060
ECC42070
ECC42080
ECC42090
ECC4A050
ECC4A060
ECC4A070
ECC4A080
ECC4A090
ECC4B070
ECC4B080
ECC4B090
Pipe Rack Detail Dwg
ECC51010
ECC51020
ECC51030
ECC52010
ECC52020
ECC52030
ECC52040
ECC5A010
ECC5A020
ECC5A030
ECC5A040
ECC5A050
ECC5B010
ECC5B020
ECC5B030
RC Pipe Rack Detail Dwg
ECC71010
ECC71020
ECC71030
ECC72010
ECC72020
Structure Detail Design
Structural Calculation for Structure
ECD21010
ECD21020
ECD21030
ECD21040
ECD21050
ECD21060
ECD21070
ECD21080
ECD21090
ECD21100
ECD21110
ECD21120
ECD21130
ECD21140
ECD21150
ECD21160
ECD21165
ECD21170
ECD21180
ECD21190
ECD21200
ECD21210
ECD21220
ECD21230
ECD21240
ECD21250
ECD21260
ECD21270
ECD21280
ECD21290
ECD21300
ECD21310
ECD21320
ECD21330
ECD21340
ECD21350
ECD21360
ECD21370
ECD22010
ECD22020
ECD22030
ECD22040
ECD22050
ECD22060
ECD22070
ECD22080
ECD22090
ECD22100
ECD22110
ECD22120
ECD22140
ECD22150
ECD22160
ECD22170
ECD22180
ECD22190
ECD22200
ECD22210
ECD22220
ECD22240
ECD22250
ECD22260
ECD22270
ECD22280
ECD22290
ECD22300
ECD22310
ECD22320
ECD22330
ECD22340
ECD22350
ECD22360
ECD22370
ECD22380
ECD22390
ECD22400
ECD22410
ECD2A010
ECD2A020
ECD2A030
ECD2A040
ECD2A050
ECD2A060
ECD2A070
ECD2A080
ECD2A090
ECD2A100
ECD2A110
ECD2A120
ECD2A130
ECD2A140
ECD2A150
ECD2A160
ECD2A170
ECD2A180
ECD2B010
ECD2B020
ECD2B030
ECD2B040
ECD2B050
ECD2B060
ECD2B070
ECD2B080
Foundation Dwg for Structure
ECD31010
ECD31015
ECD31020
ECD31025
ECD31030
ECD31035
ECD31040
ECD31045
ECD31050
ECD31055
ECD31060
ECD31065
ECD31070
ECD31075
ECD31080
ECD31085
ECD31090
ECD31095
ECD31100
ECD31105
ECD31110
ECD31115
ECD31120
ECD31125
ECD31130
ECD31135
ECD31140
ECD31145
ECD31150
ECD31155
ECD31160
ECD31165
ECD31170
ECD31175
ECD32010
ECD32015
ECD32020
ECD32025
ECD32030
ECD32035
ECD32040
ECD32045
ECD32050
ECD32055
ECD32060
ECD32065
ECD32070
ECD32075
ECD32080
ECD32085
ECD32090
ECD32095
ECD32100
ECD32105
ECD32110
ECD32115
ECD32120
ECD32125
ECD32130
ECD32135
ECD32140
ECD32145
ECD3A010
ECD3A015
ECD3A020
ECD3A025
ECD3A030
ECD3A035
ECD3A040
ECD3A045
ECD3A050
ECD3A055
ECD3A060
ECD3A065
ECD3A070
ECD3A075
ECD3A080
ECD3A085
ECD3A090
ECD3A095
ECD3B010
ECD3B015
ECD3B020
ECD3B025
ECD3B030
ECD3B035
ECD3B040
ECD3B045
Framing Plan & Elevation for Structure
ECD41010
ECD41020
ECD41030
ECD41040
ECD41050
ECD41060
ECD41070
ECD41080
ECD42050
ECD42060
ECD42070
ECD42080
ECD42090
ECD42100
ECD42110
ECD42120
ECD42130
ECD42140
ECD42150
ECD42160
ECD42170
ECD42180
ECD42190
Steel Structure Detail Dwg
ECD51010
ECD51020
ECD51030
ECD51040
ECD51050
ECD51060
ECD51070
ECD51080
ECD52010
ECD52020
ECD52030
ECD52040
ECD52050
ECD52060
ECD52070
ECD52080
ECD52090
ECD52100
ECD52110
ECD52120
ECD52130
ECD52160
ECD52170
ECD5A010
ECD5A020
ECD5A030
ECD5A040
ECD5A050
ECD5A060
ECD5A070
ECD5A080
ECD5A090
ECD5B010
ECD5B020
ECD5B030
ECD5B040
Equip. Foundation Detail Design
Structural Calculation for Equip. Foundation
ECE21010
ECE22020
ECE2A030
ECE2B040
Foundation Dwg for Equip. Foundation
ECE31010
ECE32020
ECE3A030
ECE3B040
Trench, Drainage, etc. Detail Design
Cable Trench & Duct Bank Dwg
ECF10010
Pipe Trench & Valve Pit Dwg
ECF20010
Drainage Dwg
ECF30010
Miscellaneous Foundation Dwg (include Piping & Cable Support)
ECF50010
Road & Pavement Drawing
ECF60010
Fence & Gate Dwg
ECF80010
Land Scaping Dwg
ECF90010
Concrete Basin Dwg
ECFAA010
ECFAA020
Building Detail Design
Structural Calculation for Building
ECG21000
ECG21010
ECG21015
ECG21020
ECG21025
ECG21030
ECG21035
ECG21040
ECG21045
ECG21050
ECG21055
ECG21060
ECG21065
ECG21070
ECG21075
ECG21080
ECG21085
ECG22010
ECG22020
ECG22030
ECG22040
ECG22050
ECG22060
ECG22070
ECG22080
ECG22090
ECG22100
ECG22110
ECG2A050
ECG2A080
ECG2A090
ECG2A100
ECG2A120
ECG2A130
ECG2A140
ECG2A150
ECG2A160
ECG2A170
ECG2A190
ECG2A200
ECG2A210
ECG2A220
ECG2A230
ECG2A240
ECG2A250
ECG2A260
ECG2A270
ECG2A280
ECG2A290
ECG2A300
ECG2A310
ECG2A320
ECG2A330
ECG2A340
ECG2A350
ECG2A360
ECG2A380
ECG2A390
ECG2A400
ECG2A410
ECG2A420
ECG2A430
ECG2A440
ECG2A450
ECG2A460
ECG2A470
ECG2A480
ECG2A490
ECG2A500
ECG2A510
ECG2A520
ECG2A530
ECG2A540
ECG2A550
ECG2A560
ECG2A570
ECG2A580
ECG2A590
ECG2A600
ECG2A610
ECG2A620
ECG2A630
ECG2A640
ECG2A650
ECG2A660
ECG2B010
ECG2B020
ECG2B040
ECG2B050
ECG2B060
ECG2B080
ECG2B100
ECG2B110
ECG2B120
ECG2B130
ECG2B134
ECG2B135
ECG2B140
ECG2B150
ECG2B160
ECG2B170
ECG2B180
ECG2B190
ECG2B200
ECG2B210
Foundation Dwg
ECG31010
ECG31020
ECG31030
ECG31040
ECG31050
ECG31060
ECG31070
ECG32040
ECG32050
ECG32060
ECG32070
ECG32080
ECG32090
ECG3A050
ECG3A060
ECG3A070
ECG3A080
ECG3A090
ECG3A100
ECG3A110
ECG3A120
ECG3A130
ECG3A140
ECG3A150
ECG3A160
ECG3A170
ECG3A180
ECG3A210
ECG3A220
ECG3A230
ECG3A240
ECG3A250
ECG3A260
ECG3A270
ECG3A280
ECG3A310
ECG3A320
ECG3A330
ECG3A340
ECG3A350
ECG3A360
ECG3A370
ECG3A380
ECG3A390
ECG3A400
ECG3A410
ECG3B020
ECG3B030
ECG3B040
ECG3B050
ECG3B060
ECG3B070
ECG3B080
ECG3B090
ECG3B100
ECG3B110
ECG3B120
ECG3B130
ECG3B140
ECG91250
ECG91260
ECG91570
Building Structural Dwg
ECG41000
ECG41010
ECG41020
ECG41030
ECG41040
ECG41050
ECG41060
ECG41070
ECG41080
ECG41090
ECG41100
ECG41110
ECG41120
ECG42040
ECG42050
ECG42060
ECG42070
ECG42080
ECG42090
ECG42100
ECG42110
ECG4A010
ECG4A020
ECG4A030
ECG4A040
ECG4A050
ECG4A060
ECG4A110
ECG4A120
ECG4A150
ECG4A160
ECG4A170
ECG4A180
ECG4A190
ECG4A200
ECG4A210
ECG4A220
ECG4A230
ECG4A240
ECG4A310
ECG4A320
ECG4A330
ECG4A340
ECG4A380
ECG4A390
ECG4A400
ECG4A410
ECG4A420
ECG4A430
ECG4A440
ECG4B130
ECG4B135
ECG4B140
ECG4B150
ECG4B160
ECG4B170
ECG4B190
ECG4B200
ECG4B210
ECG4B220
ECG4B230
ECG4B240
ECG4B260
ECG4B270
ECG4B280
ECG4B290
Building Architectural Dwg
ECG61020
ECG61030
ECG61040
ECG61050
ECG62010
ECG62020
ECG62030
ECG62040
ECG6A050
ECG6A060
ECG6A080
ECG6A090
ECG6A110
ECG6A120
ECG6A130
ECG6A140
ECG6A150
ECG6A170
ECG6A180
ECG6A210
ECG6A220
ECG6A240
ECG6A250
ECG6A260
ECG6B130
ECG6B150
ECG6B160
ECG6B170
ECG6B200
ECG6B210
HVAC Calculation
ECG81010
ECG81020
ECG81030
ECG81040
ECG82010
ECG82020
ECG8A010
ECG8A020
ECG8A030
ECG8A040
ECG8A050
ECG8A060
ECG8A110
ECG8A120
ECG8A130
ECG8A140
ECG8A150
ECG8A160
ECG8A170
ECG8B010
ECG8B020
ECG8B030
ECG8B040
ECG8B050
ECG8B060
HVAC Dwg
ECG91010
ECG9A050
ECG9B080
ECG9B100
3D Modeling Work
3D Modeling Work for Foundation
3D Modeling for Foundation (Step-1)
ECK20010
3D Update for Foundation (Step-2)
ECK20020
3D Update for Foundation (Step-3)
ECK20030
3D Modeling Work for Drainage
3D Modeling for Drainage (Step-1)
ECK30010
3D Update for Drainage (Step-2)
ECK30020
3D Modeling Work for Ductbank
3D Modeling for Ductbank (Step-1)
ECK40010
3D Update for Ductbank (Step-3)
ECK40020
3D Modeling Work for Steel Structure & Concrete Structure
3D Modeling for Structure (Step-1)
ECK50010
3D Update for Structure (Step-2)
ECK50020
3D Update for Structure (Step-4)
ECK50030
3D Modeling Work for Paving
3D Modeling for Paving (Step-1)
ECK90010
3D Update for Paving (Step-2)
ECK90020
Construction Planning & Subcontract
Construction Basic Planning
Construction Plan
ES310010
Construction Schedule
Construction Schedule
ES340010
Detailed Construction Schedule
ES340020
Construction Manpower & Equipment Plan
ES350010
Construction Specification
Spec. for Installation Work
ES510010
Spec. for Piping Work
ES520010
Spec. for Thermal Insulation
ES530010
Spec. for Painting
ES540010
Construction Planning
Material Control Plan at Site
ES620010
Heavy Equipment Installation Plan
ES630010
Flushing Plan
ES640010
Temporary Facility Plan & Fixtures List
ES650010
Construction Procedure / Subcontractor's Document Review
Material Control Procedure at Site
ES710010
Procedure for Equipment Installation
ES720010
Procedure for Piping Work
ES730010
Procedure for Thermal Insulation Work
ES740010
Procedure for Painting
ES750010
Construction BOQ / MPPL
Material List for Thermal Insulation
ESH30010
Material List for Painting
ESH40010
Purchase Spec. / Subcontract Spec.
Subcontract Specification
ESM20010
ESM20020
ESM20030
ESM20040
ESM20050
ESM20060
PROCUREMENT
Stationary Equipment Procurement
Reactor
Reactor Inquiry/PO
PV11110
PV11120
PV11130
PV11140
PV11141
PV11210
Reactor Fabrication
PV12110
PV12120
PV12130
PV12140
PV12210
PV12220
PV32210
Reactor Transportation
PV13110
PV13111
PV13119
PV13120
PV13130
PV13131
PV13140
PV13141
PV13210
PV13211
PV13220
PV13221
PV33210
PV33211
Tower / Column
Tower / Column Inquiry/PO
PV21110
PV21120
Tower / Column Fabrication
PV22110
PV22120
PV22240
Tower / Column Transportation
PV23110
PV23111
PV23120
PV23121
PV23122
PV23240
PV23241
Vessel / Drum
Vessel / Drum Inquiry/PO
PV31110
PV31120
PV31140
PV31150
Vessel / Drum Fabrication
PV32110
PV32120
PV32140
PV32150
PV32240
PV32250
PV32A00
PV32A10
Vessel / Drum Transportation
PV33110
PV33111
PV33112
PV33120
PV33121
PV33140
PV33141
PV33142
PV33150
PV33240
PV33241
PV33242
PV33250
PV33251
PV33252
PV33A00
PV33A10
PV33A11
Waste Heat Boiler
Waste Heat Boiler Inquiry/PO
PV41100
Waste Heat Boiler Fabrication
PV42100
Waste Heat Boiler Transportation
PV43100
PV43110
S&T Heat Exchanger
S&T Heat Exchanger Inquiry/PO
PV51120
PV51130
PV51135
PV51140
PV51150
PV51210
PV51220
PV51230
S&T Heat Exchanger Fabrication
PV52120
PV52130
PV52135
PV52140
PV52150
PV52210
PV52220
PV52230
PV52240
PV52250
PV52260
PV52A00
S&T Heat Exchanger Transportation
PV53120
PV53121
PV53122
PV53130
PV53131
PV53134
PV53135
PV53137
PV53140
PV53141
PV53142
PV53150
PV53151
PV53152
PV53210
PV53211
PV53220
PV53221
PV53230
PV53231
PV53232
PV53240
PV53250
PV53260
PV53A00
Other Heat Exchangers
Other Heat Exchangers Inquiry/PO
PV71100
PV71110
PV71230
Other Heat Exchangers Fabrication
PV72100
PV72110
PV72210
PV72220
PV72230
Other Heat Exchangers Transportation
PV73100
PV73110
PV73111
PV73210
PV73220
PV73221
PV73230
PV73231
PV73232
Shop Tank
Shop Tank Inquiry/PO
PVA1100
Shop Tank Fabrication
PVA2100
PVA2200
PVA2A00
Shop Tank Transportation
PVA3100
PVA3200
PVA3A00
K.D. Tank
K.D. Tank Inquiry/PO
PVB1100
PVB1B00
K.D. Tank Fabrication
PVB2100
PVB2200
PVB2A00
PVB2B00
PVB3220
K.D. Tank Transportation
PVB3100
PVB3200
PVB3230
PVB3A00
PVB3B00
Filter
Filter Inquiry/PO
PVD1100
PVD1110
Filter Fabrication
PVD2100
PVD2110
PVD2210
PVD2A00
Filter Transportation
PVD3100
PVD3110
PVD3210
PVD3A00
Mixer / Silencer / Ejector
Mixer / Silencer / Ejector Inquiry/PO
PVE1100
PVE1210
PVE1230
PVE1240
Mixer / Silencer / Ejector Fabrication
PVE2100
PVE2210
PVE2220
PVE2230
PVE2240
PVE2A00
Mixer / Silencer / Ejector Transportation
PVE3100
PVE3210
PVE3220
PVE3230
PVE3240
PVE3A00
Tower Internal & Other Internal
Tower Internal & Other Internal Inquiry/PO
PVI1010
PVI1020
PVI1030
Tower Internal & Other Internal Fabrication
PVI2010
PVI2020
PVI2030
Tower Internal & Other Internal Transportation
PVI3010
PVI3020
PVI3030
Other Equipment
Other Equipment Inquiry/PO
PVF1210
PVF1220
PVF1230
Other Equipment Fabrication
PVF2210
PVF2220
PVF2230
Other Equipment Transportation
PVF3210
PVF3220
PVF3230
PVF3231
Platform & Ladder
Platform & Ladder Inquiry/PO
PVP1000
Platform & Ladder Fabrication
PVP2000
Platform & Ladder Transportation
PVP3000
Furnace Procurement
Primary Reformer
Primary Reformer Inquiry/PO
PU11100
Primary Reformer Fabrication
PU12110
PU12120
PU12130
PU12140
PU12150
PU12160
PU12170
PU12180
PU12190
PU12191
PU121A0
Primary Reformer Transportation
PU13110
PU13111
PU13112
PU13120
PU13121
PU13125
PU13130
PU13135
PU13140
PU13145
PU13150
PU13155
PU13160
PU13165
PU13170
PU13175
PU13180
PU13185
PU13190
PU13191
PU131A0
Start-Up Heater
Start Up Heater Inquiry/PO
PU21100
Start Up Heater Fabrication
PU22100
Start Up Heater Transportation
PU23100
Auxiliary Boiler
Auxiliary Boiler Inquiry/PO
PU31A00
Auxiliary Boiler Fabrication
PU32A00
Auxiliary Boiler Transportation
PU33A00
PU33A01
Flare
Flare Inquiry/PO
PU61200
Flare Fabrication
PU62200
PU62A00
Flare Transportation
PU63200
PU63201
PU63A00
PU63A01
Machinery Procurement
Centrifugal Pump (Heavy Duty)
Centrifugal Pump (Heavy Duty) Inquiry/PO
PM11110
PM11120
PM11130
PM11210
PM11A10
Centrifugal Pump (Heavy Duty) Fabrication
PM12111
PM12112
PM12121
PM12122
PM12131
PM12132
PM12211
PM12212
PM12221
PM12231
PM12A11
PM12A12
Centrifugal Pump (Heavy Duty) Transportation
PM13108
PM13110
PM13120
PM13125
PM13130
PM13210
PM13211
PM13A10
PM13A15
Centrifugal Pump (Middle & Light Duty)
Centrifugal Pump (Middle & Light Duty) Inquiry/PO
PM21120
PM21130
PM21140
PM21A00
Centrifugal Pump (Middle & Light Duty) Fabrication
PM22130
PM22140
PM22215
PM22216
PM22225
PM22226
PM22A10
PM22A20
PM22B10
PM22B20
Centrifugal Pump (Middle & Light Duty) Transportation
PM23120
PM23215
PM23225
PM23A00
PM23B00
Centrifugal Pump (Fire Water Pump)
Centrifugal Pump (Fire Water Pump) Inquiry/PO
PM31A00
Centrifugal Pump (Fire Water Pump) Fabrication
PM32A00
Centrifugal Pump (Fire Water Pump) Transportation
PM33A00
Reciprocating Pump
Reciprocating Pump Inquiry/PO
PM41000
Reciprocating Pump Fabrication
PM42000
Reciprocating Pump Transportation
PM43000
Other Pump
Other Pump Inquiry/PO
PM51110
PM51120
Other Pump Fabrication
PM52110
PM52120
PM52130
Other Pump Transportation
PM53110
PM53120
Centrifugal Compressor
Centrifugal Compressor Inquiry/PO
PM61110
Centrifugal Compressor Fabrication
PM62110
PM62120
PM62130
PM62140
PM62210
Centrifugal Compressor Transportation
PM63110
PM63111
PM63120
PM63121
PM63130
PM63131
PM63140
PM63141
PM63210
PM63211
Reciprocating Compressor
Reciprocating Compressor Inquiry/PO
PM81100
PM81200
Reciprocating Compressor Fabrication
PM82100
PM82200
Reciprocating Compressor Transportation
PM83100
PM83200
Fan / Blower
Fan / Blower Inquiry/PO
PM91110
PM91120
PM91210
Fan / Blower Fabrication
PM92110
PM92120
PM92210
Fan / Blower Transportation
PM93110
PM93115
PM93120
PM93210
PM93220
Instrument Air Compressor & Dryer
Instrument Air Compressor & Dryer Inquiry/PO
PMA1A00
Instrument Air Compressor & Dryer Fabrication
PMA2A00
Instrument Air Compressor & Dryer Transportation
PMA3A00
Steam Turbine
Steam Turbine Inquiry/PO
PMC1A00
Steam Turbine Fabrication
PMC2A00
Steam Turbine Transportation
PMC3A00
Emergency Diesel Engine Generator
Emergency Diesel Engine Generator Inquiry/PO
PMH1A00
Emergency Diesel Engine Generator Fabrication
PMH2A00
Emergency Diesel Engine Generator Transportation
PMH3A00
Demineralized Water Treatment Unit
Demineralized Water Treatment Unit Inquiry/PO
PMU1A10
Demineralized Water Treatment Unit Fabrication
PMU1A20
Demineralized Water Treatment Unit Transportation
PMU1A28
PMU1A30
Other Water Treatment Unit
Other Water Treatment Unit Inquiry/PO
PMU3B10
Other Water Treatment Unit Fabrication
PMU3B20
Other Water Treatment Unit Transportation
PMU3B30
Waste Water Treatment Unit
Waste Water Treatment Unit Inquiry/PO
PMU4A10
Waste Water Treatment Unit Fabrication
PMU4A20
Waste Water Treatment Unit Transportation
PMU4A30
Hydrogen Recoery Unit
Hydrogen Recoery Unit Inquiry/PO
PMU9112
Hydrogen Recoery Unit Fabrication
PMU9122
Hydrogen Recoery Unit Transportation
PMU9132
Cooling Tower
Cooling Tower Inquiry/PO
PMUAA10
Cooling Tower Fabrication
PMUAA20
Cooling Tower Transportation
PMUAA30
Refrigeration Unit
Refrigeration Unit Inquiry/PO
PMUBB10
Refrigeration Unit Fabrication
PMUBB20
Refrigeration Unit Transportation
PMUBB30
Chemical Injection Unit
Chemical Injection Unit Inquiry/PO
PMUC010
Chemical Injection Unit Fabrication
PMUC020
Chemical Injection Unit Transportation
PMUC030
Crane & Hoist
Crane & Hoist Inquiry/PO
PMX1010
Crane & Hoist Fabrication
PMX1020
Crane & Hoist Transportation
PMX1030
Conveyor
Conveyor Inquiry/PO
PMX2210
Conveyor Fabrication
PMX2220
Conveyor Transportation
PMX2230
PMX2240
PMX8250
Granulator(Lower)
Granulator(Lower) Inquiry/PO
PMX3210
Granulator(Lower) Fabrication
PMX3220
Granulator(Lower) Transportation
PMX3230
PMX3231
Mixing Equipment
Mixing Equipment Inquiry/PO
PMX4210
PMX6210
PMX7110
PMX7210
Mixing Equipment Fabrication
PMX4220
PMX6220
PMX7120
PMX7220
Mixing Equipment Transportation
PMX4230
PMX6230
PMX7130
PMX7230
Scrubber
Scrubber Inquiry/PO
PMX8210
Scrubber Fabrication
PMX8220
Scrubber Transportation
PMX8230
PMX8231
Loading Arm
Loading Arm Inquiry/PO
PMXGB10
Loading Arm Fabrication
PMXGB20
Loading Arm Transportation
PMXGB30
Reclaimer
Reclaimer Inquiry/PO
PMXIB10
Reclaimer Fabrication
PMXIB20
Reclaimer Transportation
PMXIB30
PMXIB40
PMXIB50
Piping Material Procurement
U/G Piping Material
U/G Piping Material Inquiry/PO
PP11010
PP11020
PP11030
U/G Piping Material Fabrication
PP12010
PP12020
PP12030
U/G Piping Material Transportation
PP13010
PP13020
PP13030
A/G Piping Material (1st)
A/G Piping Material (1st) Inquiry/PO
PP31000
A/G Piping Material (1st) Fabrication
PP32000
A/G Piping Material (1st) Transportation
PP33000
A/G Piping Material (2nd)
A/G Piping Material (2nd) Inquiry/PO
PP51000
A/G Piping Material (2nd) Fabrication
PP52000
A/G Piping Material (2nd) Transportation
PP53000
A/G Piping Material (3rd)
A/G Piping Material (3rd) Inquiry/PO
PP61000
A/G Piping Material (3rd) Fabrication
PP62000
A/G Piping Material (3rd) Transportation
PP63000
A/G Piping Material (4th)
A/G Piping Material (4th) Inquiry/PO
PP63001
A/G Piping Material (4th) Fabrication
PP63002
A/G Piping Material (4th) Transportation
PP63003
Valve (1st)
Valve (1st) Inquiry/PO
PPA1000
PPA1010
Valve (1st) Fabrication
PPA2000
PPA2010
Valve (1st) Transportation
PPA3000
PPA3010
Valve (2nd)
Valve (2nd) Inquiry/PO
PPB1000
Valve (2nd) Fabrication
PPB2000
Valve (2nd) Transportation
PPB3000
Safety Device (1st)
Safety Device (1st) Inqury/PO
PPD1000
Safety Device (1st) Fabrication
PPD2000
Safety Device (1st) Transportation
PPD3000
Complete Parts (1st)
Complete Parts (1st) Inqury/PO
PPG1010
Complete Parts (1st) Fabrication
PPG2010
Complete Parts (1st) Transportation
PPG3010
Complete Parts (2nd)
Complete Parts (2nd) Inqury/PO
PPH1000
Complete Parts (2nd) Fabrication
PPH2000
Complete Parts (2nd) Transportation
PPH3000
Piping Support Material (1st)
Piping Support Material (1st) Inqury/PO
PPP1000
Piping Support Material (1st) Fabrication
PPP2000
Piping Support Material (1st) Transportation
PPP3000
Fire Protection Material (A/G)
Fire Protection Material (A/G) Inqury/PO
PPY1000
Fire Protection Material (A/G) Fabrication
PPY2000
Fire Protection Material (A/G) Transportation
PPY3000
Instrumentation Procurement
DCS
DCS Inquiry/PO
PK11010
DCS Fabrication
PK12011
PK12012
PK12013
PK12014
DCS Transportation
PK13010
Instrument Panel
Instrument Panel Inquiry/PO
PK11040
Instrument Panel Fabrication
PK12040
Instrument Panel Transportation
PK13040
Control Valve
Control Valve Inquiry/PO
PK21000
Control Valve Fabrication
PK22000
Control Valve Transportation
PK23000
Flow Instrument
Flow Instrument Inquiry/PO
PK31000
Flow Instrument Fabrication
PK32000
Flow Instrument Transportation
PK33000
Other Instrument
Other Insrument Inquiry/PO
PK51010
PK51020
PK51030
PK51035
PK51040
PK51045
PK51050
PK51060
PK51070
Other Insrument Fabrication
PK52010
PK52020
PK52030
PK52035
PK52040
PK52045
PK52050
PK52060
PK52070
Other Insrument Transportation
PK53010
PK53020
PK53030
PK53035
PK53040
PK53045
PK53050
PK53060
PK53070
Instrument U/G Material
Instrument U/G Material Inquiry/PO
PK71000
Instrument U/G Material Fabrication
PK72000
Instrument U/G Material Transportation
PK73000
Instrument Cable Tray/Duct
Instrument Cable Tray/Duct Inquiry/PO
PK81000
Instrument Cable Tray/Duct Fabrication
PK82000
Instrument Cable Tray/Duct Transportation
PK83000
Instrument Cable
Instrument Cable Inquiry/PO
PK91000
Instrument Cable Fabrication
PK92000
Instrument Cable Transportation
PK93000
Instrument Other Construction Material
Instrument Other Contruction Material Inquiry/PO
PKA1010
PKA1020
PKA1030
Instrument Other Contruction Material Fabrication
PKA2010
PKA2020
PKA2030
Instrument Other Contruction Material Transportation
PKA3010
PKA3020
PKA3030
Electrical Equipment & Material Procurement
Motor
Motor Inquiry/PO
PE11010
PE11020
Motor Fabrication
PE12011
PE12012
PE12021
PE12022
Motor Transportation
PE13011
PE13012
PE13013
PE13021
PE13022
PE13023
Distribution Transformer
Distribution Transformer Inquiry/PO
PE31040
Distribution Transformer Fabrication
PE32040
Distribution Transformer Transportation
PE33041
HV SWGR & MCC
HV SWGR & MCC Inquiry/PO
PE31060
HV SWGR & MCC Fabrication
PE32060
HV SWGR & MCC Transportation
PE33061
LV SWGR & MCC
LV SWGR & MCC Inquiry/PO
PE31070
LV SWGR & MCC Fabrication
PE32070
LV SWGR & MCC Transportation
PE33071
Capacitor
Capacitor Inquiry/PO
PE31080
Capacitor Fabrication
PE32080
Capacitor Transportation
PE33080
Busduct
Bus Duct Inquiry/PO
PE31090
Bus Duct Fabrication
PE32090
Bus Duct Transportation
PE33090
UPS/DC
UPS/DC Inquiry/PO
PE310A0
UPS/DC Fabrication
PE320A0
UPS/DC Transportation
PE330A0
Communication & Fire Alarm
Communication & Fire Alarm System Inquiry/PO
PE310B0
PE310C0
Communication & Fire Alarm System Fabrication
PE320B0
PE320C0
Communication & Fire Alarm System Transportation
PE330B0
PE330C0
PE330C1
Cathodic Protection
Cathodic Protection Inquiry/PO
PE310D1
Cathodic Protection Fabrication
PE320D1
Cathodic Protection Transportation
PE330D1
Other Electrical Equipment
Other Electrical Equipment Inquiry/PO
PE310D2
PE310D9
Other Electrical Equipment Fabrication
PE320D2
PE320D9
Other Electrical Equipment Transportation
PE330D2
PE330D9
Electrical U/G Construction Material
Electrical U/G Construction Material Inquiry/PO
PEG1000
Electrical U/G Construction Material Fabrication
PEG2000
Electrical U/G Construction Material Transportation
PEG3000
Electrical Cable Tray
Electrical Cable Tray Inquiry/PO
PEK1000
Electrical Cable Tray Fabrication
PEK2000
Electrical Cable Tray Transportation
PEK3000
PEK3010
Electrical Cable
Electrical Cable Inquiry/PO
PEH1000
Electrical Cable Fabrication
PEH2000
PEH3010
PEH3030
PEH3050
Electrical Cable Transportation
PEH3000
PEH3020
PEH3040
PEH3060
Lighting Fixture
Lighting Fixture Inquiry/PO
PEI1010
Lighting Fixture Fabrication
PEI2010
PEI3100
Lighting Fixture Transportation
PEI3010
PEI3110
Lighting Panel
Lighting Panel Inquiry/PO
PEI1020
Lighting Panel Fabrication
PEI2020
Lighting Panel Transportation
PEI3020
Ex-Proof Material
Ex-Proof Material Inquiry/PO
PEI1030
Ex-Proof Material Fabrication
PEI2030
Ex-Proof Material Transportation
PEI3030
Electrical Other Construction Material
Electrical Other Construction Material Inquiry/PO
PEI1090
Electrical Other Construction Material Fabrication
PEI2090
Electrical Other Construction Material Transportation
PEI3090
Civil & Building Procurement
Pipe Rack
Pipe Rack Material Fabrication
PC22010
PC22020
PC22030
PC22040
PC22050
PC22060
PC22070
PC22080
PC22090
PC22100
PC22110
PC22120
PC22130
PC22140
PC22150
Steel Structure
Steel Structure Material Inquiry/PO
PC31000
Steel Structure Material Fabrication
PC32010
PC32020
PC32030
PC32050
PC32060
PC32070
PC32080
PC32090
PC32100
PC32110
PC32120
PC32130
PC32140
PC32150
PC32160
PC32170
PC32180
PC32190
PC32210
PC32220
PC32230
PC32240
PC32250
PC32260
PC32270
PC32280
HVAC
HVAC Inquiry/PO Inquiry/PO
PCH1011
PCH1021
PCH1031
PCH1041
PCH1051
PCH1061
PCH1071
PCH1081
PCH1091
PCH1101
HVAC Fabrication
PCH2012
PCH2022
PCH2032
PCH2042
PCH2052
PCH2062
PCH2072
PCH2082
PCH2092
PCH2102
PCH2112
PCH2132
PCH2152
PCH2162
PCH2172
PCH2182
PCH2192
PCH2202
PCH2212
PCH2222
PCH2232
PCH2242
PCH2252
HVAC Transportation
PCH3013
PCH3023
PCH3033
PCH3043
PCH3053
PCH3063
PCH3073
PCH3083
PCH3093
PCH3103
Subcontracting
Steel Work Subcontract
PCS3010
PCS3020
PCS3030
PCS3040
PCS3050
PCS3070
PCS3080
PCS3090
PCS3100
PCS3130
PCS3140
PCS3150
PCS3160
PCS3170
PCS3180
Insulation & Painting Material Procurement
Insulation Material Inquiry/PO
PSIS011
Insulation Material Fabrication
PSIS012
Insulation Material Transportation
PSIS013
Painting Material Inquiry/PO
PSPT011
Painting Material Fabrication
PSPT012
Painting Material Transportation
PSPT013
Catalyst, Chemical & Laboratory Procurement
Catalist & Chemical
Catalist & Chemical Inquiry/PO
PBCA0T1
PBCH0M1
Catalist & Chemical Fabrication
PBCA0T2
PBCH0M2
Catalist & Chemical Transportation
PBCA0T3
PBCH0M3
Laboratory Equipment
Laboratory Equipment Inquiry/PO
PBLA0B1
Laboratory Equipment Fabrication
PBLA0B2
Laboratory Equipment Transportation
PBLA0B3
Construction Work Subcontracting
Heavy Lift Work Subcontract
PSS20H0
Installation Work Subcontract
PSS302I
Piping Work Subcontract
PSS40P0
Thermal Insulation Work Subcontract
PSS50I0
Painting Work Subcontract
PSS60P0
Temporary Facility
PSS10T0
Delivery Milestone
Steel Structure & Pipe Rack Material
Steel Structure & Pipe Rack Material Delivery at Site
CC1001D
CC1002D
CC1003D
CC1004D
CC1005D
CC1006D
CC1007D
CC1008D
CC1009D
CC1010D
CC1011D
CC1012D
CC1013D
CC1014D
CC1015D
CC2011D
CC2012D
CC2013D
CC2021D
CC2022D
CC2023D
CC2024D
CC2025D
CC2026D
CC2027D
CC2028D
CC2029D
CC2030D
CC2031D
CC2032D
CC2033D
CC2034D
CC2035D
CC2036D
CC2037D
CC2038D
CC2039D
CC2040D
CC2041D
CC2042D
CC2043D
Steel Structure & Pipe Rack Material Required at Site
CC1001R
CC1002R
CC1003R
CC1004R
CC1005R
CC1006R
CC1007R
CC1008R
CC1009R
CC1010R
CC1011R
CC1012R
CC1013R
CC1014R
CC1015R
CC2011R
CC2012R
CC2013R
CC2021R
CC2022R
CC2023R
CC2024R
CC2025R
CC2026R
CC2027R
CC2028R
CC2029R
CC2030R
CC2031R
CC2032R
CC2033R
CC2034R
CC2035R
CC2036R
CC2037R
CC2038R
CC2039R
CC2040R
CC2041R
CC2042R
CC2043R
Building Facility
Building Facility Delivery at Site
CC4001D
CC4002D
CC4003D
CC4004D
CC4005D
CC4006D
CC4007D
CC4008D
CC4009D
CC4010D
CC4011D
CC4012D
CC4013D
CC4014D
CC4015D
CC4016D
CC4017D
CC4018D
CC4019D
CC4020D
CC4021D
CC4022D
CC4023D
CC4101D
CC4103D
CC4104D
CC4105D
CC4106D
CC4107D
CC4108D
CC4109D
CC4110D
CC4111D
CC4112D
CC4113D
CC4114D
CC4115D
CC4116D
Building Facility Required at Site
CC1404R
CC4001R
CC4002R
CC4003R
CC4004R
CC4005R
CC4006R
CC4007R
CC4008R
CC4009R
CC4010R
CC4011R
CC4012R
CC4013R
CC4014R
CC4015R
CC4016R
CC4017R
CC4018R
CC4019R
CC4020R
CC4021R
CC4022R
CC4023R
CC4101R
CC4103R
CC4105R
CC4106R
CC4107R
CC4108R
CC4109R
CC4110R
CC4111R
CC4112R
CC4113R
CC4114R
CC4115R
CC4116R
Equipment & Machinery
Equipment & Machinery Delivery at Site
CM0111D
CM0112D
CM0113D
CM0212D
CM0403D
CM0513D
CM0514D
CM0611D
CM0612D
CM0613D
CM0614D
CM0615D
CM07A1D
CM07A3D
CM07A5D
CM0813D
CM0913D
CM0914D
CM09A1D
CM09A8D
CM0C01D
CM0GA0D
CM0HA0D
CM0IA0D
CM0JA1D
CM0KA0D
CM0U08D
CM0U1AD
CM0X17D
CM7121D
CM7320D
CM7330D
CM73B0D
CM7B20D
CM9120D
CMB120D
CMB121D
CMN1B0D
CMT1B0D
CMT1B1D
CMU7B0D
CMXZ2AD
CMXZ2BD
CMXZ2CD
CMXZ2YD
CMXZ2YD10
CV010VD
CV010WD
CV010YD
CV0111D
CV0112D
CV0113D
CV0114D
CV0115D
CV0116D
CV0118D
CV0119D
CV011AD
CV011BD
CV011ED
CV011FD
CV011GD
CV011HD
CV011HD10
CV011MD
CV011ND
CV011TD
CV011TD10
CV011UD
CV01A5D
CV01A7D
CV01ADD
CV01AFD
CV01AHD
CV03A0D
CV1121D
CV1122D
CV1422D
CV1521D
CV1524D
CV1721D
CV1722D
CV1723D
CV1725D
CV1727D
CV1A21D
CV1A21D10
CV1A23D
CV1D20D
CV1F20D
CV1G20D
CV1H20D
CV1J20D
CV1K20D
CV1O21D
CV1O22D
CV1O23D
CV3020D
CV3025D
CV30B0D
Equipment & Machinery Required at Site
CB0100R
CB0200R
CM0111R
CM0112R
CM0113R
CM0212R
CM0403R
CM0513R
CM0514R
CM0611R
CM0612R
CM0613R
CM0614R
CM0615R
CM07A1R
CM07A3R
CM07A5R
CM0813R
CM0913R
CM0914R
CM09A1R
CM09A8R
CM0C01R
CM0GA0R
CM0HA0R
CM0IA0R
CM0JA1R
CM0KA0R
CM0U08R
CM0U1AR
CM0X17R
CM7121R
CM7320R
CM7330R
CM73B0R
CM7B20R
CM9120R
CMB120R
CMB121R
CMN1B0R
CMT1B0R
CMT1B1R
CMU7B0R
CMXZ2AR
CMXZ2BR
CMXZ2CR
CMXZ2YR
CMXZ2YR10
CU0420R
CV010VR
CV010WR
CV010YR
CV0111R
CV0112R
CV0113R
CV0114R
CV0115R
CV0116R
CV0118R
CV0119R
CV011AR
CV011BR
CV011ER
CV011FR
CV011GR
CV011HR
CV011HR10
CV011MR
CV011NR
CV011TR
CV011TR10
CV011UR
CV01A5R
CV01A7R
CV01ADR
CV01AFR
CV01AHR
CV03A0R
CV1121R
CV1122R
CV1422R
CV1521R
CV1524R
CV1721R
CV1722R
CV1723R
CV1725R
CV1727R
CV1A21R
CV1A21R10
CV1A23R
CV1D20R
CV1F20R
CV1G20R
CV1H20R
CV1J20R
CV1K20R
CV1O21R
CV1O22R
CV1O23R
CV3020R
CV3025R
CV30B0R
Furnace Equipment
Furnace Equipment Delivery at Site
CU0110D
CU02110D
CU02120D
CU02130D
CU02140D
CU02150D
CU02160D
CU02161D
CU02170D
CU02180D
CU02190D
CU021A0D
CU03A0D
CU0420D
CU04A0D
Furnace Equipment Required at Site
CU0110R
CU02110R
CU02120R
CU02130R
CU02140R
CU02150R
CU02160R
CU02161R
CU02170R
CU02180R
CU02190R
CU021A0R
CU03A0R
CU04A0R
Piping Material
Piping Material Delivery at Site
CP0101D
CP0102D
CP0201D
CP0203D
CP0204D
CP0205D
CP0301D
CP0302D
CP0303D
CP0401D
CP0A01D
CP0A03D
CP0C00D
CP0F00D
Piping Material Required at Site
CP0101R
CP0102R
CP0201R
CP0203R
CP0204R
CP0205R
CP0301R
CP0302R
CP0303R
CP0401R
CP0A01R
CP0A03R
CP0C00R
CP0F00R
Electrical Equipment & Material
Electrical Equipment & Material Delivery at Site
CE0101D
CE0102D
CE0201D
CE0401D
CE0402D
CE0500D
CE0600D
CE0700D
CE0801D
CE0802D
CE0900D
CE0A01D
CE0A09D
CE0B00D
CE0C01D
CE0C01D10
CE0C01D20
CE0C01D30
CE0C02D
CE0C03D
CE0C04D
CE0C05D
CE0C09D
Electrical Equipment & Material Required at Site
CE0101R
CE0102R
CE0201R
CE0401R
CE0402R
CE0500R
CE0600R
CE0700R
CE0801R
CE0802R
CE0900R
CE0A01R
CE0A09R
CE0B00R
CE0C01R
CE0C01R10
CE0C01R20
CE0C01R30
CE0C02R
CE0C03R
CE0C04R
CE0C05R
CE0C09R
Instrument Equipment & Material
Instrument Equipment & Material Delivery at Site
CK0101D
CK0109D
CK0201D
CK0202D
CK0203D
CK0204D
CK0205D
CK0205D10
CK0206D
CK0206D10
CK0207D
CK0208D
CK0209D
CK0301D
CK0302D
CK0303D
CK0305D
CK0306D
CK0309D
Instrument Equipment & Material Required at Site
CK0101R
CK0109R
CK0201R
CK0202R
CK0203R
CK0204R
CK0205R
CK0205R10
CK0206R
CK0206R10
CK0207R
CK0208R
CK0209R
CK0301R
CK0302R
CK0303R
CK0305R
CK0306R
CK0309R
Insulation Material
Insulation Material Delivery at Site
CS0A01D
Insulation Material Required at Site
CS0A01R
Painting Material
Painting Material Delivery at Site
CS0B01D
Painting Material Required at Site
CS0B01R
Other Material
Catalyst Delivery at Site
CB0100D
Laboratory Equip. Required at Site
C0BZ00R
Chemical Delivery at Site
CB0200D
Laboratory Equip. Delivery at Site
C0BZ00D
CONSTRUCTION
Temporary Work
Land Preparation (Excl. Plant Site)
CS11010
CS11020
CS11030
CS11040
Temporary Office
CS13010
Temporary Camp
CS14010
CS14090
Temporary Storage House
CS15010
Temporary Access Road & Laydown Area
CS16010
Temporary Fence & Gate
CS17010
CS17020
CS17030
CS17040
Temporary Utility
CS18010
CS18020
Other Temporary Facilities
CS1A010
CS1A020
CS1A030
Civil Work
CC20000
Site Preparation
CC21010
Equipment Foundation
CC23100
CC23200
CC23A00
CC23B00
Tank Foundation
CC24100
CC24200
CC24A00
CC24B00
Cooling Tower
CC25A10
CC25A20
Structure Foundation & RC Structure
CC26110
CC26112
CC26114
CC26210
CC26212
CC26214
CC26216
CC26218
CC26220
Pipe Rack Foundation & RC Structure
CC27111
CC27112
CC27121
CC27122
CC27131
CC27132
CC27141
CC27142
CC27211
CC27212
CC27221
CC27222
CC27231
CC27232
CC27241
CC27242
CC27243
CC27244
CC27245
CC27A11
CC27A12
CC27A21
CC27A22
CC27A31
CC27A32
CC27A41
CC27A42
CC27A51
CC27A52
CC27B11
CC27B12
CC27B21
CC27B22
CC27B31
CC27B32
CC2D160
CC2D170
CC2D180
CC2D190
CC2D200
CC2D210
CC2D220
CC2D230
Cable & Pipe Trench
CC29010
Drainage System
CC2A010
Road & Pavement
CC2B010
CC2B020
Underground Piping & Cable
CC2C010
Miscellaneous Work
CC2D020
CC2D030
CC2D040
CC2D050
CC2D060
CC2D240
CC2D250
CC2D260
CC2D270
CC2D280
CC2D290
CC2D300
CC2D310
CC2D320
CC2D330
CC2D340
CC2DA10
CC2DA20
CC2DA21
CC2DA22
CC2DA23
CC2DA24
CC2DA25
CC2DA26
CC2DA27
CC2DA28
CC2DA29
Steel Structure & Pipe Rack Shop Fabrication & Erection
CC30000
Steel Structure Erection
CC32110
CC32120
CC32130
CC32135
CC32136
CC32137
CC32138
CC32139
CC32140
CC32141
CC32142
CC32143
CC32210
CC32215
CC32220
CC32225
CC32230
CC32235
CC32240
CC32245
CC32250
CC32255
CC32260
CC32265
CC32270
CC32275
Steel Pipe Rack Erection
CC33110
CC33120
CC33130
CC33200
CC33210
CC33220
CC33240
CC33A10
CC33A30
CC33A40
CC33A50
CC33A60
CC33B00
CC33B10
CC33B20
Pipe Support Structure Erection
CC34100
CC34200
CC34A00
CC34A10
CC34A15
CC34A20
CC34A25
CC34A30
CC34A35
CC34A40
CC34A45
CC34A50
CC34B00
CC34B10
CC34B15
CC34B20
CC34B25
Others
CC36A20
CC36A30
CC36A40
CC36A50
CC36A60
CC36A70
CC36A80
CC36A90
Building Work
Control Building
CC41110
CC41120
CC41130
CC41140
CC41150
CC41160
CC41A10
CC41A11
CC41A12
CC41A13
CC41A14
CC41A15
CC41A16
CC41A17
CC41A18
CC41A19
CC41A20
CC41A21
CC41A22
CC41A24
CC41A25
CC41A26
CC41A27
CC41A28
CC41A29
CC41A30
CC41A31
CC41A32
CC41A33
CC41A34
CC41A35
CC41A36
CC41A37
CC41A38
CC41A39
CC41A40
Administration Building
CC42B10
CC42B20
CC42B30
CC42B40
CC42B50
CC42B70
Substation
CC44100
CC44105
CC44110
CC44115
CC44120
CC44125
CC44130
CC44135
CC44200
CC44205
CC44210
CC44215
CC44220
CC44225
CC44230
CC44235
CC44A00
CC44A05
CC44A10
CC44A15
CC44A20
CC44A25
CC44A30
CC44A35
CC44B00
CC44B05
CC44B10
CC44B15
CC44B20
CC44B25
CC44B30
CC44B35
CC44B40
CC44B45
CC44B50
CC44B55
CC44B60
CC44B65
CC44B70
CC44B75
EDG House
CC45A10
CC45A20
CC45A30
CC45A40
CC45A50
Compressor House
CC46110
CC46120
CC46130
CC46140
CC46150
Product Ware House
CC48B10
CC48B20
CC48B30
CC48B40
CC48B50
CC48B70
CC48B80
Laboratory Building
CC4CA10
CC4CA20
CC4CA30
CC4CA40
CC4CA50
CC4CA60
CC4CA70
CC4CA80
Granulation House
CC4F210
CC4F220
CC4F230
CC4F240
CC4F250
Others
CC4G100
CC4G101
CC4G102
CC4G103
CC4G104
CC4G105
CC4G106
CC4G107
CC4G108
CC4G109
CC4G110
CC4G111
CC4G201
CC4G202
CC4G203
CC4G204
CC4G205
CC4G206
CC4GA10
CC4GA11
CC4GA12
CC4GA13
CC4GA14
CC4GA15
CC4GA16
CC4GA17
CC4GA18
CC4GA19
CC4GA20
CC4GA21
CC4GA22
CC4GA23
CC4GA24
CC4GA25
CC4GA26
CC4GA27
CC4GA28
CC4GA29
CC4GA30
CC4GA31
CC4GA32
CC4GA33
CC4GA34
CC4GA35
CC4GA36
CC4GA37
CC4GA38
CC4GA39
CC4GA40
CC4GA41
CC4GA42
CC4GA43
CC4GA44
CC4GA45
CC4GA46
CC4GA47
CC4GB11
CC4GB12
CC4GB31
CC4GB32
CC4GB33
CC4GB34
CC4GB35
CC4GB36
CC4GB37
CC4GB38
CC4GB39
CC4GB40
CC4GB41
CC4GB42
CC4GB43
CC4GB44
CC4GB45
Equipment & Machinery Installation Work
Stationary Equipment
CV11110
CV11120
CV11130
CV11140
CV11210
CV11220
CV13120
CV14110
CV14120
CV14130
CV14141
CV14142
CV14221
CV15110
CV15131
CV15132
CV15141
CV15142
CV15161
CV15162
CV15211
CV15241
CV15242
CV15243
CV15244
CV15245
CV15A11
CV15A12
CV16110
CV17211
CV17221
CV17222
CV17231
CV17232
CV17233
CV17251
CV17252
CV17253
CV17A11
CV17A12
CV19110
CV19115
CV1A111
CV1A112
CV1A211
CV1A231
CV1A241
CV1A251
CV1D110
CV1D201
CV1DA11
CV1DA12
CV1F201
CV1FA01
CV1FA02
CV1G201
CV1H201
CV1H202
CV1HA01
CV1HA02
CV1J201
CV1K201
CV1O211
CV1O221
CV1O232
CV60260
CV60270
K.D. Tank
CV53210
CV53211
CV53212
CV53213
CV53311
CV53312
CV53313
CV53314
CV53A10
CV53A11
CV53A12
CV53A13
CV53A14
CV53A15
CV53A16
CV53A20
CV53A21
CV53A22
CV53A23
CV53A24
CV53A25
CV53A26
CV53A30
CV53A31
CV53A32
CV53A33
CV53A34
CV53A35
CV53A36
CV53A40
CV53B10
CV53B20
CV53B30
CV53B40
Internal Work
CV50210
CV5B110
CV5B120
Platform & Ladder
CV60210
CV60A10
CV60B10
CV6P110
Rotating Machine (Such As Pump, Fan Etc.)
CM71111
CM71112
CM71113
CM71132
CM71140
CM71151
CM71161
CM71191
CM71192
CM71210
CM71A10
CM71A20
CM73210
CM73220
CM73A10
CM73B10
CM73B20
CM75A10
CM77210
CM77220
CM7B210
CM7B220
Compressor & Gas / Steam Turbine Etc.
CM91161
CM91162
CM91163
CM91164
CM91165
CM91166
CM91167
CM91168
CM91169
CM9116A
CM91180
CM91210
CM91212
CM98A10
Conveyor
CMB1210
CMB1220
Hoist & Trolley
CMC3111
Demi. Water Unit
CMG0A10
Diesel Engine Generator
CMH1A10
CMH1A20
Cooling Tower
CMI1A10
Water Treatment Unit
CMJ0B10
Waste Water Unit
CMK0A10
Loading Unit
CMN1B10
Other Equipment Installation
CMT1B10
CMU7B10
CMU8A10
CMW2192
CMW21C0
CMW7110
CMXZ2B1
CMXZ2B2
CMXZ2C1
CMXZ2D1
CMXZ2Z0
CMXZ2Z10
Furnace Equipment Erection Work
Reformer Erection Work
CU21110
CU21111
CU21112
CU21113
CU21120
CU21130
CU21131
CU21140
CU21141
CU21150
CU21160
CU21170
CU21171
CU21180
CU211T0
CU22110
CU22120
CU22130
CU22140
CU22150
Package Boiler Erection Work
CU31A10
CU31A20
CU31A30
CU31A40
CU31A50
CU31A60
CU32A70
CU33A80
Flare Unit Erection Work
CU41200
CU41A00
CU41A10
CU42200
CU42A00
CU42A10
CU43200
CU43A00
CU43A10
CU44200
CU44A00
CU44A10
Other Furnace Equipment Erection Work
CU12110
CU12120
CU12130
CU12140
CU12150
Piping Work
Pipe Prefabrication Work
CP10100
CP10110
CP10200
CP10A00
CP10A10
CP10A20
CP10A30
CP10B00
Under Ground Pipe Installation (Including Prefab.)
CP21010
CP21020
CP23010
CP23020
Above Ground Pipe Installation
CP31100
CP31200
CP31A00
CP31B00
CP32100
CP32110
CP32200
CP32A00
CP32A10
CP32A20
CP32A30
CP32B00
CP33100
CP33200
CP33A00
CP33B00
CP34100
CP34200
CP34A00
CP34B00
Pipe Support (Including Stage Etc)
CP51100
CP51200
CP51A00
CP51B00
CP52100
CP52200
CP52A00
CP52B00
Test
CPA0100
CPA0110
CPA0200
CPA0A00
CPA0A10
CPA0A20
CPA0A30
CPA0B00
Flushing
CPB0100
CPB0110
CPB0200
CPB0A00
CPB0B00
Chemical Cleaning
CPC0100
CPC0200
CPC0A00
CPC0B00
Electrical Work
CE00010
CE00020
Electrical Underground Work
CE01000
Grounding & Lightning System Work
CE02000
Substation Equipment Work
CE31B10
CE31B20
CE32A10
CE32A20
CE32A30
CEC1B00
Cable Tray & Conduit Work
CE40100
CE40200
CE40A00
CE40B00
Power & Control Cable Work
CE50100
CE50200
CE50B00
CE51A00
CE52A00
Lighting System Work
CE60100
CE60200
CE60A00
CE60B00
Communication System Work
CE70100
CE70200
CE70A00
CE70B00
Fire Alarm System Work
CE80100
CE80200
CE80A00
CE80B00
Cathodic Protection System Work
CE90100
CE90200
CE90A00
CE90B00
Heat Trace Work
CEA0100
CEA0200
CEA0A00
CEA0B00
Other System Work
CEB0100
CEB0200
CEB0A00
CEB0B00
Electrical Test & Inspection
CEC0100
CEC0200
CEC0A00
CEC0B00
CEC1A00
Instrumentation Work
CK00010
CK00020
CK01A10
CK01A20
CK01A30
Control System Installation
CK11110
CK11A10
CK11B10
CK14A10
Instrument & Equipment Installation
CK20100
CK20110
CK20200
CK20A00
CK20B00
Piping/Tubing
CK31100
CK31200
CK31A00
CK31B00
CK36100
CK36200
CK36A00
CK36B00
CK37100
CK37200
CK37A00
CK37B00
Cabling/Wiring
CK40000
CK41100
CK41200
CK41A00
CK41B00
CK42100
CK42200
CK42A00
CK42B00
CK44100
CK44200
CK44A00
CK44B00
CK45100
CK45200
CK45A00
CK45B00
Special Test & Special Work
CK50100
CK50200
CK50A00
CK50B00
Calibration
CK60100
CK60200
CK60A00
CK60B00
Loop/Sequence Test
CK70100
CK70110
CK70200
CK70A00
CK70A10
CK70A20
CK70A30
CK70B00
Insulation Work
Insulation Work
CSA1100
CSA1200
CSA1A00
CSA1B00
CSA2100
CSA2200
CSA2A00
CSA2B00
CSA3100
CSA3200
CSA3A00
CSA3B00
Painting Work
Painting Work
CSB1100
CSB1200
CSB1A00
CSB1B00
CSB2100
CSB2200
CSB2A00
CSB2B00
CSB3100
CSB3200
CSB3A00
CSB3B00
CSB4100
CSB4200
CSB4A00
CSB4B00
CSB6100
CSB6200
CSB6A00
CSB6B00
CSB7100
CSB7200
CSB7A00
CSB7B00
Other Unclassified Work
Laboratory Work
CBZ1000
PRE-COMMISSIONING
Utility Pre-commissioning
Electrical Power & Control
SBC0110
SBC0120
SBC0130
SBC0140
SBC0210
SBC0220
SBC0310
SBC0410
SBC0510
SBC0610
IA System
SBC1910
SBC1920
SBC1930
Raw Water System
SBC1310
SBC1320
SBC1330
Demi, Water System
SBC1400
SBC1410
SBC1420
SBC1440
Cooling Water System
SBC1200
SBC1201
SBC1210
SBC1212
SBC1214
SBC1230
SBC1232
SBC1234
SBC1236
SBC1238
SBC1260
SBC1261
SBC1262
SBC1264
SBC1266
SBC1268
SBC1270
WWT System
SBC3510
SBC3511
SBC3520
SBC3530
Fire Water System
SBC3110
SBC3120
SBC3130
Nitrogen System
SBC2010
SBC2020
SBC2030
SBC2040
Natural Gas System
SBC1810
SBC1820
Flare System
SBC4310
SBC4320
SBC4330
BFW System
SBC1500
SBC1501
SBC1510
SBC1511
SBC1520
SBC1530
SBC1540
SBC1550
Boiler & Steam System
SBC1600
SBC1610
SBC1620
SBC1630
SBC1635
SBC1640
SBC1650
SBC1660
SBC1670
SBC1680
SBC1690
EDG System
SBC4210
SBC4220
SBC4230
Ammonia Pre-commissioning
SBCA111
SBCA112
SBCA121
SBCA122
SBCA131
SBCA132
SBCA141
SBCA142
SBCA151
SBCA152
SBCA161
SBCA162
SBCA171
SBCA172
Front End
SBCA210
SBCA211
SBCA212
SBCA213
SBCA214
SBCA220
SBCA230
SBCA241
SBCA242
SBCA243
SBCA244
SBCA250
SBCA251
SBCA260
SBCA261
SBCA262
SBCA263
CO2 Removal
SBCA310
SBCA320
SBCA330
SBCA340
SBCA350
SBCA360
SBCA370
SBCA380
Process Compressor
SBCA410
SBCA411
SBCA412
SBCA413
SBCA414
SBCA420
SBCA421
SBCA422
SBCA423
SBCA424
SBCA425
SBCA426
SBCA427
SBCA430
SBCA431
SBCA432
SBCA433
SBCA434
SBCA435
SBCA436
SBCA442
SBCA443
SBCA444
SBCA445
Syn. Loop
SBCA510
SBCA520
HP BFW
SBCA610
SBCA620
SBCA630
SBCA631
SBCA640
SBCA641
Process Condensate
SBCA700
SBCA710
SBCA720
SBCA730
ARU & HRU
SBCA810
SBCA820
SBCA830
Flare
SBCA900
SBCA910
SBCA920
SBCA930
SBCA940
Urea Pre-commissioning
SBCU111
SBCU112
SBCU121
SBCU122
SBCU141
SBCU142
SBCU151
SBCU152
SBCU161
SBCU162
SBCU163
SBCU164
CO2 Compressor
SBCU110
SBCU120
SBCU125
SBCU130
SBCU140
SBCU150
SBCU160
SBCU170
HP Section
SBCU210
SBCU220
SBCU230
SBCU240
SBCU250
SBCU260
MP Section
SBCU310
SBCU320
SBCU330
SBCU340
LP Section
SBCU410
SBCU420
SBCU430
SBCU440
Vaccum Section
SBCU510
SBCU520
SBCU530
SBCU540
SBCU550
Process Condensate Tretement Section
SBCU610
SBCU620
SBCU630
SBCU640
SBCU650
SBCU660
Condensate Recovery & Washing Section
SBCU710
SBCU720
SBCU730
SBCU740
SBCU750
Granulation
SBCU810
SBCU811
SBCU820
SBCU830
SBCU840
SBCU850
SBCU860
SBCU870
Vent & Drain Section
SBCU910
SBCU920
SBCU930
SBCU950
SBCU960
SBCU970
SBCU980
Offsite Pre-commissioning
Ammonia Storage
SBCO3210
SBCO3220
SBCO3230
SBCO3240
SBCO3250
SBCO3260
SBCO3270
SBCO3280
SBCO3290
Urea Material Handling
SBCAC110
SBCAC120
SBCAC130
SBCAC210
SBCAC220
SBCAC230
SBCAC240
COMMISSIONING
Ammonia Commissioning
SBCG100
SBCG101
SBCG102
SBCG103
SBCG104
SBCG105
SBCG106
SBCG107
SBCG108
SBCG130
SBCG140
SBCG141
SBCG142
SBCG143
SBCG144
SBCG145
SBCG146
SBCG150
SBCG151
SBCG152
SBCM100
Urea Commissioning
SBCG201
SBCG202
SBCG203
SBCG204
SBCG205
SBCG206
SBCG211
SBCG212
SBCG213
SBCG215
SBCM200
Offsite Commissioning
SBCG321
SBCG322
SBCG323
SBCG361
SBCG371
SBCG381
SBCM300