## Лист1
Risk theme | Risk title
Executive_Support

## Лист2
Executive_Support | Scope | Cost_Management | Change_Management | Stakeholders | Communication | Resources_and_Team | Architecture | Design | Technical | Integration | Requirements | Decisions_and_Issue_Resolution | Procurement | Authority | Approvals_and_Red_Tape | Organizational | External | Project_Management | Secondary_Risks | User_Acceptance
Executives fail to support project | Scope is ill defined | Cost forecasts are inaccurate | Change management overload | Stakeholders become disengaged | Project team misunderstand requirements | Resource shortfalls | Architecture fails to pass governance processes | Design is infeasible | Technology components aren't fit for purpose | Delays to required infrastructure | Requirements fail to align with strategy | Decision delays impact project | No response to RFP | Project team lack authority to complete work | Delays to stakeholder approvals impact the project | The project fails to match the organization's culture | Legal & regulatory change impacts project | Failure to follow methodology | Counterparty risk | Users reject the prototype
Executives become disengaged with project | Scope creep inflates scope | Exchange rate variability | Stakeholder conflict over proposed changes | Stakeholders have inaccurate expectations | Communication overhead | Learning curves lead to delays and cost overrun | Architecture lacks flexibility | Design lacks flexibility | Technology components aren't scalable | Failure to integrate with business processes | Requirements fail to align with business processes | Decisions are ambiguous | Low quality responses to RFP | Authority is unclear | Delays to financial approvals impact the project | An organizational restructuring throws the project into chaos | Force Majeure (eg act of nature) impacts project | Lack of management or control |  | User interface doesn't allow users to complete tasks
Conflict between executive stakeholders disrupts project | Gold plating inflates scope |  | Perceptions that a project failed because of changes | Stakeholder turnover | Under communication | Training isn't available | Architecture is not fit for purpose | Design is not fit for purpose | Technology components aren't interoperable | Failure to integrate with systems | Requirements fail to align with systems | Decisions are low quality | Failure to negotiation a reasonable price for contracts |  | Delays to procurement processes impact the project | A merger or acquisition disrupts the project | Market forces impact project | Errors in key project management processes |  | User interface is low quality
Executive turnover disrupts project | Estimates are inaccurate |  | Lack of a change management system | Stakeholders fail to support project | Users have inaccurate expectations | Training is inadequate | Architecture is infeasible | Design fails peer review | Technology components aren't compliant with standards and best practices | Integration testing environments aren't available | Requirements have compliance issues | Decisions are incomplete | Unacceptable contract terms |  | Delays to recruiting processes impact the project |  | Technical change impacts project |  |  | User interface isn't accessible
| Dependencies are inaccurate |  | Lack of a change management process | Stakeholder conflict | Impacted individuals aren't kept informed | Resources are inexperienced |  |  | Technology components have security vulnerabilities | Failure to integration with the organization | Requirements are ambiguous |  | Conflict with vendor leads to project issues |  | Delays to training impact the project |  | Business change impacts project |  |  | Project reduces business productivity
| Activities are missing from scope |  | Lack of a change control board | Process inputs are low quality |  | Resource performance issues |  |  | Technology components are over-engineered | Failure to integrate components | Requirements are low quality |  | Conflict between vendors leads to project issues | [6 empty] | Project reduces innovation
|  |  | Inaccurate change priorities |  |  | Team members with negative attitudes towards the project |  |  | Technology components lack stability | Project disrupts operations | Requirements are incomplete |  | Vendors start late | [6 empty] | Product disrupts business metrics (measurements of objectives)
|  |  | Low quality of change requests |  |  | Resource turnover |  |  | Technology components aren't extensible | Project disrupts sales |  |  | Vendor components fail to meet requirements | [6 empty] | Users reject the product
|  |  | Change request conflicts with requirements |  |  | Low team motivation |  |  | Technology components aren't reliable | Project disrupts compliance |  |  | Vendor components are low quality | [6 empty] | Product doesn't sell
[6 empty] | Lack of commitment from functional managers |  |  | Information security incidents |  |  |  | Infrastructure is low quality | [6 empty] | Product incurs legal liability
[9 empty] | System outages |  |  |  | Service quality is low | [6 empty] | Product negatively affects brand
[9 empty] | Legacy components lack documentation |  |  |  | Vendor components introduce third party liability | [6 empty] | Product negatively affects reputation
[9 empty] | Legacy components are out of support |  |  |  | Loss of intellectual property
Components or products aren't maintainable
Components or products can't be operationalized
Project management tool problems & issues
Theme
Executive_Support
Scope
Cost_Management
Change_Management
Stakeholders
Communication
Resources_and_Team
Architecture
Design
Technical
Integration
Requirements
Decisions_and_Issue_Resolution
Procurement
Authority
Approvals_and_Red_Tape
Organizational
External
Project_Management
Secondary_Risks
User_Acceptance