{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["Лист1","Лист2"],"not_rendered":{"charts":0,"images":3,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Лист1","index":0,"n_rows":479,"n_cols":13,"rows_kept":479,"cut":false,"hidden":false,"merged":[[476,12,476,13],[477,12,477,13],[478,12,478,13],[476,8,476,9],[477,8,477,9],[478,8,478,9],[476,10,476,11],[477,10,477,11],[478,10,478,11],[473,12,473,13],[474,12,474,13],[475,12,475,13],[476,0,478,0],[476,1,476,2],[477,1,477,2],[478,1,478,2],[476,3,478,3],[476,4,478,5],[476,6,478,7],[473,6,475,7],[473,8,473,9],[474,8,474,9],[475,8,475,9],[473,10,473,11],[474,10,474,11],[475,10,475,11],[473,0,475,0],[473,1,473,2],[474,1,474,2],[475,1,475,2],[473,3,475,3],[473,4,475,5],[470,6,472,7],[470,8,470,9],[471,8,471,9],[472,8,472,9],[470,10,472,11],[470,12,470,13],[471,12,471,13],[472,12,472,13],[470,0,472,0],[470,1,470,2],[471,1,471,2],[472,1,472,2],[470,3,472,3],[470,4,472,5],[467,6,469,7],[467,8,467,9],[468,8,468,9],[469,8,469,9],[467,10,469,11],[467,12,467,13],[468,12,468,13],[469,12,469,13],[467,0,469,0],[467,1,467,2],[468,1,468,2],[469,1,469,2],[467,3,469,3],[467,4,469,5],[464,8,464,9],[465,8,465,9],[466,8,466,9],[464,10,466,11],[464,12,464,13],[465,12,465,13],[466,12,466,13],[461,12,461,13],[462,12,462,13],[463,12,463,13],[464,0,466,0],[464,1,464,2],[465,1,465,2],[466,1,466,2],[464,3,466,3],[464,4,466,5],[464,6,466,7],[461,4,463,5],[461,6,463,7],[461,8,461,9],[462,8,462,9],[463,8,463,9],[461,10,463,11],[461,0,463,0],[461,1,461,2],[462,1,462,2],[463,1,463,2],[461,3,463,3],[458,6,460,7],[458,8,458,9],[459,8,459,9],[460,8,460,9],[458,10,460,11],[458,12,458,13],[459,12,459,13],[460,12,460,13],[458,0,460,0],[458,1,458,2],[459,1,459,2],[460,1,460,2],[458,3,460,3],[458,4,460,5],[455,6,457,7],[455,8,455,9],[456,8,456,9],[457,8,457,9],[455,10,457,11],[455,12,455,13],[456,12,456,13],[457,12,457,13],[455,0,457,0],[455,1,455,2],[456,1,456,2],[457,1,457,2],[455,3,457,3],[455,4,457,5],[452,6,454,7],[452,8,452,9],[453,8,453,9],[454,8,454,9],[452,10,454,11],[452,12,452,13],[453,12,453,13],[454,12,454,13],[452,0,454,0],[452,1,452,2],[453,1,453,2],[454,1,454,2],[452,3,454,3],[452,4,454,5],[449,6,451,7],[449,8,449,9],[450,8,450,9],[451,8,451,9],[449,10,451,11],[449,12,449,13],[450,12,450,13],[451,12,451,13],[449,0,451,0],[449,1,449,2],[450,1,450,2],[451,1,451,2],[449,3,451,3],[449,4,451,5],[446,6,448,7],[446,8,446,9],[447,8,447,9],[448,8,448,9],[446,10,448,11],[446,12,446,13],[447,12,447,13],[448,12,448,13],[446,0,448,0],[446,1,446,2],[447,1,447,2],[448,1,448,2],[446,3,448,3],[446,4,448,5],[443,6,445,7],[443,8,443,9],[444,8,444,9],[445,8,445,9],[443,10,445,11],[443,12,443,13],[444,12,444,13],[445,12,445,13],[443,0,445,0],[443,1,443,2],[444,1,444,2],[445,1,445,2],[443,3,445,3],[443,4,445,5],[440,8,440,9],[441,8,441,9],[442,8,442,9],[440,10,442,11],[440,12,440,13],[441,12,441,13],[442,12,442,13],[437,12,437,13],[438,12,438,13],[439,12,439,13],[440,0,442,0],[440,1,440,2],[441,1,441,2],[442,1,442,2],[440,3,442,3],[440,4,442,5],[440,6,442,7],[437,6,439,7],[437,8,437,9],[438,8,438,9],[439,8,439,9],[437,10,437,11],[438,10,438,11],[439,10,439,11],[437,0,439,0],[437,1,437,2],[438,1,438,2],[439,1,439,2],[437,3,439,3],[437,4,439,5],[434,6,436,7],[434,8,434,9],[435,8,435,9],[436,8,436,9],[434,10,436,11],[434,12,434,13],[435,12,435,13],[436,12,436,13],[434,0,436,0],[434,1,434,2],[435,1,435,2],[436,1,436,2],[434,3,436,3],[434,4,436,5],[431,6,433,7],[431,8,431,9],[432,8,432,9],[433,8,433,9],[431,10,433,11],[431,12,431,13],[432,12,432,13],[433,12,433,13],[431,0,433,0],[431,1,431,2],[432,1,432,2],[433,1,433,2],[431,3,433,3],[431,4,433,5],[428,6,430,7],[428,8,428,9],[429,8,429,9],[430,8,430,9],[428,10,430,11],[428,12,428,13],[429,12,429,13],[430,12,430,13],[428,0,430,0],[428,1,428,2],[429,1,429,2],[430,1,430,2],[428,3,430,3],[428,4,430,5],[425,6,427,7],[425,8,425,9],[426,8,426,9],[427,8,427,9],[425,10,427,11],[425,12,425,13],[426,12,426,13],[427,12,427,13],[425,0,427,0],[425,1,425,2],[426,1,426,2],[427,1,427,2],[425,3,427,3],[425,4,427,5],[422,6,424,7],[422,8,422,9],[423,8,423,9],[424,8,424,9],[422,10,424,11],[422,12,422,13],[423,12,423,13],[424,12,424,13],[422,0,424,0],[422,1,422,2],[423,1,423,2],[424,1,424,2],[422,3,424,3],[422,4,424,5],[419,6,421,7],[419,8,419,9],[420,8,420,9],[421,8,421,9],[419,10,421,11],[419,12,419,13],[420,12,420,13],[421,12,421,13],[419,0,421,0],[419,1,419,2],[420,1,420,2],[421,1,421,2],[419,3,421,3],[419,4,421,5],[416,6,418,7],[416,8,416,9],[417,8,417,9],[418,8,418,9],[416,10,418,11],[416,12,416,13],[417,12,417,13],[418,12,418,13],[416,0,418,0],[416,1,416,2],[417,1,417,2],[418,1,418,2],[416,3,418,3],[416,4,418,5],[413,6,415,7],[413,8,413,9],[414,8,414,9],[415,8,415,9],[413,10,415,11],[413,12,413,13],[414,12,414,13],[415,12,415,13],[413,0,415,0],[413,1,413,2],[414,1,414,2],[415,1,415,2],[413,3,415,3],[413,4,415,5],[410,6,412,7],[410,8,410,9],[411,8,411,9],[412,8,412,9],[410,10,412,11],[410,12,410,13],[411,12,411,13],[412,12,412,13],[410,0,412,0],[410,1,410,2],[411,1,411,2],[412,1,412,2],[410,3,412,3],[410,4,412,5],[407,6,409,7],[407,8,407,9],[408,8,408,9],[409,8,409,9],[407,10,409,11],[407,12,407,13],[408,12,408,13],[409,12,409,13],[407,0,409,0],[407,1,407,2],[408,1,408,2],[409,1,409,2],[407,3,409,3],[407,4,409,5],[404,6,406,7],[404,8,404,9],[405,8,405,9],[406,8,406,9],[404,10,406,11],[404,12,404,13],[405,12,405,13],[406,12,406,13],[404,0,406,0],[404,1,404,2],[405,1,405,2],[406,1,406,2],[404,3,406,3],[404,4,406,5],[401,6,403,7],[401,8,401,9],[402,8,402,9],[403,8,403,9],[401,10,403,11],[401,12,401,13],[402,12,402,13],[403,12,403,13],[401,0,403,0],[401,1,401,2],[402,1,402,2],[403,1,403,2],[401,3,403,3],[401,4,403,5],[398,6,400,7],[398,8,398,9],[399,8,399,9],[400,8,400,9],[398,10,400,11],[398,12,398,13],[399,12,399,13],[400,12,400,13],[398,0,400,0],[398,1,398,2],[399,1,399,2],[400,1,400,2],[398,3,400,3],[398,4,400,5],[395,6,397,7],[395,8,395,9],[396,8,396,9],[397,8,397,9],[395,10,397,11],[395,12,395,13],[396,12,396,13],[397,12,397,13],[395,0,397,0],[395,1,395,2],[396,1,396,2],[397,1,397,2],[395,3,397,3],[395,4,397,5],[392,6,394,7],[392,8,392,9],[393,8,393,9],[394,8,394,9],[392,10,394,11],[392,12,392,13],[393,12,393,13],[394,12,394,13],[392,0,394,0],[392,1,392,2],[393,1,393,2],[394,1,394,2],[392,3,394,3],[392,4,394,5],[389,6,391,7],[389,8,389,9],[390,8,390,9],[391,8,391,9],[389,10,391,11],[389,12,389,13],[390,12,390,13],[391,12,391,13],[389,0,391,0],[389,1,389,2],[390,1,390,2],[391,1,391,2],[389,3,391,3],[389,4,391,5],[386,6,388,7],[386,8,386,9],[387,8,387,9],[388,8,388,9],[386,10,388,11],[386,12,386,13],[387,12,387,13],[388,12,388,13],[386,0,388,0],[386,1,386,2],[387,1,387,2],[388,1,388,2],[386,3,388,3],[386,4,388,5],[383,6,385,7],[383,8,383,9],[384,8,384,9],[385,8,385,9],[383,10,385,11],[383,12,383,13],[384,12,384,13],[385,12,385,13],[383,0,385,0],[383,1,383,2],[384,1,384,2],[385,1,385,2],[383,3,385,3],[383,4,385,5],[380,6,382,7],[380,8,380,9],[381,8,381,9],[382,8,382,9],[380,10,382,11],[380,12,380,13],[381,12,381,13],[382,12,382,13],[380,0,382,0],[380,1,380,2],[381,1,381,2],[382,1,382,2],[380,3,382,3],[380,4,382,5],[377,6,379,7],[377,8,377,9],[378,8,378,9],[379,8,379,9],[377,10,379,11],[377,12,377,13],[378,12,378,13],[379,12,379,13],[377,0,379,0],[377,1,377,2],[378,1,378,2],[379,1,379,2],[377,3,379,3],[377,4,379,5],[374,6,376,7],[374,8,374,9],[375,8,375,9],[376,8,376,9],[374,10,376,11],[374,12,374,13],[375,12,375,13],[376,12,376,13],[374,0,376,0],[374,1,374,2],[375,1,375,2],[376,1,376,2],[374,3,376,3],[374,4,376,5],[371,8,371,9],[372,8,372,9],[373,8,373,9],[371,10,373,11],[371,12,371,13],[372,12,372,13],[373,12,373,13],[368,12,368,13],[369,12,369,13],[370,12,370,13],[371,0,373,0],[371,1,371,2],[372,1,372,2],[373,1,373,2],[371,3,373,3],[371,4,373,5],[371,6,373,7],[368,6,370,7],[368,8,368,9],[369,8,369,9],[370,8,370,9],[368,10,368,11],[369,10,369,11],[370,10,370,11],[368,0,370,0],[368,1,368,2],[369,1,369,2],[370,1,370,2],[368,3,370,3],[368,4,370,5],[365,6,367,7],[365,8,365,9],[366,8,366,9],[367,8,367,9],[365,10,367,11],[365,12,365,13],[366,12,366,13],[367,12,367,13],[365,0,367,0],[365,1,365,2],[366,1,366,2],[367,1,367,2],[365,3,367,3],[365,4,367,5],[362,6,364,7],[362,8,362,9],[363,8,363,9],[364,8,364,9],[362,10,364,11],[362,12,362,13],[363,12,363,13],[364,12,364,13],[362,0,364,0],[362,1,362,2],[363,1,363,2],[364,1,364,2],[362,3,364,3],[362,4,364,5],[359,8,359,9],[360,8,360,9],[361,8,361,9],[359,10,361,11],[359,12,359,13],[360,12,360,13],[361,12,361,13],[356,12,356,13],[357,12,357,13],[358,12,358,13],[359,0,361,0],[359,1,359,2],[360,1,360,2],[361,1,361,2],[359,3,361,3],[359,4,361,5],[359,6,361,7],[356,8,356,9],[357,8,357,9],[358,8,358,9],[356,10,356,11],[357,10,357,11],[358,10,358,11],[353,12,353,13],[354,12,354,13],[355,12,355,13],[356,0,358,0],[356,1,356,2],[357,1,357,2],[358,1,358,2],[356,3,358,3],[356,4,358,5],[356,6,358,7],[353,6,355,7],[353,8,353,9],[354,8,354,9],[355,8,355,9],[353,10,353,11],[354,10,354,11],[355,10,355,11],[353,0,355,0],[353,1,353,2],[354,1,354,2],[355,1,355,2],[353,3,355,3],[353,4,355,5],[350,6,352,7],[350,8,350,9],[351,8,351,9],[352,8,352,9],[350,10,352,11],[350,12,350,13],[351,12,351,13],[352,12,352,13],[350,0,352,0],[350,1,350,2],[351,1,351,2],[352,1,352,2],[350,3,352,3],[350,4,352,5],[347,6,349,7],[347,8,347,9],[348,8,348,9],[349,8,349,9],[347,10,349,11],[347,12,347,13],[348,12,348,13],[349,12,349,13],[347,0,349,0],[347,1,347,2],[348,1,348,2],[349,1,349,2],[347,3,349,3],[347,4,349,5],[344,6,346,7],[344,8,344,9],[345,8,345,9],[346,8,346,9],[344,10,346,11],[344,12,344,13],[345,12,345,13],[346,12,346,13],[344,0,346,0],[344,1,344,2],[345,1,345,2],[346,1,346,2],[344,3,346,3],[344,4,346,5],[341,8,341,9],[342,8,342,9],[343,8,343,9],[341,10,343,11],[341,12,341,13],[342,12,342,13],[343,12,343,13],[338,12,338,13],[339,12,339,13],[340,12,340,13],[341,0,343,0],[341,1,341,2],[342,1,342,2],[343,1,343,2],[341,3,343,3],[341,4,343,5],[341,6,343,7],[338,6,340,7],[338,8,338,9],[339,8,339,9],[340,8,340,9],[338,10,338,11],[339,10,339,11],[340,10,340,11],[338,0,340,0],[338,1,338,2],[339,1,339,2],[340,1,340,2],[338,3,340,3],[338,4,340,5],[335,6,337,7],[335,8,335,9],[336,8,336,9],[337,8,337,9],[335,10,337,11],[335,12,335,13],[336,12,336,13],[337,12,337,13],[335,0,337,0],[335,1,335,2],[336,1,336,2],[337,1,337,2],[335,3,337,3],[335,4,337,5],[332,6,334,7],[332,8,332,9],[333,8,333,9],[334,8,334,9],[332,10,334,11],[332,12,332,13],[333,12,333,13],[334,12,334,13],[332,0,334,0],[332,1,332,2],[333,1,333,2],[334,1,334,2],[332,3,334,3],[332,4,334,5],[329,8,329,9],[330,8,330,9],[331,8,331,9],[329,10,331,11],[329,12,329,13],[330,12,330,13],[331,12,331,13],[326,12,326,13],[327,12,327,13],[328,12,328,13],[329,0,331,0],[329,1,329,2],[330,1,330,2],[331,1,331,2],[329,3,331,3],[329,4,331,5],[329,6,331,7],[326,6,328,7],[326,8,326,9],[327,8,327,9],[328,8,328,9],[326,10,326,11],[327,10,327,11],[328,10,328,11],[326,0,328,0],[326,1,326,2],[327,1,327,2],[328,1,328,2],[326,3,328,3],[326,4,328,5],[323,6,325,7],[323,8,323,9],[324,8,324,9],[325,8,325,9],[323,10,325,11],[323,12,323,13],[324,12,324,13],[325,12,325,13],[323,0,325,0],[323,1,323,2],[324,1,324,2],[325,1,325,2],[323,3,325,3],[323,4,325,5],[320,6,322,7],[320,8,320,9],[321,8,321,9],[322,8,322,9],[320,10,322,11],[320,12,320,13],[321,12,321,13],[322,12,322,13],[320,0,322,0],[320,1,320,2],[321,1,321,2],[322,1,322,2],[320,3,322,3],[320,4,322,5],[317,6,319,7],[317,8,317,9],[318,8,318,9],[319,8,319,9],[317,10,319,11],[317,12,317,13],[318,12,318,13],[319,12,319,13],[317,0,319,0],[317,1,317,2],[318,1,318,2],[319,1,319,2],[317,3,319,3],[317,4,319,5],[314,6,316,7],[314,8,314,9],[315,8,315,9],[316,8,316,9],[314,10,316,11],[314,12,314,13],[315,12,315,13],[316,12,316,13],[314,0,316,0],[314,1,314,2],[315,1,315,2],[316,1,316,2],[314,3,316,3],[314,4,316,5],[311,8,311,9],[312,8,312,9],[313,8,313,9],[311,10,313,11],[311,12,311,13],[312,12,312,13],[313,12,313,13],[308,12,308,13],[309,12,309,13],[310,12,310,13],[311,0,313,0],[311,1,311,2],[312,1,312,2],[313,1,313,2],[311,3,313,3],[311,4,313,5],[311,6,313,7],[308,8,308,9],[309,8,309,9],[310,8,310,9],[308,10,308,11],[309,10,309,11],[310,10,310,11],[305,12,305,13],[306,12,306,13],[307,12,307,13],[308,0,310,0],[308,1,308,2],[309,1,309,2],[310,1,310,2],[308,3,310,3],[308,4,310,5],[308,6,310,7],[305,8,305,9],[306,8,306,9],[307,8,307,9],[305,10,305,11],[306,10,306,11],[307,10,307,11],[302,12,302,13],[303,12,303,13],[304,12,304,13],[305,0,307,0],[305,1,305,2],[306,1,306,2],[307,1,307,2],[305,3,307,3],[305,4,307,5],[305,6,307,7],[302,8,302,9],[303,8,303,9],[304,8,304,9],[302,10,302,11],[303,10,303,11],[304,10,304,11],[299,12,299,13],[300,12,300,13],[301,12,301,13],[302,0,304,0],[302,1,302,2],[303,1,303,2],[304,1,304,2],[302,3,304,3],[302,4,304,5],[302,6,304,7],[299,8,299,9],[300,8,300,9],[301,8,301,9],[299,10,299,11],[300,10,300,11],[301,10,301,11],[296,12,296,13],[297,12,297,13],[298,12,298,13],[299,0,301,0],[299,1,299,2],[300,1,300,2],[301,1,301,2],[299,3,301,3],[299,4,301,5],[299,6,301,7],[296,8,296,9],[297,8,297,9],[298,8,298,9],[296,10,296,11],[297,10,297,11],[298,10,298,11],[293,12,293,13],[294,12,294,13],[295,12,295,13],[296,0,298,0],[296,1,296,2],[297,1,297,2],[298,1,298,2],[296,3,298,3],[296,4,298,5],[296,6,298,7],[293,8,293,9],[294,8,294,9],[295,8,295,9],[293,10,293,11],[294,10,294,11],[295,10,295,11],[290,12,290,13],[291,12,291,13],[292,12,292,13],[293,0,295,0],[293,1,293,2],[294,1,294,2],[295,1,295,2],[293,3,295,3],[293,4,295,5],[293,6,295,7],[290,6,292,7],[290,8,290,9],[291,8,291,9],[292,8,292,9],[290,10,290,11],[291,10,291,11],[292,10,292,11],[290,0,292,0],[290,1,290,2],[291,1,291,2],[292,1,292,2],[290,3,292,3],[290,4,292,5],[287,6,289,7],[287,8,287,9],[288,8,288,9],[289,8,289,9],[287,10,289,11],[287,12,287,13],[288,12,288,13],[289,12,289,13],[287,0,289,0],[287,1,287,2],[288,1,288,2],[289,1,289,2],[287,3,289,3],[287,4,289,5],[284,6,286,7],[284,8,284,9],[285,8,285,9],[286,8,286,9],[284,10,286,11],[284,12,284,13],[285,12,285,13],[286,12,286,13],[284,0,286,0],[284,1,284,2],[285,1,285,2],[286,1,286,2],[284,3,286,3],[284,4,286,5],[281,6,283,7],[281,8,281,9],[282,8,282,9],[283,8,283,9],[281,10,283,11],[281,12,281,13],[282,12,282,13],[283,12,283,13],[281,0,283,0],[281,1,281,2],[282,1,282,2],[283,1,283,2],[281,3,283,3],[281,4,283,5],[278,6,280,7],[278,8,278,9],[279,8,279,9],[280,8,280,9],[278,10,280,11],[278,12,278,13],[279,12,279,13],[280,12,280,13],[278,0,280,0],[278,1,278,2],[279,1,279,2],[280,1,280,2],[278,3,280,3],[278,4,280,5],[275,6,277,7],[275,8,275,9],[276,8,276,9],[277,8,277,9],[275,10,277,11],[275,12,275,13],[276,12,276,13],[277,12,277,13],[275,0,277,0],[275,1,275,2],[276,1,276,2],[277,1,277,2],[275,3,277,3],[275,4,277,5],[272,6,274,7],[272,8,272,9],[273,8,273,9],[274,8,274,9],[272,10,274,11],[272,12,272,13],[273,12,273,13],[274,12,274,13],[272,0,274,0],[272,1,272,2],[273,1,273,2],[274,1,274,2],[272,3,274,3],[272,4,274,5],[269,6,271,7],[269,8,269,9],[270,8,270,9],[271,8,271,9]],"merged_total":2237,"flags":["merged_cut"]}
[]
[]
[]
["№ пп","НОМЕР ЗАДАЧИ",null,"Класс инцидента","ИНВЕНТАРНЫЙ НОМЕР",null,"МЕСТО­НАХОЖДЕНИЕ",null,"ДАТА"]
[null,null,null,null,null,null,null,null,"Создания",null,"Прибытия",null,"Решения"]
[null,null,null,null,null,null,null,null,null,null,"на объект",null,"(план.)"]
[null,null,null,null,null,null,null,null,null,null,"(план.)"]
[1,"TSK_5043142  «  INC_23901203",null,null,null,null,"ВФ ДК 6794 (НЧ)",null,"2018-01-23",null,"—",null,"2018-02-20"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"11:30:00",null,null,null,"11:30:00"]
[null,"НазначенаВыполняется",null,null,null,null,null,null,"59м. назад"]
[2,"TSK_5043001  «  INC_23900919",null,null,null,null,"ВФ ДК 7772 (НЧ)",null,"2018-01-23",null,"—",null,"2018-02-20"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"11:18:00",null,null,null,"11:18:00"]
[null,"НазначенаВыполняется",null,null,null,null,null,null,"1ч. 11м. назад"]
[3,"TSK_5042987  «  INC_23900758",null,null,null,null,"ВФ ДК 5945 (НЧ)",null,"2018-01-23",null,"—",null,"2018-02-20"]
[null,"Ме­ха­ни­че­ское по­вре­жде­ние двери (де­фор­ми­ро­ва­на, сло­ма­ны петли)",null,null,null,null,null,null,"11:10:00",null,null,null,"11:10:00"]
[null,"НазначенаВыполняется",null,null,null,null,null,null,"1ч. 19м. назад"]
[4,"TSK_5042948  «  INC_23900574",null,null,null,null,"ВФ ДК 5945 (НЧ)",null,"2018-01-23",null,"—",null,"2018-02-20"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"11:06:00",null,null,null,"11:06:00"]
[null,"НазначенаВыполняется",null,null,null,null,null,null,"1ч. 23м. назад"]
[5,"TSK_5041086  «  INC_23894151",null,null,null,null,"ВФ ДК 6803 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"17:49:00",null,null,null,"17:49:00"]
[null,"ВыполняетсяВыполняется"]
[6,"TSK_5041028  «  INC_23893921",null,null,null,null,"ВФ ДК 4709 (Кез)",null,"2018-01-22",null,"—",null,"2018-01-26"]
[null,"Не горит осве­ще­ние при вклю­че­нии тум­бле­ра",null,null,null,null,null,null,"17:33:00",null,null,null,"17:33:00"]
[null,"НазначенаВыполняется"]
[7,"TSK_5040238  «  INC_23891442",null,null,null,null,"ВФ ДК 7998 (Мензелинск)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"15:20:00",null,null,null,"15:20:00"]
[null,"ВыполняетсяВыполняется"]
[8,"TSK_5039300  «  INC_23888772",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"13:11:00",null,null,null,"13:11:00"]
[null,"ВыполняетсяВыполняется"]
[9,"TSK_5039218  «  INC_23888579",null,null,null,null,"ВФ ДК 5945 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"13:00:00",null,null,null,"13:00:00"]
[null,"ВыполняетсяВыполняется"]
[10,"TSK_5038526  «  INC_23871236",null,140000745641,null,null,"ВФ ДК 1663 (Ижевск)",null,"2018-01-22",null,"—",null,"2018-01-28"]
[null,"Сло­ма­на кноп­ка кассы",null,null,null,null,null,null,"11:25:00",null,null,null,"11:25:00"]
[null,"НазначенаВыполняется"]
[11,"TSK_5038302  «  INC_23885717",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"10:56:00",null,null,null,"10:56:00"]
[null,"ВыполняетсяВыполняется"]
[12,"TSK_5038251  «  INC_23885683",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"10:50:00",null,null,null,"10:50:00"]
[null,"ВыполняетсяВыполняется"]
[13,"TSK_5038188  «  INC_23885630",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2018-01-22",null,"—",null,"2018-01-28"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"10:49:00",null,null,null,"10:49:00"]
[null,"ВыполняетсяВыполняется"]
[14,"TSK_5038248  «  INC_23885617",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"10:48:00",null,null,null,"10:48:00"]
[null,"ВыполняетсяВыполняется"]
[15,"TSK_5038134  «  INC_23885311",null,null,null,null,"ВФ ДК 5037 (Ижевск)",null,"2018-01-22",null,"—",null,"2018-02-07"]
[null,"Не све­тит­ся вся вы­вес­ка",null,null,null,null,null,null,"10:30:00",null,null,null,"10:30:00"]
[null,"НазначенаВыполняется"]
[16,"TSK_5038123  «  INC_23885233",null,null,null,null,"ВФ ДК 5037 (Ижевск)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"10:29:00",null,null,null,"10:29:00"]
[null,"НазначенаВыполняется"]
[17,"TSK_5037946  «  INC_23884806",null,null,null,null,"ВФ ДК 7782 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"10:14:00",null,null,null,"10:14:00"]
[null,"ВыполняетсяВыполняется"]
[18,"TSK_5037125  «  INC_23882860",null,null,null,null,"ВФ ДК 3379 (Муслюмово)",null,"2018-01-22",null,"—",null,"2018-02-21"]
[null,"От­сут­ствие внеш­них по­вре­жде­ний. Сле­дов ко­па­ти. Це­лост­ность кор­пу­са",null,null,null,null,null,null,"08:07:00",null,null,null,"09:00:00"]
[null,"ВыполняетсяВыполняется"]
[19,"TSK_5036999  «  INC_23882545",null,null,null,null,"ВФ ДК 6800 (НЧ)",null,"2018-01-22",null,"—",null,"2018-02-19"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"07:30:00",null,null,null,"09:00:00"]
[null,"ВыполняетсяВыполняется"]
[20,"TSK_5033673  «  INC_23869689",null,null,null,null,"ВФ ДК 3614 (НЧ)",null,"2018-01-20",null,"—",null,"2018-02-17"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"11:20:00",null,null,null,"11:20:00"]
[null,"ВыполняетсяВыполняется"]
[21,"TSK_5032284  «  INC_23865100",null,null,null,null,"ВФ ДК 1580 (НЧ)",null,"2018-01-19",null,"—",null,"2018-02-16"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"17:32:00",null,null,null,"17:32:00"]
[null,"ВыполняетсяВыполняется"]
[22,"TSK_5031742  «  INC_23863579",null,null,null,null,"ВФ ДК 7298 (Красногорское)",null,"2018-01-19",null,"—",null,"2018-02-18"]
[null,"От­сут­ствие внеш­них по­вре­жде­ний. Сле­дов ко­па­ти. Це­лост­ность кор­пу­са",null,null,null,null,null,null,"15:55:00",null,null,null,"15:55:00"]
[null,"НазначенаВыполняется"]
[23,"TSK_5030688  «  INC_23860729",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2018-01-19",null,"—",null,"2018-02-16"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"13:32:00",null,null,null,"13:32:00"]
[null,"ВыполняетсяВыполняется"]
[24,"TSK_5030616  «  INC_23860474",null,null,null,null,"ВФ ДК 6800 (НЧ)",null,"2018-01-19",null,"—",null,"2018-01-27"]
[null,"На­гре­ва­ют­ся в ра­бо­чем ре­жи­ме",null,null,null,null,null,null,"13:20:00",null,null,null,"13:20:00"]
[null,"ВыполняетсяВыполняется"]
[25,"TSK_5030351  «  INC_23859881",null,null,null,null,"ВФ ДК 6794 (НЧ)",null,"2018-01-19",null,"—",null,"2018-02-16"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"12:52:00",null,null,null,"12:52:00"]
[null,"ВыполняетсяВыполняется"]
[26,"TSK_5030383  «  INC_23859862",null,null,null,null,"ВФ ДК 6794 (НЧ)",null,"2018-01-19",null,"—",null,"2018-01-25"]
[null,"Течет в ме­стах со­еди­не­ния и под­во­да воды, на­ру­ше­на про­клад­ка.",null,null,null,null,null,null,"12:51:00",null,null,null,"12:51:00"]
[null,"ВыполняетсяВыполняется"]
[27,"TSK_5030348  «  INC_23859878",null,null,null,null,"ВФ ДК 6794 (НЧ)",null,"2018-01-19",null,"—",null,"2018-02-16"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"12:50:00",null,null,null,"12:50:00"]
[null,"ВыполняетсяВыполняется"]
[28,"TSK_5030366  «  INC_23859795",null,null,null,null,"ВФ ДК 6794 (НЧ)",null,"2018-01-19",null,"—",null,"2018-01-25"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"12:50:00",null,null,null,"12:50:00"]
[null,"ВыполняетсяВыполняется"]
[29,"TSK_5030357  «  INC_23859806",null,null,null,null,"ВФ ДК 6794 (НЧ)",null,"2018-01-19",null,"—",null,"2018-03-16"]
[null,"По­вре­жде­ние ме­тал­ло­кон­струк­ции по­руч­ней(ме­ха­ни­че­ское, ко­ро­зия ме­тел­ла)",null,null,null,null,null,null,"12:49:00",null,null,null,"12:49:00"]
[null,"ВыполняетсяВыполняется"]
[30,"TSK_5029941  «  INC_23858556",null,null,null,null,"ВФ ДК 7772 (НЧ)",null,"2018-01-19",null,"—",null,"2018-02-16"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"11:55:00",null,null,null,"11:55:00"]
[null,"ВыполняетсяВыполняется"]
[31,"TSK_5029540  «  INC_23857641",null,null,null,null,"ВФ ДК 7782 (НЧ)",null,"2018-01-19",null,"—",null,"2018-02-16"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"11:17:00",null,null,null,"11:17:00"]
[null,"ВыполняетсяВыполняется"]
[32,"TSK_5029570  «  INC_23857620",null,null,null,null,"ВФ ДК 7782 (НЧ)",null,"2018-01-19",null,"—",null,"2018-03-16"]
[null,"По­вре­жде­ние ме­тал­ло­кон­струк­ции по­руч­ней(ме­ха­ни­че­ское, ко­ро­зия ме­тел­ла)",null,null,null,null,null,null,"11:15:00",null,null,null,"11:15:00"]
[null,"ВыполняетсяВыполняется"]
[33,"TSK_5029345  «  INC_23856910",null,null,null,null,"ВФ ДК 6796 (НЧ)",null,"2018-01-19",null,"—",null,"2018-02-16"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"10:40:00",null,null,null,"10:40:00"]
[null,"ВыполняетсяВыполняется"]
[34,"TSK_5028589  «  INC_23854820",null,null,null,null,"ВФ ДК 7298 (Красногорское)",null,"2018-01-19",null,"2018-01-19",null,"2018-02-16"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"08:50:00",null,"08:54:00",null,"09:00:00"]
[null,"ВыполняетсяВыполняется"]
[35,"TSK_5026885  «  INC_23849564",null,null,null,null,"ВФ ДК 1596 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"16:19:00",null,null,null,"16:19:00"]
[null,"ВыполняетсяВыполняется"]
[36,"TSK_5026854  «  INC_23849513",null,null,null,null,"ВФ ДК 1596 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"16:13:00",null,null,null,"16:13:00"]
[null,"ВыполняетсяВыполняется"]
[37,"TSK_5026852  «  INC_23849511",null,null,null,null,"ВФ ДК 1596 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"16:13:00",null,null,null,"16:13:00"]
[null,"ВыполняетсяВыполняется"]
[38,"TSK_5026080  «  INC_23847444",null,null,null,null,"ВФ ДК 6796 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"14:32:00",null,null,null,"14:32:00"]
[null,"ВыполняетсяВыполняется"]
[39,"TSK_5025776  «  INC_23846587",null,null,null,null,"ВФ ДК 6796 (НЧ)",null,"2018-01-18",null,"—",null,"2018-01-24"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"13:54:00",null,null,null,"13:54:00"]
[null,"ВыполняетсяВыполняется"]
[40,"TSK_5025559  «  INC_23846017",null,null,null,null,"ВФ ДК 6801 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"13:27:00",null,null,null,"13:27:00"]
[null,"ВыполняетсяВыполняется"]
[41,"TSK_5025135  «  INC_23844973",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"12:36:00",null,null,null,"12:36:00"]
[null,"ВыполняетсяВыполняется"]
[42,"TSK_5025125  «  INC_23844934",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"12:33:00",null,null,null,"12:33:00"]
[null,"ВыполняетсяВыполняется"]
[43,"TSK_5025120  «  INC_23844929",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-18",null,"—",null,"2018-01-26"]
[null,"На­гре­ва­ют­ся в ра­бо­чем ре­жи­ме",null,null,null,null,null,null,"12:31:00",null,null,null,"12:31:00"]
[null,"ВыполняетсяВыполняется"]
[44,"TSK_5025116  «  INC_23844875",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-18",null,"—",null,"2018-01-21"]
[null,"Треск и ис­кре­ние в све­тиль­ни­ках в ра­бо­чем ре­жи­ме",null,null,null,null,null,null,"12:30:00",null,null,null,"12:30:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[45,"TSK_5024625  «  INC_23843382",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-15"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"11:17:00",null,null,null,"11:17:00"]
[null,"ВыполняетсяВыполняется"]
[46,"TSK_5024318  «  INC_23842515",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-18",null,"—",null,"2018-03-15"]
[null,"На­ру­ше­но кра­соч­ное по­кры­тие по­руч­ней",null,null,null,null,null,null,"10:38:00",null,null,null,"10:38:00"]
[null,"ВыполняетсяВыполняется"]
[47,"TSK_5024309  «  INC_23842475",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-18",null,"—",null,"2018-02-17"]
[null,"От­сут­ствие внеш­них по­вре­жде­ний. Сле­дов ко­па­ти. Це­лост­ность кор­пу­са",null,null,null,null,null,null,"10:37:00",null,null,null,"10:37:00"]
[null,"ВыполняетсяВыполняется"]
[48,"TSK_5024255  «  INC_23842334",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-18",null,"—",null,"2018-01-24"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"10:26:00",null,null,null,"10:26:00"]
[null,"ВыполняетсяВыполняется"]
[49,"TSK_5023482  «  INC_23840085",null,null,null,null,"ВФ ДК 9181 (Глазов)",null,"2018-01-18",null,"2018-01-18",null,"2018-02-15"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"08:04:00",null,"08:56:00",null,"09:00:00"]
[null,"ВыполняетсяВыполняется"]
[50,"TSK_5022808  «  INC_23837763",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-16"]
[null,"От­сут­ствие внеш­них по­вре­жде­ний. Сле­дов ко­па­ти. Це­лост­ность кор­пу­са",null,null,null,null,null,null,"18:56:00",null,null,null,"18:56:00"]
[null,"ВыполняетсяВыполняется"]
[51,"TSK_5022665  «  INC_23837280",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-06"]
[null,"Сло­ма­на крыш­ка кон­тей­не­ра",null,null,null,null,null,null,"18:10:00",null,null,null,"18:10:00"]
[null,"ВыполняетсяВыполняется"]
[52,"TSK_5022651  «  INC_23837187",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-20"]
[null,"На­ли­чие пыли, по­сто­рон­них пред­ме­тов, не ис­прав­ные замки или их от­сут­ствие на шка­фах",null,null,null,null,null,null,"18:10:00",null,null,null,"18:10:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[53,"TSK_5022641  «  INC_23837176",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"18:09:00",null,null,null,"18:09:00"]
[null,"ВыполняетсяВыполняется"]
[54,"TSK_5022650  «  INC_23837186",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"18:09:00",null,null,null,"18:09:00"]
[null,"ВыполняетсяВыполняется"]
[55,"TSK_5022656  «  INC_23837216",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-03-14"]
[null,"На­ру­ше­но кра­соч­ное по­кры­тие по­руч­ней",null,null,null,null,null,null,"18:08:00",null,null,null,"18:08:00"]
[null,"ВыполняетсяВыполняется"]
[56,"TSK_5022653  «  INC_23837211",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"18:07:00",null,null,null,"18:07:00"]
[null,"ВыполняетсяВыполняется"]
[57,"TSK_5022648  «  INC_23837184",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Тре­бу­ет­ся за­ме­на во­до­сто­ка, во­до­сток от­сут­ству­ет - тре­бу­ет­ся уста­нов­ка во­до­сто­ка",null,null,null,null,null,null,"18:06:00",null,null,null,"18:06:00"]
[null,"ВыполняетсяВыполняется"]
[58,"TSK_5022591  «  INC_23837209",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"18:05:00",null,null,null,"18:05:00"]
[null,"ВыполняетсяВыполняется"]
[59,"TSK_5022588  «  INC_23837036",null,null,null,null,"ВФ ДК 1577 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"18:04:00",null,null,null,"18:04:00"]
[null,"ВыполняетсяВыполняется"]
[60,"TSK_5021468  «  INC_23833135",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-25"]
[null,"На­гре­ва­ют­ся в ра­бо­чем ре­жи­ме",null,null,null,null,null,null,"14:26:00",null,null,null,"14:26:00"]
[null,"ВыполняетсяВыполняется"]
[61,"TSK_5021428  «  INC_23833036",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-23"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"14:25:00",null,null,null,"14:25:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"через 1ч. 56м."]
[62,"TSK_5021463  «  INC_23833130",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-23"]
[null,"Течет в ме­стах со­еди­не­ния и под­во­да воды, на­ру­ше­на про­клад­ка.",null,null,null,null,null,null,"14:24:00",null,null,null,"14:24:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"через 1ч. 55м."]
[63,"TSK_5021441  «  INC_23833086",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-16"]
[null,"От­сут­ствие внеш­них по­вре­жде­ний. Сле­дов ко­па­ти. Це­лост­ность кор­пу­са",null,null,null,null,null,null,"14:23:00",null,null,null,"14:23:00"]
[null,"ВыполняетсяВыполняется"]
[64,"TSK_5021433  «  INC_23833078",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"14:21:00",null,null,null,"14:21:00"]
[null,"ВыполняетсяВыполняется"]
[65,"TSK_5021419  «  INC_23833024",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"14:19:00",null,null,null,"14:19:00"]
[null,"ВыполняетсяВыполняется"]
[66,"TSK_5021398  «  INC_23832956",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"14:17:00",null,null,null,"14:17:00"]
[null,"ВыполняетсяВыполняется"]
[67,"TSK_5021387  «  INC_23832914",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Ме­ха­ни­че­ское по­вре­жде­ние двери (де­фор­ми­ро­ва­на, сло­ма­ны петли)",null,null,null,null,null,null,"14:13:00",null,null,null,"14:13:00"]
[null,"ВыполняетсяВыполняется"]
[68,"TSK_5021347  «  INC_23832843",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-03-14"]
[null,"По­вре­жде­ние ме­тал­ло­кон­струк­ции по­руч­ней(ме­ха­ни­че­ское, ко­ро­зия ме­тел­ла)",null,null,null,null,null,null,"14:12:00",null,null,null,"14:12:00"]
[null,"ВыполняетсяВыполняется"]
[69,"TSK_5021338  «  INC_23832834",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"14:11:00",null,null,null,"14:11:00"]
[null,"ВыполняетсяВыполняется"]
[70,"TSK_5021337  «  INC_23832833",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"14:10:00",null,null,null,"14:10:00"]
[null,"ВыполняетсяВыполняется"]
[71,"TSK_5020893  «  INC_23831075",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-24"]
[null,"Засор ра­ко­вин или моек",null,null,null,null,null,null,"13:07:00",null,null,null,"13:07:00"]
[null,"ВыполняетсяВыполняется"]
[72,"TSK_5020771  «  INC_23830681",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"12:54:00",null,null,null,"12:54:00"]
[null,"ВыполняетсяВыполняется"]
[73,"TSK_5020782  «  INC_23830626",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"12:53:00",null,null,null,"12:53:00"]
[null,"ВыполняетсяВыполняется"]
[74,"TSK_5020772  «  INC_23830649",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-20"]
[null,"На­ли­чие пыли, по­сто­рон­них пред­ме­тов, не ис­прав­ные замки или их от­сут­ствие на шка­фах",null,null,null,null,null,null,"12:52:00",null,null,null,"12:52:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[75,"TSK_5020738  «  INC_23830515",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"12:51:00",null,null,null,"12:51:00"]
[null,"ВыполняетсяВыполняется"]
[76,"TSK_5020765  «  INC_23830593",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"12:50:00",null,null,null,"12:50:00"]
[null,"ВыполняетсяВыполняется"]
[77,"TSK_5020710  «  INC_23830588",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"12:49:00",null,null,null,"12:49:00"]
[null,"ВыполняетсяВыполняется"]
[78,"TSK_5019684  «  INC_23827210",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"10:35:00",null,null,null,"10:35:00"]
[null,"ВыполняетсяВыполняется"]
[79,"TSK_5019682  «  INC_23827208",null,null,null,null,"ВФ ДК 5122 (НЧ)",null,"2018-01-17",null,"—",null,"2018-02-14"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"10:35:00",null,null,null,"10:35:00"]
[null,"ВыполняетсяВыполняется"]
[80,"TSK_5019590  «  INC_23826955",null,null,null,null,"ВФ ДК 5122 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-23"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"10:24:00",null,null,null,"10:24:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"2ч. 5м. назад"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[81,"TSK_5019478  «  INC_23826613",null,null,null,null,"ВФ ДК 3614 (НЧ)",null,"2018-01-17",null,"—",null,"2018-01-23"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"10:11:00",null,null,null,"10:11:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"2ч. 18м. назад"]
[]
[null,null,null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[82,"TSK_5019477  «  INC_23826612",null,null,null,null,"ВФ ДК 5689 (Яр)",null,"2018-01-17",null,"2018-01-18",null,"2018-02-14"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"10:10:00",null,"09:00:00",null,"10:10:00"]
[null,"ВыполняетсяВыполняется"]
[83,"TSK_5017198  «  INC_23809733",null,null,null,null,"ВФ ДК 3615 (НЧ)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"16:02:00",null,null,null,"16:02:00"]
[null,"ВыполняетсяВыполняется"]
[84,"TSK_5015887  «  INC_23805097",null,null,null,null,"ВФ ДК 3612 (НЧ)",null,"2018-01-16",null,"—",null,"2018-03-13"]
[null,"На­ру­ше­но кра­соч­ное по­кры­тие по­руч­ней",null,null,null,null,null,null,"13:10:00",null,null,null,"13:10:00"]
[null,"ВыполняетсяВыполняется"]
[85,"TSK_5015826  «  INC_23804808",null,null,null,null,"ВФ ДК 3612 (НЧ)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"13:03:00",null,null,null,"13:03:00"]
[null,"ВыполняетсяВыполняется"]
[86,"TSK_5015807  «  INC_23804723",null,null,null,null,"ВФ ДК 3612 (НЧ)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"13:02:00",null,null,null,"13:02:00"]
[null,"ВыполняетсяВыполняется"]
[87,"TSK_5015784  «  INC_23804542",null,null,null,null,"ВФ ДК 3612 (НЧ)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"12:57:00",null,null,null,"12:57:00"]
[null,"ВыполняетсяВыполняется"]
[88,"TSK_5014362  «  INC_23800359",null,null,null,null,"ВФ ДК 7874 (Мензелинск)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"10:08:00",null,null,null,"10:08:00"]
[null,"ВыполняетсяВыполняется"]
[89,"TSK_5014348  «  INC_23800314",null,null,null,null,"ВФ ДК 7874 (Мензелинск)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"10:07:00",null,null,null,"10:07:00"]
[null,"ВыполняетсяВыполняется"]
[90,"TSK_5014296  «  INC_23800076",null,null,null,null,"ВФ ДК 7874 (Мензелинск)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"09:56:00",null,null,null,"09:56:00"]
[null,"ВыполняетсяВыполняется"]
[91,"TSK_5014200  «  INC_23799967",null,null,null,null,"ВФ ДК 7874 (Мензелинск)",null,"2018-01-16",null,"—",null,"2018-02-13"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"09:51:00",null,null,null,"09:51:00"]
[null,"ВыполняетсяВыполняется"]
[92,"TSK_5012575  «  INC_23794506",null,null,null,null,"ВФ ДК 1583 (Мензелинск)",null,"2018-01-15",null,"—",null,"2018-02-12"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"16:55:00",null,null,null,"16:55:00"]
[null,"ВыполняетсяВыполняется"]
[93,"TSK_5012546  «  INC_23794494",null,null,null,null,"ВФ ДК 1583 (Мензелинск)",null,"2018-01-15",null,"—",null,"2018-02-12"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"16:54:00",null,null,null,"16:54:00"]
[null,"ВыполняетсяВыполняется"]
[94,"TSK_5010193  «  INC_23787609",null,null,null,null,"ВФ ДК 7971 (Глазов)",null,"2018-01-15",null,"2018-01-16",null,"2018-02-12"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"11:09:00",null,"08:31:00",null,"11:09:00"]
[null,"ВыполняетсяВыполняется"]
[95,"TSK_5010106  «  INC_23787332",null,null,null,null,"ВФ ДК 6114 (Ижевск)",null,"2018-01-15",null,"2018-01-16",null,"2018-02-12"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"10:58:00",null,"08:32:00",null,"10:58:00"]
[null,"ВыполняетсяВыполняется"]
[96,"TSK_5009642  «  INC_23785840",null,null,null,null,"ВФ ДК 6511 (Ижевск)",null,"2018-01-15",null,"2018-01-15",null,"2018-02-12"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"09:52:00",null,"10:00:00",null,"09:52:00"]
[null,"ВыполняетсяВыполняется"]
[97,"TSK_5009395  «  INC_23785102",null,null,null,null,"ВФ ДК 1515 (Ижевск)",null,"2018-01-15",null,"2018-01-15",null,"2018-02-12"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"09:16:00",null,"09:47:00",null,"09:16:00"]
[null,"ВыполняетсяВыполняется"]
[98,"TSK_5009008  «  INC_23783997",null,null,null,null,"ВФ ДК 5689 (Яр)",null,"2018-01-15",null,"2018-01-15",null,"2018-02-12"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"07:31:00",null,"08:20:00",null,"09:00:00"]
[null,"ВыполняетсяВыполняется"]
[99,"TSK_5009006  «  INC_23783995",null,null,null,null,"ВФ ДК 5689 (Яр)",null,"2018-01-15",null,"2018-01-15",null,"2018-02-12"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"07:30:00",null,"08:21:00",null,"09:00:00"]
[null,"ВыполняетсяВыполняется"]
[100,"TSK_5006758  «  INC_23776204",null,null,null,null,"ВФ ДК 3863 (Дебесы)",null,"2018-01-13",null,"2018-01-15",null,"2018-02-10"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"18:27:00",null,"08:23:00",null,"18:27:00"]
[null,"ВыполняетсяВыполняется"]
[101,"TSK_5005167  «  INC_23771257",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-13",null,"—",null,"2018-02-02"]
[null,"Сло­ма­на крыш­ка кон­тей­не­ра",null,null,null,null,null,null,"09:07:00",null,null,null,"09:07:00"]
[null,"ВыполняетсяВыполняется"]
[102,"TSK_5005140  «  INC_23771291",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2018-01-13",null,"—",null,"2018-02-10"]
[null,"Сло­ман замок, от­сут­ству­ет ключ",null,null,null,null,null,null,"09:01:00",null,null,null,"09:01:00"]
[null,"ВыполняетсяВыполняется"]
[103,"TSK_5003626  «  INC_23766343",null,null,null,null,"ВФ ДК 1580 (НЧ)",null,"2018-01-12",null,"—",null,"2018-02-09"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"15:57:00",null,null,null,"15:57:00"]
[null,"ВыполняетсяВыполняется"]
[104,"TSK_5001866  «  INC_23761375",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2018-01-12",null,"—",null,"2018-03-09"]
[null,"На­ру­ше­но кра­соч­ное по­кры­тие по­руч­ней",null,null,null,null,null,null,"11:53:00",null,null,null,"11:53:00"]
[null,"ВыполняетсяВыполняется"]
[105,"TSK_5001572  «  INC_23760562",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2018-01-12",null,"—",null,"2018-02-09"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"11:12:00",null,null,null,"11:12:00"]
[null,"ВыполняетсяВыполняется"]
[106,"TSK_5001457  «  INC_23760329",null,null,null,null,"ВФ ДК 6686 (Ижевск)",null,"2018-01-12",null,"2018-01-15",null,"2018-02-09"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"11:01:00",null,"08:45:00",null,"11:01:00"]
[null,"ВыполняетсяВыполняется"]
[107,"TSK_4998339  «  INC_23750768",null,null,null,null,"ВФ ДК 6800 (НЧ)",null,"2018-01-11",null,"—",null,"2018-02-08"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"15:00:00",null,null,null,"15:00:00"]
[null,"ВыполняетсяВыполняется"]
[108,"TSK_4998217  «  INC_23750494",null,null,null,null,"ВФ ДК 6800 (НЧ)",null,"2018-01-11",null,"—",null,"2018-02-08"]
[null,"На­блю­да­ют­ся про­теч­ки (кол-во, как силь­но течет) в ТЗ , в П.П., на глав­ной кассе, на де­бар­ка­де­ре",null,null,null,null,null,null,"14:48:00",null,null,null,"14:48:00"]
[null,"ВыполняетсяВыполняется"]
[109,"TSK_4998209  «  INC_23750437",null,null,null,null,"ВФ ДК 6800 (НЧ)",null,"2018-01-11",null,"—",null,"2018-01-17"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"14:46:00",null,null,null,"14:46:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[110,"TSK_4996354  «  INC_23745496",null,null,null,null,"ВФ ДК 1663 (Ижевск)",null,"2018-01-11",null,"2018-01-12",null,"2018-02-08"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"10:59:00",null,"09:52:00",null,"10:59:00"]
[null,"ВыполняетсяВыполняется"]
[111,"TSK_4996008  «  INC_23744591",null,null,null,null,"ВФ ДК 3613 (НЧ)",null,"2018-01-11",null,"—",null,"2018-02-10"]
[null,"От­сут­ствие внеш­них по­вре­жде­ний. Сле­дов ко­па­ти. Це­лост­ность кор­пу­са",null,null,null,null,null,null,"10:18:00",null,null,null,"10:18:00"]
[null,"ВыполняетсяВыполняется"]
[112,"TSK_4992397  «  INC_23732941",null,null,null,null,"ВФ ДК 5093 (Набережные Челны)",null,"2018-01-10",null,"—",null,"2018-02-07"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"12:17:00",null,null,null,"12:17:00"]
[null,"ВыполняетсяВыполняется"]
[113,"TSK_4992311  «  INC_23732662",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2018-01-10",null,"—",null,"2018-02-07"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"12:07:00",null,null,null,"12:07:00"]
[null,"ВыполняетсяВыполняется"]
[114,"TSK_4991496  «  INC_23730279",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2018-01-10",null,"—",null,"2018-01-16"]
[null,"Течет в ме­стах со­еди­не­ния и под­во­да воды, на­ру­ше­на про­клад­ка.",null,null,null,null,null,null,"10:14:00",null,null,null,"10:14:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[115,"TSK_4990718  «  INC_23727912",null,null,null,null,"ВФ ДК 5254 (Балезино)",null,"2018-01-10",null,"2018-01-12",null,"2018-02-07"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"07:53:00",null,"09:56:00",null,"09:00:00"]
[null,"ВыполняетсяВыполняется"]
[116,"TSK_4989669  «  INC_23724046",null,null,null,null,"ВФ ДК 4542 (Глазов)",null,"2018-01-09",null,"2018-01-12",null,"2018-02-06"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"16:40:00",null,"09:57:00",null,"16:40:00"]
[null,"ВыполняетсяВыполняется"]
[117,"TSK_4988006  «  INC_23719396",null,null,null,null,"ВФ ДК 5238 (НЧ)",null,"2018-01-09",null,"—",null,"2018-02-06"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"12:51:00",null,null,null,"12:51:00"]
[null,"ВыполняетсяВыполняется"]
[118,"TSK_4986874  «  INC_23716480",null,null,null,null,"ВФ ДК 7874 (Мензелинск)",null,"2018-01-09",null,"—",null,"2018-02-06"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"10:45:00",null,null,null,"10:45:00"]
[null,"ВыполняетсяВыполняется"]
[119,"TSK_4983633  «  INC_23706955",null,null,null,null,"ВФ ДК 7772 (НЧ)",null,"2018-01-08",null,"—",null,"2018-01-14"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"10:44:00",null,null,null,"10:44:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[120,"TSK_4979135  «  INC_23691711",null,null,null,null,"ВФ ДК 5689 (Яр)",null,"2018-01-05",null,"2018-01-09",null,"2018-02-02"]
[null,"Ме­ха­ни­че­ское по­вре­жде­ние двери (де­фор­ми­ро­ва­на, сло­ма­ны петли)",null,null,null,null,null,null,"16:43:00",null,"14:39:00",null,"16:43:00"]
[null,"ВыполняетсяВыполняется"]
[121,"TSK_4971171  «  INC_23663007",null,null,null,null,"ВФ ДК 4010 (НЧ)",null,"2017-12-31",null,"—",null,"2018-01-28"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"18:18:00",null,null,null,"18:18:00"]
[null,"ВыполняетсяВыполняется"]
[122,"TSK_4967079  «  INC_23646516",null,null,null,null,"ВФ ДК 6796 (НЧ)",null,"2017-12-29",null,"—",null,"2018-01-26"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"12:19:00",null,null,null,"12:19:00"]
[null,"ВыполняетсяВыполняется"]
[123,"TSK_4967032  «  INC_23646313",null,null,null,null,"ВФ ДК 6796 (НЧ)",null,"2017-12-29",null,"—",null,"2018-01-26"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"12:02:00",null,null,null,"12:02:00"]
[null,"ВыполняетсяВыполняется"]
[124,"TSK_4964516  «  INC_23637282",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2017-12-28",null,"—",null,"2018-01-25"]
[null,"Ме­ха­ни­че­ское по­вре­жде­ние двери (де­фор­ми­ро­ва­на, сло­ма­ны петли)",null,null,null,null,null,null,"15:03:00",null,null,null,"15:03:00"]
[null,"ВыполняетсяВыполняется"]
[125,"TSK_4960110  «  INC_23621901",null,null,null,null,"ВФ ДК 6801 (НЧ)",null,"2017-12-27",null,"—",null,"2018-01-24"]
[null,"На­блю­да­ют­ся про­теч­ки (кол-во, как силь­но течет) в ТЗ , в П.П., на глав­ной кассе, на де­бар­ка­де­ре",null,null,null,null,null,null,"12:17:00",null,null,null,"12:17:00"]
[null,"ВыполняетсяВыполняется"]
[126,"TSK_4959410  «  INC_23619415",null,null,null,null,"ВФ ДК 5238 (НЧ)",null,"2017-12-27",null,"—",null,"2018-01-24"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"09:53:00",null,null,null,"09:53:00"]
[null,"ВыполняетсяВыполняется"]
[127,"TSK_4959399  «  INC_23619388",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2017-12-27",null,"—",null,"2018-01-24"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"09:49:00",null,null,null,"09:49:00"]
[null,"ВыполняетсяВыполняется"]
[128,"TSK_4957768  «  INC_23612966",null,null,null,null,"ВФ ДК 1578 (НЧ)",null,"2017-12-26",null,"—",null,"2018-01-23"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"16:02:00",null,null,null,"16:02:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"через 3ч. 33м."]
[129,"TSK_4943986  «  INC_23566680",null,null,null,null,"ВФ ДК 4048 (Набережные Челны)",null,"2017-12-22",null,"—",null,"2018-01-19"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"10:29:00",null,null,null,"10:29:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[130,"TSK_4942320  «  INC_23560495",null,null,null,null,"ВФ ДК 7047 (НЧ)",null,"2017-12-21",null,"—",null,"2018-01-18"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"17:17:00",null,null,null,"17:17:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[131,"TSK_4941828  «  INC_23558976",null,null,null,null,"ВФ ДК 3614 (НЧ)",null,"2017-12-21",null,"—",null,"2018-01-18"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"15:53:00",null,null,null,"15:53:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[132,"TSK_4939306  «  INC_23551223",null,null,null,null,"ВФ ДК 1580 (НЧ)",null,"2017-12-21",null,"—",null,"2017-12-27"]
[null,"Сло­ма­ны петли, про­се­ла пра­вая сто­ро­на ворот, де­фор­ми­ро­ва­на левая сто­ро­на ворот",null,null,null,null,null,null,"09:31:00",null,null,null,"09:31:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[133,"TSK_4937836  «  INC_23546064",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2017-12-20",null,"—",null,"2018-01-17"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"17:31:00",null,null,null,"17:31:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[134,"TSK_4929908  «  INC_23518115",null,null,null,null,"ВФ ДК 1580 (НЧ)",null,"2017-12-19",null,"—",null,"2017-12-25"]
[null,"Течет в ме­стах со­еди­не­ния и под­во­да воды, на­ру­ше­на про­клад­ка.",null,null,null,null,null,null,"09:28:00",null,null,null,"09:28:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[135,"TSK_4928267  «  INC_23512073",null,null,null,null,"ВФ ДК 6963 (НЧ)",null,"2017-12-18",null,"—",null,"2018-01-15"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"16:27:00",null,null,null,"16:27:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[136,"TSK_4928095  «  INC_23511451",null,null,null,null,"ВФ ДК 6963 (НЧ)",null,"2017-12-18",null,"—",null,"2018-01-15"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"16:00:00",null,null,null,"16:00:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[137,"TSK_4928005  «  INC_23511201",null,null,null,null,"ВФ ДК 6963 (НЧ)",null,"2017-12-18",null,"—",null,"2018-02-12"]
[null,"Раз­ру­ше­но пли­точ­ное по­кры­тие (лест­ни­цы, пло­щад­ки, пан­ду­са)",null,null,null,null,null,null,"15:46:00",null,null,null,"15:46:00"]
[null,"ВыполняетсяВыполняется"]
[138,"TSK_4925912  «  INC_23504543",null,null,null,null,"ВФ ДК 6801 (НЧ)",null,"2017-12-18",null,"—",null,"2018-02-07"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"11:07:00",null,null,null,"11:03:00"]
[null,"ВыполняетсяВыполняется"]
[139,"TSK_4918914  «  INC_23479123",null,null,null,null,"ВФ ДК 5093 (Набережные Челны)",null,"2017-12-15",null,"—",null,"2018-01-12"]
[null,"За­ме­на \"кол-во\" пли­ток по­тол­ка, за­ме­на на­прав­ля­ю­щих под­вис­но­го по­тол­ка",null,null,null,null,null,null,"14:47:00",null,null,null,"15:16:00"]
[null,"ВыполняетсяВыполняется"]
[140,"TSK_4917926  «  INC_23476262",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2017-12-15",null,"—",null,"2018-01-12"]
[null,"Вы­па­ла рама, ото­рва­лась петля",null,null,null,null,null,null,"12:29:00",null,null,null,"12:29:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[141,"TSK_4917575  «  INC_23474904",null,null,null,null,"ВФ ДК 7772 (НЧ)",null,"2017-12-15",null,"—",null,"2018-02-02"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"11:27:00",null,null,null,"11:02:00"]
[null,"ВыполняетсяВыполняется"]
[142,"TSK_4917287  «  INC_23474144",null,null,null,null,"ВФ ДК 7020 (НЧ)",null,"2017-12-15",null,"—",null,"2018-02-02"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"10:48:00",null,null,null,"10:24:00"]
[null,"ВыполняетсяВыполняется"]
[143,"TSK_4913418  «  INC_23462086",null,null,null,null,"ВФ ДК 3521 (Балезино)",null,"2017-12-14",null,"2017-12-18",null,"2017-12-20"]
[null,"Ба­та­реи про­гре­ва­ют­ся нерав­но­мер­но (по­ло­ви­на ба­та­реи хо­лод­ная, по­ло­ви­на тёп­лая)",null,null,null,null,null,null,"12:43:00",null,"08:38:00",null,"12:43:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[144,"TSK_4912769  «  INC_23460307",null,null,null,null,"ВФ ДК 6803 (НЧ)",null,"2017-12-14",null,"—",null,"2018-02-01"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"11:28:00",null,null,null,"10:56:00"]
[null,"ВыполняетсяВыполняется"]
[145,"TSK_4912329  «  INC_23459156",null,null,null,null,"ВФ ДК 1580 (НЧ)",null,"2017-12-14",null,"—",null,"2018-02-01"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"10:34:00",null,null,null,"10:03:00"]
[null,"ВыполняетсяВыполняется"]
[146,"TSK_4912216  «  INC_23458803",null,null,null,null,"ВФ ДК 3612 (НЧ)",null,"2017-12-14",null,"—",null,"2017-12-18"]
[null,"Не горит осве­ще­ние при вклю­че­нии тум­бле­ра",null,null,null,null,null,null,"10:17:00",null,null,null,"10:17:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[147,"TSK_4910382  «  INC_23453360",null,null,null,null,"ВФ ДК 6797 (НЧ)",null,"2017-12-13",null,"—",null,"2018-01-29"]
[null,"Яма в полу, за­ме­на ли­но­ли­у­ма, за­ме­на плит­ки в ТЗ \"кол-во\"",null,null,null,null,null,null,"17:43:00",null,null,null,"17:49:00"]
[null,"ВыполняетсяВыполняется"]
[148,"TSK_4907061  «  INC_23443254",null,null,null,null,"ВФ ДК 1587 (НЧ)",null,"2017-12-13",null,"—",null,"2018-01-28"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"09:28:00",null,null,null,"10:17:00"]
[null,"ВыполняетсяВыполняется"]
[149,"TSK_4904785  «  INC_23435567",null,null,null,null,"ВФ ДК 6794 (НЧ)",null,"2017-12-12",null,"—",null,"2018-01-22"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"14:26:00",null,null,null,"14:50:00"]
[null,"ВыполняетсяВыполняется"]
[150,"TSK_4903103  «  INC_23430846",null,null,null,null,"ВФ ДК 1579 (НЧ)",null,"2017-12-12",null,"—",null,"2018-01-21"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"10:53:00",null,null,null,"10:10:00"]
[null,"ВыполняетсяВыполняется"]
[151,"TSK_4891239  «  INC_23393029",null,null,null,null,"ВФ ДК 1583 (Мензелинск)",null,"2017-12-08",null,"—",null,"2018-01-05"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"13:36:00",null,null,null,"13:36:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[152,"TSK_4877204  «  INC_23348022",null,null,null,null,"ВФ ДК 1579 (НЧ)",null,"2017-12-05",null,"—",null,"2018-01-14"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"14:16:00",null,null,null,"13:05:00"]
[null,"ВыполняетсяВыполняется"]
[153,"TSK_4876104  «  INC_23344930",null,null,null,null,"ВФ ДК 4048 (Набережные Челны)",null,"2017-12-05",null,"—",null,"2018-01-13"]
[null,"Тре­бу­ет­ся по­крас­ка стены (м2), тре­бу­ет­ся об­шить стену гип­со­кар­то­ном (м2)",null,null,null,null,null,null,"11:58:00",null,null,null,"19:21:00"]
[null,"ВыполняетсяВыполняется"]
[154,"TSK_4862819  «  INC_23298224",null,null,null,null,"ВФ ДК 6802 (НЧ)",null,"2017-12-01",null,"—",null,"2017-12-29"]
[null,"Не горят лампы в све­тиль­ни­ках",null,null,null,null,null,null,"12:03:00",null,null,null,"12:03:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[155,"TSK_4751647  «  INC_22906747",null,null,null,null,"ВФ ДК 6511 (Ижевск)",null,"2017-11-01",null,"2017-11-02",null,"2017-11-29"]
[null,"На­блю­да­ют­ся про­теч­ки (кол-во, как силь­но течет) в ТЗ , в П.П., на глав­ной кассе, на де­бар­ка­де­ре",null,null,null,null,null,null,"17:41:00",null,"09:25:00",null,"17:41:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]
[156,"TSK_4749421  «  INC_22899418",null,null,null,null,"ВФ ДК 1798 (Ижевск)",null,"2017-11-01",null,"2017-11-02",null,"2017-11-07"]
[null,"Несколь­ко ба­та­рей в ма­га­зине хо­лод­ные.",null,null,null,null,null,null,"11:49:00",null,"09:32:00",null,"11:49:00"]
[null,"ВыполняетсяВыполняется",null,null,null,null,null,null,null,null,null,null,"Просрочена"]

{"sheet":"Лист2","index":1,"n_rows":2,"n_cols":6,"rows_kept":2,"cut":false,"hidden":false,"merged":[]}
[]
["№п/п","№ заказа","Описание","№ магазина","Дата создания","Фактическая дата"]