## Sheet1
Site # | Principal Investigator | City | Approval | Monitor | Task | SQV | SIV | MV1 | MV2 | MV3 | MV4 | MV5 | MV6 | MV7 | MV8 | MV9 | MV10 | MV11 | COV | Total days of MV
N/A | N/A | N/A | N/A | N/A | Predicted Date | 2012-10-26 | 2012-12-27 | MV1: 2013-02-04; MV2: 2013-02-04
N/A | N/A | N/A | N/A | N/A | Actual visit first date | 2012-10-24 | 2012-12-27 | MV1: 2013-02-04; MV2: 2013-02-05
N/A | N/A | N/A | N/A | N/A | Actual visit last date | 2012-10-24 | 2012-12-27 | MV1: 2013-02-04; MV2: 2013-02-04
N/A | N/A | N/A | N/A | N/A | Report to PM | 2012-10-25 | 2013-01-14 | MV1: 2013-02-08; MV2: 2013-02-11
N/A | N/A | N/A | N/A | N/A | Report Finalised | 2012-10-26 | 2013-01-17 | MV1: 2013-02-11; MV2: 2013-02-12
N/A | N/A | N/A | N/A | N/A | Sent to sponsor | 2012-10-26 | 2013-01-17 | MV1: 2013-02-12; MV2: 2013-02-18
N/A | N/A | N/A | N/A | N/A | Gilead comments | 2012-10-29 |  | MV1: 2013-02-13; MV2: 2013-02-19
N/A | N/A | N/A | N/A | N/A | FN sent to Gilead | 2012-10-30 |  | MV1: 2013-02-14; MV2: 2013-02-20
N/A | N/A | N/A | N/A | N/A | number of days
N/A | N/A | N/A | N/A | N/A | additional two hours
N/A | N/A | N/A | N/A | N/A | Predicted Date | 2012-11-07 | 28Jan13-30Jan13 | MV1: 2013-02-04
N/A | N/A | N/A | N/A | N/A | Actual visit first date | 2012-11-13 |  | MV1: 2013-02-04
N/A | N/A | N/A | N/A | N/A | Actual visit last date | 2012-11-13 |  | MV1: 2013-02-04
N/A | N/A | N/A | N/A | N/A | Report to PM | 2012-11-21 |  | MV1: 2013-02-11
N/A | N/A | N/A | N/A | N/A | Report Finalised | 2012-11-22 |  | MV1: 2013-02-12
N/A | N/A | N/A | N/A | N/A | Sent to sponsor | 2012-11-22 |  | MV1: 2013-02-18
N/A | N/A | N/A | N/A | N/A | Gilead comments | 2012-11-29 |  | MV1: 2013-02-19
N/A | N/A | N/A | N/A | N/A | FN sent to Gilead | 03.12.2012/05.12.2012 |  | MV1: 2013-02-20
N/A | N/A | N/A | N/A | N/A | number of days
N/A | N/A | N/A | N/A | N/A | additional two hours
N/A | N/A | N/A | N/A | N/A | Predicted Date | 2012-10-24 | 2013-01-15
N/A | N/A | N/A | N/A | N/A | Actual visit first date | 2012-10-24 | 2013-01-15
N/A | N/A | N/A | N/A | N/A | Actual visit last date | 2012-10-24 | 2013-01-15
N/A | N/A | N/A | N/A | N/A | Report to PM | 2012-10-31 | 2013-01-23
N/A | N/A | N/A | N/A | N/A | Report Finalised | 2012-11-02
N/A | N/A | N/A | N/A | N/A | Sent to sponsor | 2012-11-02
N/A | N/A | N/A | N/A | N/A | Gilead comments | 2012-11-10
N/A | N/A | N/A | N/A | N/A | FN sent to Gilead | 2012-11-13
N/A | N/A | N/A | N/A | N/A | number of days
N/A | N/A | N/A | N/A | N/A | additional two hours
N/A | N/A | N/A | N/A | N/A | Predicted Date | 19-23.11.12 | 2013-01-16
N/A | N/A | N/A | N/A | N/A | Actual visit first date | 2012-11-21 | 2013-01-16
N/A | N/A | N/A | N/A | N/A | Actual visit last date | 2012-11-21 | 2013-01-16
N/A | N/A | N/A | N/A | N/A | Report to PM | 2012-11-27
N/A | N/A | N/A | N/A | N/A | Report Finalised | 2012-11-29
N/A | N/A | N/A | N/A | N/A | Sent to sponsor | 2012-11-29
N/A | N/A | N/A | N/A | N/A | Gilead comments | 2012-12-08
N/A | N/A | N/A | N/A | N/A | FN sent to Gilead | 2012-12-10
N/A | N/A | N/A | N/A | N/A | number of days
N/A | N/A | N/A | N/A | N/A | additional two hours
N/A | N/A | N/A | N/A | N/A | Predicted Date | 2012-11-01 | end of Feb 2013
N/A | N/A | N/A | N/A | N/A | Actual visit first date | 2012-11-01
N/A | N/A | N/A | N/A | N/A | Actual visit last date | 2012-11-01
N/A | N/A | N/A | N/A | N/A | Report to PM | 2012-11-06
N/A | N/A | N/A | N/A | N/A | Report Finalised | 2012-11-06
N/A | N/A | N/A | N/A | N/A | Sent to sponsor | 2012-11-06
N/A | N/A | N/A | N/A | N/A | Gilead comments | 2012-11-10
N/A | N/A | N/A | N/A | N/A | FN sent to Gilead | 2012-11-13
N/A | N/A | N/A | N/A | N/A | number of days
N/A | N/A | N/A | N/A | N/A | additional two hours
N/A | N/A | N/A | N/A | N/A | Predicted Date | 2012-11-08 | 2013-01-17
N/A | N/A | N/A | N/A | N/A | Actual visit first date | 2012-11-09 | 2013-01-17
N/A | N/A | N/A | N/A | N/A | Actual visit last date | 2012-11-09 | 2013-01-17
N/A | N/A | N/A | N/A | N/A | Report to PM | 2012-11-15
N/A | N/A | N/A | N/A | N/A | Report Finalised | 2012-11-16
N/A | N/A | N/A | N/A | N/A | Sent to sponsor | 2012-11-16
N/A | N/A | N/A | N/A | N/A | Gilead comments | 2012-11-20
N/A | N/A | N/A | N/A | N/A | FN sent to Gilead | 2012-11-22
N/A | N/A | N/A | N/A | N/A | number of days
N/A | N/A | N/A | N/A | N/A | additional two hours
N/A | N/A | N/A | N/A | N/A | Predicted Date | 19-20/11/12 | begin of Feb 2013
N/A | N/A | N/A | N/A | N/A | Actual visit first date | 2012-11-20
N/A | N/A | N/A | N/A | N/A | Actual visit last date | 2012-11-20

## Sheet3
Review summary | Total visits done | Out of Range Initial rpt | % deviation Initial rpt | Out of Range Review | % deviation Review |  | % deviation Sent to Santarus
Total visits | 2 | 0 | 0% | 0 | 0% | 0 | 0%
Qualification | 1 | 0 | 0% | 0 | 0% | 0 | 0%
Initiation | 1 | 0 | 0% | 0 | 0% | 0 | 0%
Mon visits | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Close out | 0 | 0 | #DIV/0! | 0 | #DIV/0! | 0 | #DIV/0!
Co-monitoring visit by PM | #REF! | NA | NA | NA | NA | NA | NA
[9 empty] | Site nr. | PI | Type | CRA name | MV Number | Actual visit first date | Actual Visit Last date | Co-monitoring visit by PM, date | Initial Rpt to Reviewer On | Rpt Finalized On | Submit To Sponsor On | Days visit to initial report | Days for report review | Days for report sent to Santarus
[8 empty] | 3 | N/A | N/A | Qualification | N/A | NA | #REF! | #REF! |  |  |  |  | #REF! | 0 | #REF!
[9 empty] | N/A | N/A | Initiation | N/A | NA | #REF! | #REF! |  |  |  |  | #REF! | 0 | #REF!
[9 empty] | N/A | N/A | Monitoring | N/A | 1 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 2 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 3 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 4 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 5 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 6 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 7 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 8 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 9 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 10 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 11 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Close out | N/A | NA | [6 empty] | 0 | 0 | 0
[8 empty] | 13 | N/A | N/A | Qualification | N/A | NA | #REF! | #REF! |  |  |  |  | #REF! | 0 | #REF!
[9 empty] | N/A | N/A | Initiation | N/A | NA | #REF! | #REF! |  |  |  |  | #REF! | 0 | #REF!
[9 empty] | N/A | N/A | Monitoring | N/A | 1 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 2 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 3 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 4 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 5 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 6 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 7 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 8 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 9 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 10 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 11 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Close out | N/A | NA | [6 empty] | 0 | 0 | 0
[8 empty] | 23 | N/A | N/A | Qualification | N/A | NA | 2012-10-24 | 2012-10-24 |  |  |  |  | -29433 | 0 | -29433
[9 empty] | N/A | N/A | Initiation | N/A | NA | 2013-01-15 | 2013-01-15 |  |  |  |  | -29492 | 0 | -29492
[9 empty] | N/A | N/A | Monitoring | N/A | 1 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 2 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 3 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 4 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 5 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 6 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 7 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 8 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 9 | [6 empty] | 0 | 0 | 0
[9 empty] | N/A | N/A | Monitoring | N/A | 10 | [6 empty] | 0 | 0 | 0
Formulas:
Days visit to initial report = NETWORKDAYS([Actual Visit Last date],[Initial Rpt to Reviewer On])
Days for report review = NETWORKDAYS([Initial Rpt to Reviewer On],[Rpt Finalized On])
Days for report sent to Santarus = NETWORKDAYS([Actual Visit Last date],[Submit To Sponsor On])