## GanttChart
| Project Start Date | 2018-09-24 |  |  |  | Display Week | 25 |  | Week 25 | [6 empty] | Week 26 | [6 empty] | Week 27 | [6 empty] | Week 28 | [6 empty] | Week 29 | [6 empty] | Week 30 | [6 empty] | Week 31 | [6 empty] | Week 32
| Project End Date | 2019-04-05 | [6 empty] | 2019-03-11 | [6 empty] | 2019-03-18 | [6 empty] | 2019-03-25 | [6 empty] | 2019-04-01 | [6 empty] | 2019-04-08 | [6 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29
 | time axis 2019-03-11 to 2019-05-05
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2019-03-11 to 2019-05-05
1 | 865 11kV/50Hz HV SWB (HVTF) |  |  |  | - |  |  | -
0.1 | DESIGN |  |  | 2018-10-08 | 2018-12-30 | 84 | 90% | #NAME?
0.1 | INSTALLATION |  |  | 2019-01-07 | 2019-03-07 | 60 | 0% | #NAME?
0.1 | EQUIPMENT DELIVERY |  |  | 2019-03-11 | 2019-03-11 | 1 | 0% | #NAME?
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
1 | 865 HVSC SUPPLY TRANSFORMER |  |  |  | - |  |  | -
0.1 | DESIGN |  |  | 2018-10-08 | 2018-12-30 | 84 | 0% | #NAME?
0.1 | INSTALLATION |  |  | 2019-01-07 | 2019-03-07 | 60 | 0% | #NAME?
0.1 | EQUIPMENT DELIVERY |  |  | 2019-01-04 | 2019-01-04 | 1 | 100% | #NAME?
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
1 | HV SHORE SUPPLY INTAKE CABINET |  |  |  | - |  |  | -
0.1 | DESIGN |  |  | 2018-10-08 | 2018-12-30 | 84 | 0% | #NAME?
0.1 | INSTALLATION |  |  | 2019-01-07 | 2019-03-07 | 60 | 0% | #NAME?
0.1 | EQUIPMENT DELIVERY |  |  | 2019-03-15 | 2019-03-15 | 1 | 0% | #NAME?
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
1 | S2S AUTOMATION SYSTEM |  |  |  | - |  |  | -
0.1 | DESIGN |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | #NAME?
0.1 | INSTALLATION |  |  | 2019-01-07 | 2019-03-07 | 60 | 0% | #NAME?
0.1 | EQUIPMENT DELIVERY |  |  |  | - |  | 0% | -
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
1 | SHIP CONTROL MONITORING SYS (PMS) |  |  |  | - |  |  | -
0.1 | DESIGN |  |  | 2018-11-15 | 2019-01-23 | 70 | 0% | #NAME?
0.1 | INSTALLATION |  |  | 2019-01-07 | 2019-03-07 | 60 | 0% | #NAME?
0.1 | EQUIPMENT DELIVERY |  |  | 2018-12-12 | 2018-12-12 | 1 | 100% | #NAME?
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
1 | SHIP MSB 690VAC MODIFICATION |  |  |  | - |  |  | -
0.1 | DESIGN |  |  | 2018-10-08 | 2018-12-30 | 84 | 100% | #NAME?
0.1 | INSTALLATION |  |  | 2019-01-07 | 2019-03-07 | 60 | 0% | #NAME?
0.1 | EQUIPMENT DELIVERY |  |  | 2018-01-31 | 2018-01-31 | 1 | 100% | #NAME?
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
1 | 881 CABLE TRAYS, MCT AND FITTINGS |  |  |  | - |  |  | -
0.1 | DESIGN |  |  | 2018-10-08 | 2018-12-30 | 84 | 0% | #NAME?
0.1 | INSTALLATION |  |  | 2018-11-03 | 2019-01-04 | 63 | 100% | #NAME?
0.1 | EQUIPMENT DELIVERY |  |  |  | - |  | 0% | -
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
1 | 261 BULKHEADS, DECK AND HULL CUTOUTS |  |  |  | - |  |  | -
0.1 | DESIGN |  |  |  | - | 1 | 0% | -
0.1 | INSTALLATION |  |  |  | - | 1 | 0% | -
0.1 | EQUIPMENT DELIVERY |  |  |  | - | 1 | 0% | -
0.1 | COMMISSIONING |  |  | 2019-03-22 | 2019-04-03 | 13 | 0% | #NAME?
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on E9: Darja Gavrish: 2 weeks from 24/09
Note on E10: Darja Gavrish: Dock start date
Note on E11: Darja Gavrish: Order confirmation
Note on E12: Darja Gavrish: 2 weeks prior to project end date
Note on E14: Darja Gavrish: 2 weeks from 24/09
Note on E15: Darja Gavrish: Dock start date
Note on E17: Darja Gavrish: 2 weeks prior to project end date
Note on E19: Darja Gavrish: 2 weeks from 24/09
Note on E20: Darja Gavrish: Dock start date
Note on E21: Darja Gavrish: Delivery date acc to order confirmation
Note on E22: Darja Gavrish: 2 weeks prior to project end date
Note on E25: Darja Gavrish: Dock start date
Note on E27: Darja Gavrish: 2 weeks prior to project end date
Note on E30: Darja Gavrish: Dock start date
Note on E32: Darja Gavrish: 2 weeks prior to project end date
Note on E34: Darja Gavrish: 2 weeks from 24/09
Note on E35: Darja Gavrish: Dock start date
Note on E37: Darja Gavrish: 2 weeks prior to project end date
Note on E39: Darja Gavrish: 2 weeks from 24/09
Note on E42: Darja Gavrish: 2 weeks prior to project end date
Note on E47: Darja Gavrish: 2 weeks prior to project end date
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on F9: Darja Gavrish: 12 weeks from 24/09
Note on F11: Darja Gavrish: 16 weeks from 20/11/2018
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.