{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Выдержка к регламенту от 11.19г","Лист1","Лист2"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Выдержка к регламенту от 11.19г","index":0,"n_rows":21,"n_cols":7,"rows_kept":21,"cut":false,"hidden":false,"merged":[[10,1,10,2],[0,1,0,6]]}
[null,"Экран ОУСП "]
[]
[null,null,null,"x"]
[null,null,null,"x",null,"x","x"]
[null,null,null,"x"]
[null,null,null,"x",null,"x","x"]
[]
[]
[]
[null,null,null,"x",null,"x","x"]
[]
[null,null,"СОСТАВЛЕН НА:",null,{"$f":"TODAY()","v":"2020-01-09"}]
[null,"Получение ПСД"]
[null,"№ п/п","Проект, акт на др., ДВ, тех. решение","Дата получения проекта от заказчика","Наименование работ","Директивный срок начала работ","Директивный срок завершения работ"]
[null,"1","2","3","4","5","6"]
[]
[null,{"$f":"IF(ISBLANK(C17),\"\",COUNTA(C$17:C17))","v":1},"1792.17-1-КЖ1 изм.1  \n1792.17-1-КЖ1 изм.2   \n1792.17-1-КЖ1 изм.3","изм 1 -акт от 15.01.2019  \n изм.2- акт от 12.02.2019г.\nИзм.3- акт от 15.02.2019 г.","Монолитные фундаменты ","2019-02-28","2019-08-25"]
[null,{"$f":"IF(ISBLANK(C18),\"\",COUNTA(C$17:C18))","v":2},"1792.17-1-КЖ1 изм.1  \n1792.17-1-КЖ1 изм.2   \n1792.17-1-КЖ1 изм.3","изм 1 -акт от 15.01.2019  \n изм.2- акт от 12.02.2019г.\nИзм.3- акт от 15.02.2019 г.","Монолитные фундаменты ","2019-02-28","2019-04-15"]
[null,{"$f":"IF(ISBLANK(C19),\"\",COUNTA(C$17:C19))","v":3},"1792.17-1-КЖ1 изм.1  \n1792.17-1-КЖ1 изм.2   \n1792.17-1-КЖ1 изм.3","изм 1 -акт от 15.01.2019  \n изм.2- акт от 12.02.2019г.\nИзм.3- акт от 15.02.2019 г.","Монолитные фундаменты ","2019-03-18","2019-10-18"]
[null,{"$f":"IF(ISBLANK(C20),\"\",COUNTA(C$17:C20))","v":4},"1792.17-1-КЖ1 изм.1  \n1792.17-1-КЖ1 изм.2   \n1792.17-1-КЖ1 изм.3","изм 1 -акт от 15.01.2019  \n изм.2- акт от 12.02.2019г.\nИзм.3- акт от 15.02.2019 г.","Монолитные фундаменты ","2019-03-18","2019-10-18"]
[null,{"$f":"IF(ISBLANK(C21),\"\",COUNTA(C$17:C21))","v":5},"1792.17-1-КЖ1 изм.1  \n1792.17-1-КЖ1 изм.2   \n1792.17-1-КЖ1 изм.3","изм 1 -акт от 15.01.2019  \n изм.2- акт от 12.02.2019г.\nИзм.3- акт от 15.02.2019 г.","Монолитные фундаменты ","2019-01-15","2019-10-18"]

{"sheet":"Лист1","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Лист2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}