## Overall
VLS
OMSK DCC Project (SRU)-DAILY WORK REPORT_IN
Date: | 2020-05-11 |  |  | Weather: | Fine
Instrumentional/КИП
| Total | Done | Remain | % Completion | Today | RFI | % RFI(Done)
Perforated tray Secondary Вторичный лоток | 10692 | 8624 | 2068 | 80.66% | 94 | 6358 | 73.72%
Primary Cable Pulling Первичный кабель | 45285 | 44785 | 500 | 98.9% |  | 29535 | 65.95%
Secondary Cable Pulling Вторичный кабель | 47622 | 20862 | 26760 | 43.81% | 370 | 13312 | 63.81%
Primary Cable Termination Подлключение первичного кабеля | 474 | 369 | 105 | 77.85% | 0 | 163 | 44.17%
Secondary Cable Termination Подключение вторичного кабеля | 3289 | 1219 | 2070 | 37.06% | 0 | 591 | 48.48%
Panel installation Установка панелей управления | #REF! | #REF! | #REF! | #REF! | 0 | 42 | #REF!
JB installattion Установка распределтельных коробок | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF!
Instrument device Приборы | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Local Hand Switch Кнопки управления | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF!
Rizur Boxes | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF!
Analysers Анализаторы | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Electrical/Электрика
| Total | Done | Remain | % Completion | Today | RFI | % RFI(Done)
Perforated tray Primary Первичный лоток | #REF! | #REF! | #REF! | #REF! | 0 | 1384 | #REF!
Perforated tray Secondary Вторичный лоток | 2868 | 1767 | 1101 | 61.61% | 0 | 1542.5 | 87.29%
Primary Cable Pulling Первичный кабель | 23802 | 21047 | 2755 | 88.43% | 0 | 0 | 0%
Secondary Cable Pulling Вторчный кабель | 9306 | 6496 | 2810 | 69.8% | 0 | 4882 | 75.15%
Primary Cable Termination Подключения первичного кабеля | 192 | 77 | 115 | 40.1% | 0 | 0 | 0%
Secondary Cable Termination Подключения вторичного кабеля | 582 | 395 | 187 | 67.87% | 0 | 330 | 83.54%
Panel installation Установка панелей управления | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF!
JB & JB installattion Установка распределтельных коробок | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF!
Instrument device Приборы | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
HVAC
| Total | Done | Remain | % Completion | Today | RFI | % RFI(Done)
Perforated tray Secondary Вторичный лоток | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF!
Secondary Cable Termination Подключения вторичного кабеля | 300 | 239 | 61 | 79.67% | 1 | 0 | 0%
Secondary Cable Pulling Вторичный кабель | 5062 | 5062 | 0 | 100% | 0 | 4565 | 90.18%
Panel installation Установка панелей управления | #REF! | #REF! | #REF! | #REF! | 0 | 2 | #REF!
JB & JB installattion Установка распределтельных коробок | #REF! | #REF! | #REF! | #REF! | 0 | 0 | #REF!
Instrument device Приборы | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF!
FIRE FIGHTING / Пожаротушение
| Total | Done | Remain | % Completion | Today | RFI | % RFI(Done)
Perforated tray Secondary Вторичный лоток | 90 | 81 | 9 | 90% | 0 | 81 | 100%
Secondary Cable Pulling Вторичный кабель | 1896 | 1896 | 0 | 100% | 0 | 1884 | 99.37%
Secondary Cable Termination Подключение вторичного кабеля | 356 | 277 | 79 | 77.81% | 0 | 0 | 0%
Panel installation Установка панелей управления | #REF! | #REF! | #REF! | #REF! | 0 | 4 | #REF!
JB & JB installattion Установка распределтельных коробок | #REF! | #REF! | #REF! | #REF! | 0 | 2 | #REF!
Instrument device Приборы | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF!
Detail Man-Power (Direct Labor) |  |  |  | Equipment &Machinery
Man-power | Prev. Acc | Today | Accum. | Description | Capacity | Prev. Acc | Today | Accum.
Foreman | #REF! | #REF! | #REF! | Crane 25T | 0 | 0 | 0 | 0
Fitter | #REF! | #REF! | #REF! | Excavator | 0 | 0 | 0 | 0
Helper | #REF! | #REF! | #REF! | Boom Truck | 0 | 0 | 0 | 0
Welder | #REF! | #REF! | #REF! | Crane 50T | 0 | 0 | 0 | 0
Electrician | #REF! | #REF! | #REF! | Pick up Truck | 0 | 0 | 0 | 0
Rigger | #REF! | #REF! | #REF! | Canter Truck | 0 | 0 | 0 | 0
Scaffolder | #REF! | #REF! | #REF! | Flat Bed Trailer | 0 | 0 | 0 | 0
Crane Operator | #REF! | #REF! | #REF! | Diesel Tanker | 0 | 0 | 0 | 0
Forklift operator | #REF! | #REF! | #REF! | Forklift | 0 | 0 | 0 | 0
Driver | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0
Calibration Technician | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0
LoopTest Technician | #REF! | #REF! | #REF! |  | 0 | 0 | 0 | 0
Direct Labor Total | #REF! | #REF! | #REF! |  |  | 0 | 0 | 0
Today
Man-Power Area | Electrician | Foreman | Calibration | Looptest
110 | 0 | 0 | 0 | 0
120 | 0 | 0 | 0 | 0
130 | 0 | 0 | 0 | 0
140 | 19 | 2 | 0 | 0
150 | 16 | 2 | 0 | 0
160 | 18 | 2 | 0 | 0
170 | 13 | 2 | 1 | 0
180 | 0 | 0 | 0 | 0
190 | 0 | 0 | 0 | 0
Total: | 66 | 8 | 1 | 0

## 1.2 Perforated tray
1.3 Perforated tray
Area | Disc | Description | Type |  |  |  | April | [29 empty] | May
|  |  |  | Done (M) | RFI | Previosly | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
 | time axis 2020-04-01 to 2020-05-27
110 | IN | Tray Instrument |  | 1047 | 952
|  | 50*50 | ATX3 | 632 | 542 | 505 | 2020-04-02: 18; 2020-04-03: 3; 2020-04-08: 6; 2020-04-09: 12; 2020-04-11: 2; 2020-04-13: 4; 2020-04-14: 3; 2020-04-15: 7; 2020-04-16: 2; 2020-04-17: 3; 2020-04-18: 6; 2020-04-20: 6; 2020-04-21: 3; 2020-04-22: 3; 2020-04-23: 3; 2020-04-24: 4; 2020-04-28: 7; 2020-04-29: 3; 2020-04-30: 2; 2020-05-01: 4; 2020-05-02: 1; 2020-05-03: 3; 2020-05-04: 8; 2020-05-05: 5; 2020-05-06: 2; 2020-05-07: 3; 2020-05-08: 4
|  | 100*50 |  | 304 | 299 | 299 | 2020-04-23: 5
|  | 200*50 |  | 111 | 111 | 111
120 |  | Tray Instrument |  | 119 | 83
|  | 50*50 | ATX3 | 87 | 57 | 57 | 2020-04-11: 2; 2020-04-21: 6; 2020-04-22: 3; 2020-04-23: 6; 2020-04-24: 3; 2020-05-05: 7; 2020-05-06: 1; 2020-05-07: 2
|  | 100*50 |  | 32 | 26 | 26 | 2020-04-20: 3; 2020-04-21: 3
|  | 200*50 |  | 0 |  | 0
130 |  | Tray Instrument |  | 167 | 154
|  | 50*50 | ATX3 | 121 | 113 | 96 | 2020-04-06: 3; 2020-04-07: 5; 2020-04-10: 11; 2020-04-11: 2; 2020-05-02: 2; 2020-05-08: 2
|  | 100*50 |  | 41 | 38 | 38 | 2020-04-07: 3
|  | 200*50 |  | 5 | 3 | 5
140 |  | Tray Instrument |  | 3934 | 2648
|  | 50*50 | ATX3 | 1622 | 1019 | 860 |  |  | 15 | 24 | 15 | 15 | 9 | 12 | 9 | 9 | 12 | 24 | 15 | 30 | 9 | 12 | 20 | 6 |  | 30 | 6 | 30 | 24 | 12 | 15 | 18 | 21 | 12 | 36 | 39 | 3 | 30 | 9 | 52 | 18 | 33 | 18 | 27 | 24 | 30 | 39
|  | 100*50 |  | 1595 | 1054 | 936 |  | 30 | 15 | 6 | 12 | 18 | 27 | 6 | 15 | 3 | 12 | 3 | 3 | 12 | 12 | 9 | 15 | 18 |  | 12 | 6 | 21 | 6 | 21 | 19 | 27 | 27 | 21 | 15 | 12 | 36 | 30 | 12 | 19 | 21 | 24 | 27 | 18 | 36 | 15 | 18
|  | 200*50 |  | 717 | 575 | 374 | 2020-04-02: 18; 2020-04-03: 9; 2020-04-04: 12; 2020-04-05: 9; 2020-04-06: 12; 2020-04-08: 18; 2020-04-09: 27; 2020-04-10: 27; 2020-04-11: 15; 2020-04-12: 3; 2020-04-13: 6; 2020-04-14: 3; 2020-04-15: 12; 2020-04-16: 12; 2020-04-17: 9; 2020-04-18: 6; 2020-04-20: 15; 2020-04-21: 12; 2020-04-22: 22; 2020-04-23: 12; 2020-04-24: 3; 2020-04-25: 7; 2020-04-26: 9; 2020-04-27: 11; 2020-04-28: 3; 2020-04-29: 18; 2020-05-01: 9; 2020-05-08: 6; 2020-05-09: 9; 2020-05-10: 6; 2020-05-11: 3
150 |  | Tray Instrument |  | 706 | 209
|  | 50*50 | ATX3 | 343 | 12 | 27 | 2020-04-02: 6; 2020-04-03: 12; 2020-04-04: 6; 2020-04-05: 3; 2020-04-06: 13; 2020-04-07: 5; 2020-04-13: 10; 2020-04-14: 6; 2020-04-15: 9; 2020-04-16: 9; 2020-04-17: 3; 2020-04-18: 12; 2020-04-20: 12; 2020-04-21: 13.5; 2020-04-22: 28; 2020-04-23: 7.5; 2020-04-24: 12; 2020-04-25: 18; 2020-04-26: 4; 2020-04-27: 3; 2020-04-28: 5; 2020-04-29: 6; 2020-04-30: 6; 2020-05-01: 5; 2020-05-02: 12; 2020-05-04: 5; 2020-05-05: 10; 2020-05-06: 3; 2020-05-08: 3; 2020-05-09: 18; 2020-05-10: 30; 2020-05-11: 21
|  | 100*50 |  | 220 | 104 | 92 | 2020-04-02: 12; 2020-04-13: 6; 2020-04-14: 21; 2020-04-15: 9; 2020-04-16: 2; 2020-04-17: 9; 2020-04-21: 4.5; 2020-04-24: 3; 2020-04-25: 11; 2020-04-27: 7.5; 2020-04-28: 6; 2020-05-02: 3; 2020-05-03: 1; 2020-05-04: 4; 2020-05-06: 9; 2020-05-07: 8; 2020-05-08: 7; 2020-05-11: 5
|  | 200*50 |  | 143 | 93 | 90 | 2020-04-02: 3; 2020-04-03: 9; 2020-04-04: 6; 2020-04-05: 3; 2020-05-04: 6; 2020-05-09: 15; 2020-05-10: 3; 2020-05-11: 8
160 |  | Tray Instrument |  | 1394 | 1100.5
|  | 50*50 | ATX3 | 546.5 | 359 | 359 | 2020-04-08: 7; 2020-04-09: 3.5; 2020-04-10: 9; 2020-04-11: 5; 2020-04-12: 3; 2020-04-14: 15; 2020-04-15: 5; 2020-04-23: 3.5; 2020-04-24: 4.5; 2020-04-29: 6; 2020-05-01: 6; 2020-05-03: 12; 2020-05-04: 7; 2020-05-05: 23; 2020-05-06: 14; 2020-05-07: 38; 2020-05-08: 6; 2020-05-09: 12; 2020-05-10: 8
|  | 100*50 |  | 538.5 | 458.5 | 503.5 | 2020-04-11: 3; 2020-04-12: 2; 2020-04-23: 3; 2020-04-24: 8; 2020-04-25: 2; 2020-05-04: 9; 2020-05-06: 4; 2020-05-07: 4
|  | 200*50 |  | 309 | 283 | 296.5 | 2020-04-12: 3; 2020-04-25: 5.5; 2020-05-03: 4
180 |  | Tray Instrument |  | 571 | 567.5
|  | 50*50 | ATX3 | 315 | 315 | 315
|  | 100*50 |  | 178 | 174.5 | 178
|  | 200*50 |  | 78 | 78 | 78
Sub-TOTAL/Remain |  | 10450 | 2512 | 7938 | 5714 |  | 0 | 87 | 63 | 54 | 42 | 61 | 49 | 49 | 66.5 | 59 | 53 | 38 | 44 | 90 | 63 | 46 | 59 | 48 | 0 | 78 | 54 | 107 | 70 | 70.5 | 77.5 | 58 | 69.5 | 54 | 84 | 59 | 63 | 78 | 41 | 110 | 84 | 90 | 100 | 73 | 114 | 92 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | SF | Tray Instrument |  | 72 | 52
|  | 50*50 | PS | 0 |  | 0
|  | 100*50 |  | 72 | 72 | 72
|  | 200*50 |  | 0 |  | 0
130 |  | Tray Instrument |  | 50 | 50
|  | 50*50 | PS | 0 |  | 0
|  | 100*50 |  | 50 | 50 | 35 | 2020-04-12: 9; 2020-04-13: 6
|  | 200*50 |  | 0 |  | 0
140 |  | Tray Instrument |  | 82 | 66
|  | 50*50 | PS | 0 |  | 0
|  | 100*50 |  | 82 | 66 | 82
|  | 200*50 |  | 0 |  | 0
150 |  | Tray Instrument |  | 0
|  | 50*50 | PS | 0 |  | 0
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
160 |  | Tray Instrument |  | 9 | 9
|  | 50*50 | PS | 0 |  | 0
|  | 100*50 |  | 9 | 9 | 9
|  | 200*50 |  | 0 |  | 0
170 |  | Tray Instrument |  | 117 | 117
|  | 50*50 | PS | 0 |  | 0
|  | 100*50 |  | 117 | 117 | 117
|  | 200*50 |  | 0 |  | 0
180 |  | Tray Instrument |  | 219 | 219
|  | 50*50 | PS | 0 |  | 0
|  | 100*50 |  | 219 | 219 | 219
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 495 | -54 | 549 | 513 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | El | Tray Instrument |  | 187 | 182
|  | 50*50 | ATX4 | 115 | 110 | 38 | 2020-04-04: 24; 2020-04-10: 35; 2020-04-11: 13; 2020-05-07: 5
|  | 100*50 |  | 50 | 50 | 17 | 2020-04-10: 27; 2020-04-11: 6
|  | 200*50 |  | 22 | 22 | 0 | 2020-04-10: 22
130 |  | Tray Instrument |  | 5 | 5
|  | 50*50 | ATX4 | 0 |  | 0
|  | 100*50 |  | 5 | 5 | 5
|  | 200*50 |  | 0 |  | 0
140 |  | Tray Instrument |  | 230 | 169
|  | 50*50 | ATX4 | 139 | 127 | 127 | 2020-04-12: 9; 2020-04-13: 3
|  | 100*50 |  | 76 | 27 | 64 | 2020-04-20: 12
|  | 200*50 |  | 15 | 15 | 15
150 |  | Tray Instrument |  | 0
|  | 50*50 | ATX4 | 0 |  | 0
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
160 |  | Tray Instrument |  | 31 | 31
|  | 50*50 | ATX4 | 31 | 31 | 24 | 2020-04-02: 7
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
180 |  | Tray Instrument |  | 99 | 87.5
|  | 50*50 | ATX4 | 83 | 83 | 83
|  | 100*50 |  | 16 | 4.5 | 16
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 1017 | 465 | 552 | 474.5 |  | 0 | 7 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 84 | 19 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | IN | Tray Instrument |  | 16 | 16
|  | 50*50 | SMMO | 16 | 16 | 11 | 2020-04-12: 5
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
140 |  | Tray Instrument |  | 79 | 79
|  | 50*50 | SMMO | 79 | 79 | 79
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
150 |  | Tray Instrument |  | 0 | 0
|  | 50*50 | SMMO | 0 |  | 0
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
160 |  | Tray Instrument |  | 42 | 36
|  | 50*50 | SMMO | 42 | 36 | 42
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 152 | 15 | 137 | 131 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total IN |  | 10602 | 2527 | 8075 | 6358 |  | 0 | 87 | 63 | 54 | 42 | 61 | 49 | 49 | 66.5 | 59 | 53 | 52 | 50 | 90 | 63 | 46 | 59 | 48 | 0 | 78 | 54 | 107 | 70 | 70.5 | 77.5 | 58 | 69.5 | 54 | 84 | 59 | 63 | 78 | 41 | 110 | 84 | 90 | 100 | 73 | 114 | 92 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | EL | Tray Instrument |  | 78 | 76
|  | 50*50 | SS | 0 |  | 0
|  | 100*50 |  | 78 | 76 | 78
|  | 200*50 |  | 0 |  | 0
120 |  | Tray Instrument |  | 0
|  | 50*50 | SS | 0 |  | 0
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
130 |  | Tray Instrument |  | 18
|  | 50*50 | SS | 0 |  | 0
|  | 100*50 |  | 18 |  | 18
|  | 200*50 |  | 0 |  | 0
140 |  | Tray Instrument |  | 127 | 102
|  | 50*50 | SS | 6 |  | 6
|  | 100*50 |  | 121 | 102 | 112 | 2020-04-20: 9
|  | 200*50 |  | 0 |  | 0
150 |  | Tray Instrument |  | 18
|  | 50*50 | SS | 0 |  | 0
|  | 100*50 |  | 18 |  | 18
|  | 200*50 |  | 0 |  | 0
160 |  | Tray Instrument |  | 0
|  | 50*50 | SS | 0 |  | 0
|  | 100*50 |  | 0 |  | 0
|  | 200*50 |  | 0 |  | 0
170 |  | Tray Instrument |  | 52 | 50
|  | 50*50 | SS | 0 |  | 0
|  | 100*50 |  | 52 | 50 | 52
|  | 200*50 |  | 0 |  | 0
180 |  | Tray Instrument |  | 242 | 242
|  | 50*50 | SS | 0 |  | 0
|  | 100*50 |  | 242 | 242 | 242
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 501 | -34 | 535 | 470 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | EL | Tray Instrument |  | 276 | 276
|  | 50*50 | SS1 | 0 |  | 0
|  | 100*50 |  | 276 | 276 | 276
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 450 | 174 | 276 | 276 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | EL | Tray Instrument |  | 79 | 76
|  | 50*50 | STVN | 0 |  | 0
|  | 100*50 |  | 79 | 76 | 76 | 2020-04-30: 3
|  | 200*50 |  | 0 |  | 0
130 |  | Tray Instrument |  | 27
|  | 50*50 | STVN | 0 |  | 0
|  | 100*50 |  | 27 |  | 0 | 2020-04-12: 13; 2020-04-13: 10; 2020-04-14: 4
|  | 200*50 |  | 0 |  | 0
140 |  | Tray Instrument |  | 86 | 66
|  | 50*50 | STVN | 0 |  | 0
|  | 100*50 |  | 86 | 66 | 66 | 2020-04-23: 2; 2020-04-24: 5; 2020-04-26: 4; 2020-05-06: 6; 2020-05-08: 3
|  | 200*50 |  | 0 |  | 0
150 |  | Tray Instrument |  | 9
|  | 50*50 | STVN | 0
|  | 100*50 |  | 9 |  |  | 2020-05-06: 9
|  | 200*50 |  | 0
160 |  | Tray Instrument |  | 9
|  | 50*50 | STVN | 0 |  | 0
|  | 100*50 |  | 9 |  | 0 | 2020-04-23: 9
|  | 200*50 |  | 0 |  | 0
170 |  | Tray Instrument |  | 9
|  | 50*50 | STVN | 0 |  | 0
|  | 100*50 |  | 9 |  | 0 | 2020-04-22: 9
|  | 200*50 |  | 0 |  | 0
180 |  | Tray Instrument |  | 185 | 180
|  | 50*50 | STVN | 0 |  | 0
|  | 100*50 |  | 185 | 180 | 180 | 2020-04-22: 2; 2020-05-04: 3
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 900 | 496 | 404 | 322 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 5 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 15 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total TE |  | 1851 | 636 | 1215 | 1068 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 11 | 11 | 5 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 15 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | FF | Tray Instrument |  | 54 | 54
|  | 50*50 | AUPT | 0 |  | 0
|  | 100*50 |  | 54 | 54 | 54
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 54 | 0 | 54 | 54 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | FF | Tray Instrument |  | 27 | 27
|  | 50*50 | AUGPT | 0 |  | 0
|  | 100*50 |  | 27 | 27 | 27
|  | 200*50 |  | 0 |  | 0
Sub-TOTAL/Remain |  | 36 | 9 | 27 | 27 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total FF |  | 90 | 9 | 81 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total IN |  | 11097 | 2473 | 8624 | 6358 |  | 0 | 87 | 63 | 54 | 42 | 61 | 49 | 49 | 66.5 | 59 | 53 | 52 | 50 | 90 | 63 | 46 | 59 | 48 | 0 | 78 | 54 | 107 | 70 | 70.5 | 77.5 | 58 | 69.5 | 54 | 84 | 59 | 63 | 78 | 41 | 110 | 84 | 90 | 100 | 73 | 114 | 92 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total EL |  | 2868 | 1101 | 1767 | 1542.5 |  | 0 | 7 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 84 | 19 | 22 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 11 | 11 | 5 | 0 | 4 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 15 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 14055
Done |  | 10472
Remaine |  | 3583
% Сompletion |  | 74.51%
RFI |  | 7981.5

## 2.0 Cable Pulling
■ Cable Pulling Schedule (Detail)
Disc | Design | Area |  |  |  |  | March, 2020 | [30 empty] | April | [29 empty] | MAY
|  |  | Plan | Total (M) | RFI | Prev | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Sat | Sun | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Sat | Sat | Sat
|  |  | Actual |  |  |  | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31
IN | ATX3 Prim | 110 | Plan | 620
|  |  | Actual | 620 | 620 | 620
|  | 120 | Plan | 1400
|  |  | Actual | 1400 | 1400 | 1400
|  | 130 | Plan | 3035
|  |  | Actual | 3035 | 3035 | 3035
|  | 140 | Plan | 25025
|  |  | Actual | 24725 | 18050 | 23035 | March, 2020 Sun: 510; MAY Sat: 690; MAY Sun: 270; MAY Fri: 220
|  | 150 | Plan | 3875
|  |  | Actual | 3875 | 1500 | 3875
|  | 160 | Plan | 5965
|  |  | Actual | 5765 | 3880 | 5765
|  | 170 | Plan | 1050
|  |  | Actual | 1050 | 1050 | 850 | March, 2020 Thu: 200
|  | 180 | Plan | 0
|  |  | Actual | 0
|  | 190 | Plan | 0
|  |  | Actual | 0
|  | Sub Total | Plan | 40970 | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 40470 | 29535 | 38580 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 270 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ATX3 Sec | 110 | Plan | 2330
|  |  | Actual | 1680 | 1610 | 310 | March, 2020 Thu: 200; March, 2020 Sat: 300; March, 2020 Wed: 60; March, 2020 Thu: 260; April Thu: 180; April Wed: 270; April Thu: 30; April Sat: 70
|  | 120 | Plan | 1550
|  |  | Actual | 1350 | 950 | 30 | March, 2020 Fri: 290; March, 2020 Tue: 80; March, 2020 Wed: 40; March, 2020 Tue: 290; April Tue: 140; April Thu: 100; April Fri: 80; April Thu: 240; April Sat: 60
|  | 130 | Plan | 700
|  |  | Actual | 690 | 630 | 40 | March, 2020 Tue: 10; March, 2020 Tue: 90; April Sun: 150; April Thu: 70; April Fri: 40; April Sun: 160; April Mon: 70; April Sat: 60
|  | 140 | Plan | 19800
|  |  | Actual | 4020 | 610 |  | April Thu: 50; April Fri: 110; April Sat: 460; April Sun: 140; April Mon: 130; April Tue: 140; April Wed: 410; April Sun: 240; April Mon: 180; April Wed: 80; April Fri: 300; April Sun: 110; April Mon: 120; April Tue: 200; April Wed: 130; April Sat: 70; MAY Fri: 40; MAY Mon: 50; MAY Tue: 60; MAY Sat: 270; MAY Sun: 360; MAY Mon: 370
|  | 150 | Plan | 4950
|  |  | Actual | 880 |  |  | April Sun: 70; April Sat: 60; April Sun: 80; April Thu: 250; April Fri: 150; April Sat: 40; MAY Wed: 230
|  | 160 | Plan | 9010
|  |  | Actual | 2960 | 1180 | 103 | March, 2020 Sun: 120; March, 2020 Wed: 487; March, 2020 Sat: 240; March, 2020 Sun: 40; April Sun: 160; April Sun: 420; April Mon: 110; April Thu: 130; April Fri: 240; April Sat: 100; April Sun: 160; April Thu: 60; April Sat: 50; MAY Fri: 20; MAY Tue: 90; MAY Wed: 80; MAY Thu: 300; MAY Fri: 50
|  | 170 | Plan | 280
|  |  | Actual | 280 | 60 | 60 | March, 2020 Thu: 220
|  | 180 | Plan
|  |  | Actual | 0
|  | 190 | Plan | 0
|  |  | Actual | 0
|  | Sub Total | Plan | 38620 | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 11860 | 5040 | 543 | 120 | 0 | 0 | 0 | 200 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 90 | 587 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | 480 | 0 | 240 | 40 | 0 | 0 | 0 | 310 | 420 | 110 | 140 | 0 | 530 | 470 | 460 | 370 | 200 | 140 | 410 | 0 | 0 | 160 | 400 | 180 | 0 | 350 | 330 | 300 | 190 | 190 | 120 | 200 | 130 | 250 | 150 | 160 | 60 | 0 | 0 | 50 | 150 | 310 | 300 | 50 | 270 | 360 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK2 Sec | 170 | Plan | 6491
|  |  | Actual | 6491 | 6491 | 6426 | March, 2020 Fri: 65
| SMMO Sec | 130 | Plan | 80
|  |  | Actual | 80 |  |  | March, 2020 Sat: 80
|  | 140 | Plan | 320
|  |  | Actual | 320 |  |  | March, 2020 Sat: 80; March, 2020 Sun: 160; March, 2020 Mon: 40; March, 2020 Fri: 40
|  | 160 | Plan | 160
|  |  | Actual | 160 |  |  | March, 2020 Sun: 160
|  | Sub Total | Plan | 560
|  |  | Actual | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 320 | 40 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SMIS Sec | 170 | Plan | 47
|  |  | Actual | 47 | 47 |  | March, 2020 Thu: 47
IN | PS Prim | 130 | Plan | 1140
|  |  | Actual | 1140 |  | 715 | March, 2020 Tue: 425
|  | 140 | Plan | 275
|  |  | Actual | 275 |  |  | March, 2020 Sun: 275
|  | 180 | Plan | 1620
|  |  | Actual | 1620 |  |  | March, 2020 Sun: 220; March, 2020 Mon: 1400
|  | Sub Total | Plan | 3035
|  |  | Actual | 3035 | 0 | 715 | March, 2020 Sun: 495; March, 2020 Mon: 1400; March, 2020 Tue: 425; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0
| PS Sec | 130 | Plan | 70
|  |  | Actual | 70 |  |  | April Sun: 30; April Fri: 40
|  | 170 | Plan | 1139
|  |  | Actual | 1139 | 1139 | 25 | March, 2020 Sun: 80; March, 2020 Mon: 200; March, 2020 Wed: 160; March, 2020 Sat: 30; March, 2020 Wed: 64; March, 2020 Sat: 41; March, 2020 Sun: 56; March, 2020 Mon: 57; March, 2020 Tue: 63; April Sun: 81; April Sun: 103; April Mon: 36; April Tue: 36; April Wed: 50; April Fri: 27; April Mon: 30
| SOUE Prim | 130 | Plan | 1280
|  |  | Actual | 1280 |  | 780 | March, 2020 Sun: 500
| SOUE Sec | 130 | Plan | 100
|  |  | Actual | 100 |  |  | April Sun: 70; April Fri: 30
|  | 170 | Plan | 595
|  |  | Actual | 595 | 595 | 579 | March, 2020 Sun: 16
|  | Sub Total | Plan | 695
|  |  | Actual | 695 | 595 | 579 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Instrument Prim |  |  | Plan | 45285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 44785 | 29535 | 40075 | 1505 | 1400 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 270 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Instrument Sec |  |  | Plan | 47622
|  |  | Actual | 20862 | 13312 | 7573 | 216 | 200 | 0 | 160 | 200 | 290 | 160 | 320 | 40 | 0 | 0 | 0 | 40 | 300 | 0 | 0 | 90 | 587 | 47 | 65 | 30 | 0 | 0 | 380 | 64 | 480 | 0 | 281 | 96 | 57 | 63 | 0 | 391 | 523 | 146 | 176 | 50 | 530 | 497 | 460 | 470 | 200 | 140 | 410 | 0 | 70 | 160 | 400 | 180 | 0 | 350 | 330 | 300 | 190 | 190 | 150 | 200 | 130 | 250 | 150 | 160 | 60 | 0 | 0 | 50 | 150 | 310 | 300 | 50 | 270 | 360 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EL | ATX4 Prim | 120 | Plan | 2688
|  |  | Actual | 2688 |  | 2688
|  | 130 | Plan | 286
|  |  | Actual | 286 |  | 286
|  | 140 | Plan | 9060
|  |  | Actual | 9004 |  | 6497 | March, 2020 Mon: 409; March, 2020 Tue: 1480; March, 2020 Wed: 618
|  | 150 | Plan | 720
|  |  | Actual | 358 |  |  | March, 2020 Thu: 358
|  | 160 | Plan | 1828
|  |  | Actual | 1436 |  | 1189 | March, 2020 Thu: 143; March, 2020 Wed: 104
|  | Sub Total | Plan | 14582
|  |  | Actual | 13772 | 0 | 10660 | 0 | 409 | 1480 | 0 | 501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ATX4 Sec | 170 | Plan | 2227
|  |  | Actual | 2227 | 2227 | 2227
| ASUE Sec | 170 | Plan | 2255
|  |  | Actual | 2255 | 2255 | 908 | March, 2020 Mon: 1272; March, 2020 Thu: 75
| SS Prim | 120 | Plan | 400
|  |  | Actual | 400 |  | 400
|  | 130 | Plan | 400
|  |  | Actual | 400 |  | 400
|  | 140 | Plan | 980
|  |  | Actual | 980 |  | 980
|  | 150 | Plan | 250
|  |  | Actual | 250 |  | 250
|  | 160 | Plan | 300
|  |  | Actual | 300 |  | 300
|  | 180 | Plan | 515
|  |  | Actual | 515 |  | 515
|  | Sub Total | Plan | 2845
|  |  | Actual | 2845 | 0 | 2845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SS Sec | 170 | Plan | 470
|  |  | Actual | 414 |  | 65 | March, 2020 Wed: 80; March, 2020 Sat: 70; March, 2020 Wed: 159; March, 2020 Sat: 35; MAY Thu: 5
| SS1 Prim | In active | Plan | 2845
|  |  | Actual | 1890 |  |  | April Fri: 1500; April Sat: 390
| SS2 Sec | 190 | Plan | 680
|  |  | Actual | 0
| SS3 Prim | 190 | Plan | 550
|  |  | Actual | 0
| TLF Sec | 170 | Plan | 630
|  |  | Actual | 630 |  | 615 | MAY Sat: 15
| RT Sec | 170 | Plan | 215
|  |  | Actual | 215 | 215 | 115 | March, 2020 Sun: 100
| STVN Prim | 110 | Plan | 700
|  |  | Actual | 700 |  |  | March, 2020 Fri: 350; March, 2020 Sun: 350
|  | 140 | Plan | 1200
|  |  | Actual | 1200 |  |  | March, 2020 Fri: 250; March, 2020 Sun: 950
|  | 160 | Plan | 300
|  |  | Actual | 300 |  |  | March, 2020 Sun: 300
|  | 180 | Plan | 340
|  |  | Actual | 340 |  |  | March, 2020 Fri: 320; March, 2020 Sun: 20
|  | Sub Total | Plan | 2540
|  |  | Actual | 2540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STVN Sec | 110 | Plan | 264
|  |  | Actual | 0
|  | 130 | Plan | 152
|  |  | Actual | 150 |  |  | MAY Sun: 150
|  | 140 | Plan | 1024
|  |  | Actual | 0
|  | 150 | Plan | 394
|  |  | Actual | 0
|  | 160 | Plan | 260
|  |  | Actual | 90 |  |  | April Mon: 90
|  | 170 | Plan | 275
|  |  | Actual | 275 | 185 |  | April Sun: 185; April Mon: 90
|  | Sub Total | Plan | 2369
|  |  | Actual | 515 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STVN 1 Prim | 190 | Plan | 440
|  |  | Actual | 0
| STVN 1 Sec | 190 | Plan | 190
|  |  | Actual | 0
| SKUD Sec | 170 | Plan | 270
|  |  | Actual | 240 |  | 240
Total Prim |  |  | Plan | 23802
|  |  | Actual | 21047 | 0 | 13505 | 0 | 409 | 1480 | 0 | 501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 722 | 0 | 920 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Sec |  |  | Plan | 9306
|  |  | Actual | 6496 | 4882 | 4170 | 100 | 1272 | 0 | 80 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 75 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 185 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 5 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AOVK | HVAC Sec | 130 | Plan | 382
|  |  | Actual | 382 |  |  | April Thu: 28; April Fri: 152; April Sat: 172; April Mon: 30
|  | 170 | Plan | 4680
|  |  | Actual | 4680 | 4565 |  | March, 2020 Tue: 9; March, 2020 Sun: 451; March, 2020 Thu: 390; March, 2020 Tue: 120; March, 2020 Wed: 460; March, 2020 Thu: 170; March, 2020 Fri: 450; March, 2020 Sat: 65; March, 2020 Mon: 117; March, 2020 Tue: 5; March, 2020 Sat: 200; March, 2020 Sun: 280; March, 2020 Mon: 588; April Sun: 570; April Mon: 18; April Tue: 349; April Wed: 408; MAY Fri: 30
|  | Sub Total | Plan | 5062 | 0 | 0 | March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0
|  |  | Actual | 5062 | 4565 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 451 | 0 | 0 | 0 | 390 | 0 | 0 | 0 | 0 | 120 | 460 | 170 | 450 | 65 | 0 | 117 | 5 | 0 | 0 | 0 | 200 | 280 | 588 | 0 | 0 | 570 | 0 | 18 | 349 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 152 | 172 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SF | AUPT Sec | 170 | Plan | 1458
|  |  | Actual | 1458 | 1446 | 1316 | March, 2020 Thu: 134; March, 2020 Mon: 8
| AUGPT Sec | 170 | Plan | 438
|  |  | Actual | 438 | 438 | 383 | March, 2020 Thu: 35; March, 2020 Wed: 20
Total SF Sec |  |  | Plan | 1896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 1896 | 1884 | 1699 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## 2.1 Cable Termination
■ Cable Termination (Detail)
Disc | Design | Area |  |  |  |  | March, 2020 | [30 empty] | April | [29 empty] | MAY
|  |  | Plan | Total (M) | RFI | Prev | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Sat | Sun | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
|  |  | Actual |  |  |  | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30 | 2019-10-31 | 2019-09-01 | 2019-09-02 | 2019-09-03 | 2019-09-04 | 2019-09-05 | 2019-09-06 | 2019-09-07 | 2019-09-08 | 2019-09-09 | 2019-09-10 | 2019-09-11 | 2019-09-12 | 2019-09-13 | 2019-09-14 | 2019-09-15 | 2019-09-16 | 2019-09-17 | 2019-09-18 | 2019-09-19 | 2019-09-20 | 2019-09-21 | 2019-09-22 | 2019-09-23 | 2019-09-24 | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-09-28 | 2019-09-29 | 2019-09-30 | 2019-10-01 | 2019-10-02 | 2019-10-03 | 2019-10-04 | 2019-10-05 | 2019-10-06 | 2019-10-07 | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18 | 2019-10-19 | 2019-10-20 | 2019-10-21 | 2019-10-22 | 2019-10-23 | 2019-10-24 | 2019-10-25 | 2019-10-26 | 2019-10-27 | 2019-10-28 | 2019-10-29 | 2019-10-30
IN | ATX3 Prim | 110 | Plan | 2
|  |  | Actual | 0
|  | 120 | Plan | 4
|  |  | Actual | 4 | 1 |  | March, 2020 Mon: 2; March, 2020 Thu: 1; April Mon: 1
|  | 130 | Plan | 9
|  |  | Actual | 8 | 5 | 0 | March, 2020 Mon: 3; March, 2020 Tue: 4; MAY Fri: 1
|  | 140 | Plan | 104
|  |  | Actual | 53 | 34 | 4 | March, 2020 Mon: 7; March, 2020 Mon: 1; March, 2020 Wed: 4; March, 2020 Tue: 3; March, 2020 Fri: 2; March, 2020 Sat: 4; March, 2020 Mon: 2; April Mon: 5; April Wed: 3; April Thu: 3; April Fri: 1; April Sat: 2; April Mon: 2; April Tue: 5; April Sat: 1; MAY Wed: 1; MAY Thu: 1; MAY Fri: 1; MAY Sat: 1
|  | 150 | Plan | 20
|  |  | Actual | 7 |  | 0 | March, 2020 Tue: 4; March, 2020 Thu: 2; April Fri: 1
|  | 160 | Plan | 43
|  |  | Actual | 20 | 4 | 0 | March, 2020 Thu: 11; March, 2020 Fri: 1; March, 2020 Fri: 1; March, 2020 Sat: 2; April Sat: 2; April Sun: 1; MAY Wed: 1; MAY Thu: 1
|  | 170 | Plan | 256
|  |  | Actual | 250 | 119 | 232 | March, 2020 Sun: 7; March, 2020 Thu: 4; March, 2020 Sun: 2; April Sun: 2; MAY Sat: 2; MAY Sat: 1
|  | 180 | Plan | 0
|  |  | Actual | 0
|  | 190 | Plan | 0
|  |  | Actual | 0
|  | Sub Total | Plan | 438 | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 342 | 163 | 236 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 8 | 0 | 17 | 1 | 0 | 0 | 1 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 6 | 2 | 2 | 0 | 0 | 0 | 2 | 5 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 1 | 3 | 5 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ATX3 Sec | 110 | Plan | 200
|  |  | Actual | 79 |  |  | March, 2020 Wed: 6; March, 2020 Tue: 2; March, 2020 Wed: 26; March, 2020 Wed: 11; April Sat: 4; April Mon: 1; April Fri: 10; April Sun: 3; MAY Thu: 15; MAY Sat: 1
|  | 120 | Plan | 100
|  |  | Actual | 26 |  |  | March, 2020 Tue: 10; March, 2020 Tue: 2; April Wed: 2; April Sat: 5; April Sat: 4; April Sun: 2; April Mon: 1
|  | 130 | Plan | 44
|  |  | Actual | 28 |  |  | March, 2020 Tue: 2; March, 2020 Sat: 2; March, 2020 Tue: 3; April Wed: 5; April Sat: 4; April Sun: 1; April Mon: 8; April Tue: 1; April Sun: 1; MAY Sat: 1
|  | 140 | Plan | 1224
|  |  | Actual | 116 |  |  | April Wed: 8; April Sun: 4; April Mon: 3; April Tue: 8; April Wed: 23; April Thu: 8; April Fri: 18; April Sat: 2; April Sun: 11; April Mon: 10; April Tue: 10; April Sat: 8; MAY Sat: 3
|  | 150 | Plan | 258
|  |  | Actual | 18 |  |  | April Sun: 12; April Fri: 1; April Sun: 1; April Sat: 4
|  | 160 | Plan | 524
|  |  | Actual | 83 | 34 | 1 | March, 2020 Wed: 6; March, 2020 Tue: 4; March, 2020 Sat: 9; March, 2020 Sun: 8; March, 2020 Mon: 8; March, 2020 Tue: 8; April Sun: 4; April Sun: 14; April Sun: 7; April Fri: 3; April Sat: 7; April Sat: 2; MAY Sat: 1; MAY Thu: 1
|  | 170 | Plan | 10
|  |  | Actual | 8 | 4 | 4 | March, 2020 Wed: 2; March, 2020 Thu: 2
|  | 180 | Plan | 0
|  |  | Actual | 0
|  | 190 | Plan | 0
|  |  | Actual | 0
|  | Sub Total | Plan | 2360 | [33 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 358 | 38 | 5 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 26 | 0 | 0 | 11 | 0 | 0 | 5 | 13 | 2 | 0 | 0 | 8 | 8 | 8 | 0 | 4 | 14 | 0 | 0 | 15 | 0 | 0 | 13 | 24 | 12 | 9 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 13 | 18 | 11 | 10 | 0 | 0 | 0 | 14 | 0 | 4 | 0 | 0 | 0 | 0 | 16 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AK2 Sec | 170 | Plan | 550
|  |  | Actual | 550 | 550 | 544 | March, 2020 Fri: 6
| SMMO Sec | 130 | Plan | 16
|  |  | Actual | 8 |  |  | March, 2020 Sat: 8
|  | 140 | Plan | 64
|  |  | Actual | 32 |  |  | March, 2020 Mon: 12; March, 2020 Wed: 12; March, 2020 Fri: 8
|  | 160 | Plan | 32
|  |  | Actual | 16 |  |  | March, 2020 Mon: 8; March, 2020 Wed: 8
|  | Sub Total | Plan | 112
|  |  | Actual | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 20 | 0 | 20 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SMIS Sec | 170 | Plan | 3
|  |  | Actual | 3 | 3 |  | March, 2020 Thu: 3
IN | PS Prim | 130 | Plan | 3
|  |  | Actual | 2 | bar: MAY Fri; MAY Fri
|  | 140 | Plan | 1
|  |  | Actual | 0
|  | 180 | Plan | 8
|  |  | Actual | 1 | bar: April Wed
|  | 170 | Plan | 12
|  |  | Actual | 11 |  | 11
|  | Sub Total | Plan | 24
|  |  | Actual | 23 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| PS Sec | 130 | Plan | 4
|  |  | Actual | 4 | 4 |  | MAY Fri: 4
|  | 170 | Plan | 192
|  |  | Actual | 180 |  |  | March, 2020 Thu: 6; March, 2020 Fri: 22; March, 2020 Sat: 4; March, 2020 Sun: 7; March, 2020 Mon: 8; March, 2020 Tue: 7; April Sun: 27; April Tue: 14; April Wed: 10; April Thu: 5; April Sun: 1; April Sat: 2; April Wed: 56; MAY Fri: 10; MAY Sat: 1
| SOUE Prim | 130 | Plan | 3
|  |  | Actual | 2 |  |  | April Thu: 2
|  | 140 | Plan | 1
|  |  | Actual | 0
|  | 170 | Plan | 7
|  |  | Actual | 2 |  |  | April Thu: 2
|  | 180 | Plan | 1
|  |  | Actual | 0
| SOUE Sec | 130 | Plan | 6
|  |  | Actual | 6 |  |  | April Thu: 6
|  | 170 | Plan | 62
|  |  | Actual | 62 |  | 44 | March, 2020 Sun: 10; April Thu: 8
|  | Sub Total | Plan | 68
|  |  | Actual | 68 | 0 | 44 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Instrument Prim |  |  | Plan | 474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 369 | 163 | 247 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 8 | 0 | 17 | 1 | 0 | 0 | 1 | 0 | 4 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 | 6 | 2 | 2 | 0 | 0 | 0 | 2 | 5 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 4 | 1 | 3 | 5 | 1 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Instrument Sec |  |  | Plan | 3289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 1219 | 591 | 593 | 10 | 0 | 0 | 12 | 0 | 0 | 8 | 0 | 20 | 0 | 20 | 6 | 8 | 0 | 0 | 0 | 18 | 26 | 3 | 28 | 11 | 0 | 0 | 5 | 13 | 2 | 0 | 4 | 15 | 16 | 15 | 0 | 4 | 41 | 0 | 14 | 25 | 5 | 0 | 13 | 25 | 12 | 9 | 23 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 32 | 15 | 18 | 11 | 10 | 56 | 0 | 0 | 14 | 14 | 5 | 0 | 0 | 0 | 0 | 16 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
EL | ATX4 Prim | 120 | Plan | 8
|  |  | Actual | 0
|  | 130 | Plan | 1
|  |  | Actual | 0
|  | 140 | Plan | 42
|  |  | Actual | 0
|  | 150 | Plan | 4
|  |  | Actual | 0
|  | 160 | Plan | 16
|  |  | Actual | 0
|  | 170 | Plan | 71
|  |  | Actual | 61 |  | 18 | March, 2020 Tue: 18; March, 2020 Wed: 7; March, 2020 Sat: 5; March, 2020 Thu: 8; April Sun: 4; April Fri: 1
|  | Sub Total | Plan | 142
|  |  | Actual | 61 | 0 | 18 | 0 | 0 | 18 | 7 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ATX4 Sec | 170 | Plan | 186
|  |  | Actual | 182 | 182 | 182
| ASUE Sec | 170 | Plan | 134
|  |  | Actual | 134 | 134 |  | March, 2020 Wed: 27; March, 2020 Thu: 38; March, 2020 Fri: 38; March, 2020 Sat: 27; March, 2020 Thu: 4
| SS Prim | 120 | Plan | 1
|  |  | Actual | 0
|  | 130 | Plan | 1
|  |  | Actual | 0
|  | 140 | Plan | 3
|  |  | Actual | 0
|  | 150 | Plan | 1
|  |  | Actual | 0
|  | 160 | Plan | 2
|  |  | Actual | 0
|  | 170 | Plan | 10
|  |  | Actual | 10 |  |  | March, 2020 Mon: 10
|  | 180 | Plan | 2
|  |  | Actual | 0
|  | Sub Total | Plan | 20
|  |  | Actual | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SS Sec | 170 | Plan | 58
|  |  | Actual | 27 |  |  | March, 2020 Thu: 2; March, 2020 Mon: 2; March, 2020 Wed: 3; March, 2020 Sat: 11; April Sat: 6; MAY Thu: 3
| SS1 Prim | In active | Plan | 5
|  |  | Actual | 1 | bar: April Wed
|  | 170 | Plan | 5
|  |  | Actual | 0
| SS2 Sec | 190 | Plan | 6
|  |  | Actual | 0
| TLF Sec | 170 | Plan | 44
|  |  | Actual | 26 |  | 25 | bar: MAY Sun
| RT Sec | 170 | Plan | 14
|  |  | Actual | 14 | 14 | 12 | April Thu: 2
| STVN Prim | 110 | Plan | 2
|  |  | Actual | 0
|  | 140 | Plan | 2
|  |  | Actual | 0
|  | 170 | Plan | 10
|  |  | Actual | 5 |  |  | March, 2020 Mon: 5
|  | 180 | Plan | 6
|  |  | Actual | 0
|  | Sub Total | Plan | 20
|  |  | Actual | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| STVN Sec | 110 | Plan | 12
|  |  | Actual | 0
|  | 130 | Plan | 6
|  |  | Actual | 0
|  | 140 | Plan | 42
|  |  | Actual | 0
|  | 150 | Plan | 16
|  |  | Actual | 0
|  | 160 | Plan | 24
|  |  | Actual | 1 | bar: April Wed
|  | 170 | Plan | 12
|  |  | Actual | 11 |  |  | April Wed: 6; April Thu: 3; April Wed: 2
|  | Sub Total | Plan | 112
|  |  | Actual | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SKUD Sec | 170 | Plan | 28
|  |  | Actual | 0
Total Prim |  |  | Plan | 192
|  |  | Actual | 77 | 0 | 18 | 0 | 0 | 18 | 7 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Sec |  |  | Plan | 582
|  |  | Actual | 395 | 330 | 219 | 0 | 0 | 0 | 27 | 38 | 38 | 27 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 3 | 4 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AOVK | HVAC Sec | 130 | Plan | 58
|  |  | Actual | 48 |  |  | April Fri: 4; April Sat: 12; MAY Fri: 32
|  | 170 | Plan | 242
|  |  | Actual | 191 |  |  | March, 2020 Tue: 17; March, 2020 Sun: 8; March, 2020 Mon: 7; March, 2020 Tue: 14; April Sun: 4; April Mon: 20; April Tue: 3; April Sat: 4; April Sat: 10; MAY Sat: 20; MAY Sun: 20; MAY Mon: 27; MAY Tue: 34; MAY Fri: 2; MAY Mon: 1
|  | Sub Total | Plan | 300 | 0 | 0 | March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0; March, 2020 Wed: 0; March, 2020 Thu: 0; March, 2020 Fri: 0; March, 2020 Sat: 0; March, 2020 Sun: 0; March, 2020 Mon: 0; March, 2020 Tue: 0
|  |  | Actual | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 8 | 7 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 20 | 3 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 27 | 34 | 0 | 0 | 34 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SF | AUPT Sec | 170 | Plan | 298
|  |  | Actual | 222 |  | 170 | March, 2020 Sun: 21; March, 2020 Fri: 14; March, 2020 Sun: 14; April Thu: 3
| AUGPT Sec | 170 | Plan | 58
|  |  | Actual | 55 |  |  | March, 2020 Sun: 7; March, 2020 Wed: 1; March, 2020 Sat: 7; March, 2020 Sun: 36; April Thu: 4
Total SF Sec |  |  | Plan | 356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Actual | 277 | 0 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 1 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0