{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["ПОД"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"ПОД","index":0,"n_rows":15,"n_cols":9,"rows_kept":15,"cut":false,"hidden":false,"merged":[[0,1,0,5],[3,1,3,2],[0,7,4,7]]}
[null,null,null,null,null,null,null,"ИСТИНА ИЛИ ЛОЖЬ в ячейке при условии что диапазон пересекается с диапазоном"]
[]
[null,null,null,"Сформировать график за период","2020-01-01","2020-12-31"]
[]
[null,null,"СОСТАВЛЕН НА:",{"$f":"TODAY()","v":"2020-06-01"}]
[]
[null,"№ п/п","Проект, акт на др., ДВ, тех. решение","Наименование работ","Директивный срок начала работ","Директивный срок завершения работ",null,"РАБОТЫ ЗАДАНОГО ПЕРИОДА","РАБОТЫ ТЕКУЩЕГО ПЕРИОДА"]
[null,"Столбец1","Столбец2","Столбец3","Столбец4","Столбец5",null,"Столбец 6","Столбец 7"]
[null,1,"Акт №1/1 от 15.01.2020","Демонтаж вертикальных связей (РД 5401-КМ лист 2, 31, 32)","2020-01-10","2020-02-02",null,{"$f":"SUMPRODUCT((E9>=$E$3)*(F9<=$F$3))>1","v":false},{"$f":"MEDIAN(Таблица2[[#This Row],[Столбец4]:[Столбец5]],$D$5+30)=$D$5+30","v":false}]
[null,2,"Акт №2/1 от 31.01.2020","Демонтаж  временных сборочных и монтажных приспособлений и площадок ±0.000, +90.450, +77.250, +69.250, +57.450, +51.450","2020-03-01","2020-08-31",null,false,{"$f":"MEDIAN(Таблица2[[#This Row],[Столбец4]:[Столбец5]],$D$5)=$D$5","v":true}]
[null,3,"Акт №3/1 от 31.01.2020","Демонтаж  временных сборочных и монтажных приспособлений и площадок на +43.850, +37.400, +31.400, +24.250, +17.800, +9.400","2020-03-01","2020-05-31",null,false,{"$f":"MEDIAN(Таблица2[[#This Row],[Столбец4]:[Столбец5]],$D$5)=$D$5","v":false}]
[null,4,"Акт №4/1 от 03.02.2020","Демонтаж существующего отклоняющего шкива  и породного бункера","2020-04-01","2020-08-31",null,false,{"$f":"MEDIAN(Таблица2[[#This Row],[Столбец4]:[Столбец5]],$D$5)=$D$5","v":true}]
[null,5,"Акт №1","АКЗ м/к башенного копра","2020-01-13","2020-08-04",null,false,{"$f":"MEDIAN(Таблица2[[#This Row],[Столбец4]:[Столбец5]],$D$5)=$D$5","v":true}]
[null,6,"Акт №5/1 от 03.02.2020","Монтаж ограждений проемов и площадок на отм. ±0.000, +5.700, +9.600, +18.000, +21.360, +21.600, +24.400, +31.600, +37.600, +44.000, +51.600, +57.600, +69.400, +77.400, +84.600, +90.600","2019-12-01","2019-12-10",null,{"$f":"SUMPRODUCT((E14>=$E$3)*(F14<=$F$3))>1","v":false},{"$f":"MEDIAN(Таблица2[[#This Row],[Столбец4]:[Столбец5]],$D$5)=$D$5","v":false}]
[null,7,"Акт №6/1 от 03.02.2020","Устройство временного перекрытия на отм. – 0.182 из листа рифленого толщиной 8мм. с установкой по периметру ограждения высотой 1200мм","2019-12-01","2021-12-02",null,{"$f":"SUMPRODUCT((E15>=$E$3)*(F15<=$F$3))>1","v":false},{"$f":"MEDIAN(Таблица2[[#This Row],[Столбец4]:[Столбец5]],$D$5)=$D$5","v":true}]