{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["База актов ","журнал работ"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"База актов ","index":0,"n_rows":12,"n_cols":19,"rows_kept":12,"cut":false,"hidden":false,"merged":[]}
[null,"НА",null,null,null,"дата начала","дата окончания","дата акта",null,null,"НР","ПОР","МАТ","ИСХ","ПР","СНИП","РЕЗУЛЬТ","КЭ","ДС"]
["Номер п/п","Номер акта","Наименование работ","L","V","дата начала","дата окончания","дата акта","ИД","напечатан","автоназвание работ","последующие работы","материалы из списка","исп.схема","проект","СНИП","результаты экспертиз, лабораторных исследований и иных","кол-во экз","дополнительные сведения"]
[1,"1-РТ","Разработка траншеи на ПК00+00-ПК01+00; ","100 м ","256 м3","2021-01-01","2021-01-05","2021-01-06",null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":"Разработка траншеи на ПК00+00-ПК01+00; 100 м 256 м3"},"устройство песчаной подушки","грутн с отвала","1-РТ","апапапап","СП111.022020.9898","хорошо",2,"нет"]
[2,"2-РТ","Забивка свай"," 15 шт",null,"2021-01-01","2021-01-03","2021-01-06",null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":"Забивка свай 15 шт"},"какие-то работы","сваи","1-ЗБ","апапапап","СП111.022020.9899","отлично",2,"нет"]
[3]
[4,null,null,null,null,null,null,null,null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":""}]
[5,null,null,null,null,null,null,null,null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":""}]
[6,null,null,null,null,null,null,null,null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":""}]
[7,null,null,null,null,null,null,null,null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":""}]
[8,null,null,null,null,null,null,null,null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":""}]
[9,null,null,null,null,null,null,null,null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":""}]
[10,null,null,null,null,null,null,null,null,null,{"$f":"Таблица1[[#This Row],[Наименование работ]]&Таблица1[[#This Row],[L]]&Таблица1[[#This Row],[V]]","v":""}]

{"sheet":"журнал работ","index":1,"n_rows":1,"n_cols":2,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["дата","вид работ"]