{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Лист1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Лист1","index":0,"n_rows":27,"n_cols":16,"rows_kept":27,"cut":false,"hidden":false,"merged":[[6,3,6,13],[6,0,7,0],[6,1,7,1],[6,2,7,2],[6,14,7,14],[6,15,7,15]]}
[{"$f":"TODAY()","v":"2025-06-11"}]
[]
["План.кол-во на месяц, шт",35]
["Факт.кол-во за месяц, шт",{"$f":"IF(N9=\"100%\",(N9+N10+N11+N12+N13+N14+N15+N16+N17+N18+N19+N20+N21+N22+N23+N24),0)","v":0}]
["Отклонение, %",{"$f":"IF(N10=\"100%\",(N10+N11+N12+N13+N14+N15+N16+N17+N18+N19+N20+N21+N22+N23+N24+N25),0)","v":0}]
[]
["Шифр","Дата заявки","План.дата поставки в МАК","Этапы производства",null,null,null,null,null,null,null,null,null,null,"Дней до поставки на МАК","Причина задержки"]
[null,null,null,"2D дизайн","Согласование дизайна","3D дизайн","Управ.программы","Обраб.центр","Термообработка","Обраб.центр","Электроэрозионная прошивка","Электроэрозионная вырезка","Сборка","Готовность, %"]
["МАК.1500-45","2025-05-31","2025-06-10","+","+","+","+","+","-","-","-","-","-",null,{"$f":"C9-$A$1","v":-1}]
["МАК.0760-04","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,{"$f":"C10-$A$1","v":19}]
["МАК.2420-22","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.1336-05","2025-05-31","2025-06-30","+","+","+","+","+","+","-","-","-","-",null,19]
["МАК.0366-01","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.0905-02","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.0366-25","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.0766-25","2025-05-31","2025-06-30","+","+","+","-","-","-","-","-","-","-",null,19]
["МАК.0420-64","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.0420-64","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.0082-04","2025-05-31","2025-06-30","+","+","+","+","+","+","+","+","-","-",null,19]
["МАК.1500-50","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.1500-61","2025-05-31","2025-06-30","+","+","+","+","+","+","+","-","-","-",null,19]
["МАК.1500-76","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,{"$f":"C22-$A$1","v":19}]
["МАК.1319-05","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
["МАК.1232-05","2025-05-31","2025-06-30","+","+","+","+","+","-","-","-","-","-",null,19]
[]
[]
["Ответственный "]